## Blank Table
Resource Name/Type | Location |  | Side | Construction Activity | Permitted Activity | Controlling Criteria | Special Provision? | Comments including any permit expiration dates
| Beginning STA | Ending STA |  |  |  | or agreement

## Example
Resource Name/Type | Location |  | Side | Construction Activity | Permitted Activity | Controlling Criteria | Special Provision? | Comments including any permit expiration dates
| Beginning STA | Ending STA |  |  |  | or agreement
Stream 1 Buffer | 114+00 | 115+00 | both | culvert construction | Activities within 50 ft of the proposed culvert are exempt | Memo from EPD date 6/8/06 re: Buffer variance issues |  | Roadway drainage exemption - work beyond 50 ft of the proposed culvert will require a buffer variance or written permission from EPD prior to commencement of the activity.
Stream 1 | 120+90 | 121+10 | Rt | rip rap placement | 25 linear ft and 0.01 acre of stream impacts | Section 404 of the CWA - NWP 14 |  | Any additional fill other than what is shown on plans will require a permit modification or a new permit prior to commencement of the activity. Permit expires June 30, 2011.
Wetland 2 | 119+15 | 121+26 | Lt | rip rap placement | 0.5 permanent impact and 0.5 temporary impact | Section 404 of the CWA - NWP 14 |  | Impacts are permitted to the Right-of-Way. Permit expires June 30, 2011.
ESA | 210+20 | 212+90 | Rt | roadway construction | Refer to Special Provision 107.23 g | NEPA Document | 107.23g | Contractor shall direct questions to the Engineer, and the Engineer shall contact Environmental Services if necessary for resolution.
Eligible Historic Resource | 213+99 | 214+75 | Lt | roadway construction | Refer to Special Provision 107.23 g | Section 106 Commitment | 107.23g | Contractor shall direct questions to the Engineer, and the Engineer shall contact Environmental Services if necessary for resolution.
Migratory Birds | 212+90 | 213+55 | both | demolition of old bridge and construction of new bridge | Refer to Special Provision 107.23 g | Migratory Bird Treaty Act | 107.23g | The Office of Environmental Services shall be contacted prior to installation of exclusionary devices. Contractor shall direct questions to the Engineer, and the Engineer shall contact Environmental Services if necessary for resolution.
Protected species | 212+90 | 213+55 | both | demolition of old bridge and construction of new bridge | Refer to Special Provision 107.23 g | Endangered Species Act | 107.23g | Contractor shall direct questions to the Engineer, and the Engineer shall contact Environmental Services if necessary for resolution.
Wetland 5 | 213+10 | 213+40 | Lt | temporary access | 0.75 acres of temporary impact to wetlands | Section 404 of the CWA - NWP 33 | 702 | Area disturbed by temporary access within the wetland shall be replanted in accordance with the specifications. Permit expires March 18, 2012.
EXAMPLE
EXAMPLE