DEPARTMENT OF TRANSPORTATION

STATE OF GEORGIA

SPECIAL PROVISION

PROJECT NUMBER:  XX

P.I. No.: 0000000

XX COUNTY

SECTION 150 – TRAFFIC CONTROL

Delete Subsection 150.6 and add the following:

150.6 Special Conditions:

- Lane Closures

The Contractor shall not install lane closures, shoulder closures (if applicable), pace traffic or move equipment or materials that interferes with traffic on  ____________________  (insert name of road)    between the hours of 6:00 am to 9:00 and 3:00 to 9:00 pm, (insert appropriate times) Monday through Friday (insert appropriate days of the week).

OR

- Single Lane Closures/Shoulder Closures (If Shoulder Closures have different time restrictions than single lane closures Shoulder closure times will be separated in own category. Need to designate if LC, SC or both)

Single lane/shoulder closures are allowed daily between the hours of 9:00 am to 4:30 pm and 7:00 pm to 6:00 am Monday through Thursday.

Single lane/shoulder closures are allowed daily between the hours of 9:00 am to 3:30 pm Friday and 7:00 pm Friday to 6:00 am Monday.

- Double lane closures:

Double lane closures are allowed daily between the hours of 11:00 pm to 5:00 am Sunday thru Thursday.

Double lane closures are allowed between the hours of 11:00 pm Friday to 7:00 am Saturday.

Double lane closures are allowed between the hours of 11:00 pm Saturday to 7:00 am Sunday.

- Interstate Lane Closures:

- Single Lane Closures/Shoulder Closures (If Shoulder Closures have different restrictions than single lane closures, Shoulder closure times will be separated in own category.  Need to designate if LC, SC or both)

Single lane/shoulder closures are allowed daily between the hours of 9:00 pm to 5:00 am Sunday  through Thursday

Single lane/shoulder closures are allowed between 9:00 pm Friday and 10:00 am on Saturday.

Single lane/shoulder closures are allowed between 9:00 pm Saturday and 12:00 pm on Sunday.

- Double lane closures:

Double lane closures are allowed daily between the hours of 11:00 pm to 5:00 am Sunday thru Thursday.

Double lane closures are allowed between the hours of 11:00 pm Friday to 7:00 am Saturday.

Double lane closures are allowed between the hours of 11:00 pm Saturday to 7:00 am Sunday.

- Detour

The Contractor may close and detour CS 435/Garretts Ferry Road over Chattahoochee River for a maximum of 90 calendar days using the detour as shown in the Project Plans. Failure to re-open the roadway to traffic by the end of the specified time will result in the assessment of Liquidated Damages as listed in the Special Provision 108.08.C.

OR

The Contractor may close and detour XXXX Road between SR XX and XX Court for a maximum of 180 calendar days as shown in the Project Plans.

OR

The Contractor may close and detour Tugalo Short Cut Road for 120 calendar days as shown in the Project Plans.  Tugalo Short Cut Road shall be constructed according to the typical section and reopened on at least the 19 MM Superpave pavement course.

OR

The Contractor may close and detour Edward Road at SR 42 for a maximum of 180 calendar days as shown in the Project Plans.

- Maintaining School Flashing Beacons Assembly

The Contractor shall maintain the existing school flashing beacon assembly within the Project Limits at all times.  This may require the installation of temporary poles, conduit, wire, and temporary relocation until the new school flashing beacon assembly can be activated.  Failure adhere to the restrictions will result in the assessment of damages as listed in Special Provision 108.08.C.2.

- Miscellaneous:

- Milled Surfaces:

All milled surfaces shall be covered before (they are opened to traffic or shall be covered within x days).  Failure to cover milled surfaces with asphaltic concrete mix as required by the applicable typical section shall be considered a failure to comply with the requirements of Section 150 Traffic Control and shall result in the assessment of non-refundable deductions as specified in Special Provision Section 150.7.01 Enforcement and Adjustments.

OR

The Contractor shall cover milled surfaces before they are open to traffic.

OR

The Contractor shall cover milled surfaces within x days.

- Portable Signs:

For this project, the advance warning signs specified in Subsection 150.3.04 shall be portable signs.

- District 2 Masters Shutdown:

(Project Manager shall contact the District Construction Manager to verify which should be used)

Beginning the Friday before the Masters Golf Tournament, which begins the Monday of the first full week in April and extending to the Monday after the Masters, the Contractor shall cease all operations except for maintaining Traffic Control and Erosion Control.  During this time period, the Contractor shall provide a clean and neat appearance throughout the project including, but not limited to trash pickup, mowing, dressing, grassing and or mulching.  Failure to cease operations during the Masters Golf Tournament will result in the assessment of Liquidated Damages.  Should the Masters Golf Tournament extend beyond schedule, the Contractor shall maintain the above noted restrictive work hours until the day following the last scheduled day of the tournament.

OR

No lane closures beginning the Wednesday before the Masters Golf Tournament, which typically begins the Monday of the first full week in April and extending to the Monday after the Masters.  Should the Masters Golf Tournament extend beyond schedule, the Contractor shall maintain the above noted restrictive work hours until the day following the last scheduled day of the tournament. (Project Manager shall contact the District Construction Engineer to verify which should be used)

- University of Georgia Home Football Games:

The Contractor shall not install lane closures, pace traffic or move equipment or materials that interfere with traffic between 3:00 pm the Friday before a University of Georgia home football game to 9:00 Pm the Sunday after the game throughout the Project.  It is the responsibility of the Contractor to verify the schedule and plan The Work accordingly.

- Atlanta Falcons Home Football Games:

The Contractor shall not install lane closures, pace traffic or move equipment or materials that interfere with traffic three hours prior to and two hours after Atlanta Falcons home football games.  It is the responsibility of the Contractor to verify the schedule and plan The Work accordingly.

- Six Flags Over Georgia:

Contractor shall not close exits to Six Flags Over Georgia simultaneously during operational dates.  No ramp closures shall occur during operational hours.  It is the responsibility of the Contractor to verify the operational hours and dates.

- District 3 Atlanta Motor Speedway NASCAR Race Shutdown:

Beginning the Wednesday before the NASCAR Atlanta Motor Speedway Race and extending to the Tuesday after the NASCAR Race, the Contractor shall cease all operations except for maintaining Traffic Control and Erosion Control.  During this time period, the Contractor shall provide a clean and neat appearance throughout the project including, but not limited to trash pickup, mowing, dressing, grassing and or mulching.  Failure to cease operations during the NASCAR Atlanta Motor Speedway Race will result in the assessments of Liquidated Damages.

- Traffic Loops

Traffic Loops removed or damaged during the resurfacing shall be replaced and operational within 4 days of applying final surface course. Failure to have replacement traffic loops operational within the time specified will result in the assessment of penalties as specified in Special Provision 108.08.

- Leaf Season Lane Closure Restrictions

No lane closures, flagging operations, or any other activity will be allowed that affects traffic between 8:00 am to 7:00 pm on Saturdays and Sundays, respectively, between October 1st to November 15th on a yearly basis for Leaf Season.

Office