Special Provision Submittals Cover Sheet:

Project Number/PI #:

County:

Date Submitted:

Letting Date:

Project Manager:

Description of project:

Statement addressing weekend closures:  tell if weekend lane closures are not needed or if you have not discussed weekend lane closures.

Road Closures for bridge replacement: (include bride plans)

# of Spans:

Type of piles:

INSTRUCTIONS FOR SPECIAL PROVISIONS:

E-MAIL Special Provision submittals to the State Construction Office, attention: X.

Use the following format for the subject:

PI # XXXXXX_YYYYYYY County Special Provisions 150.6 and 108.08 for approval

Special Provisions 150.6 and 108.08 are to be submitted for Approval when requesting FFPR.

Include a Special Provision submittal Cover Sheet with each special Provision that is submitted to the State Construction Office for review.  This information may be placed in the body of the e-mail. All special provisions shall be submitted electronically in Word format.

No submittals shall come directly from consultants.  All submittals shall be routed through the project manager.

Do not include statements in your submittal that are already in specifications or special provisions.

SP 150.6 – Is for traffic control special conditions (specifically – lane closures), do not add things that are not about traffic control.

SP 108 - Is for traffic control penalties and intermediate completion dates.

The dates, times and penalties for SP 150.6 and SP 108 are to be discussed at the field plan review with input from the construction representative.

Use the attached templates to standardize special provision language.

Do not use the words “unduly” or “visibly” in SP 150.6.

Provide a current date on every special provision.

Use the word “calendar” with days when noting the number of days a road is closed.

Make sure any intermediate completion times do not exceed the project completion date.

Make sure all intermediate completion times do not contradict other intermediate completion times.

The attached special provisions are to be used as a guide only.  They are samples of how all special provisions should look.  The template and wording are an effort to standardize the submittals to the construction office.

Each special provision section 150.6 is to contain the work hours that are specific to that project.

Other items that are needed may be added such as, but not limited to:

Use of portable signs

Use of changeable message boards

Triple or more lane closures

Special events that are unique to the area (Masters Golf Tournament – District 2)

Guardrail removal and replacement

Covering milled surfaces

Logo signs

Fence removal and replacement

The items listed on the sample special provisions are there for example.  Write your special provision for your project and only add those items that are applicable to your project.