|  | # (Reporting Period) # PROGRAM MANAGER COMPLIANCE REPORT |
| --- | --- |

|  | ### September 9, 2022 ### Marshall Troup ### District 2 Program Manager ### ASST. Office Head Chandria L. Brown, PE |  |
| --- | --- | --- |

Table of Contents

1.	Programmatic Overview	3

2.	PSRs, TPRO Comments, P6, TPRO Expanded Descriptions	4

2.1	PSRs and TPRO Comments	4

2.2	TPRO Contact Information	4

2.3	TPRO Expanded Descriptions	4

2.4	P6	5

3.	Financial Data	5

3.1	Account Balances	5

3.2	1625 Requests	7

4.	One on One Meetings/PM Compliance Reviews	8

4.1	One on One Meetings	8

4.2	PM Compliance Reviews	9

5.	Cost Estimates	9

5.1	Cost Estimate Status	9

6.	Milestone Queries (Including Escalations)	10

7.	Schedule Tracking	10

7.1	PCRFs	10

7.2	Initial Schedules	11

8.	Tracking for Specific Issues	11

9.	Contract Statuses	12

9.1	PM Managed Contracts	12

9.2	Future Task Orders	13

9.3	Regional Contracts (If Applicable)	14

10.	Local Government Coordination	14

10.1	Local Compliance Audits	14

10.2	MPO and Local Government Coordination	14

11.	Program Manager Meetings with Project Managers	15

11.1	Program Manager Meetings with Project Managers (At least once a month)	15

12.	Programmatic Meetings/Outreach/Roundtables	15

12.1	ROW and Let Status Meetings	15

13.	CATS Tracking	16

14. Special Assignments/Committee Status	20

14.1	Special Assignments	20

14.2	OPD Committee Members	21

15. Employee Training/Development (Certifications are required every 3 years)	21

15.1	LAP\PDP Training Status	21

# Programmatic Overview

District 2 Program Manager OPD Metrics for current Management Performance FY 2022 period (July 2022 – August 2022)

| Metric | Previous Period % met (May 2022 - June 2022) | Current Period % met | Met during period | Projected to Meet | FY Projected to Miss | Projected % Compliance through FY23 | OPD Performance Management Office Goal |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Metric #1 Projects with approved schedules | 79% | 91% | 35 | 39 | 0 | 100% | 90% |
| Metric #2 – PM Request PFPR on baseline | 0% | 0% | 0% | 0% | 0 | 100% | 85% |
| Metric #3 – PM Request FFPR on baseline | 100% | N/A | N/A | N/A | 0 | 100% | 85% |
| Metric #4 – PM Submit Concept Report | N/A | N/A | N/A | N/A | N/A | N/A | 85% |
| Metric #5 – Cost Estimates Within 1 Year | 93% | 86% | 24 | 28 | 4 | 100 | 95% |

*note table is example for discussions with AOH. The below is the executive summary for these metrics;

Metric #1 – 90% of programmed projects with approved schedules.

Metric #2 – 4 PFPR’s were scheduled to be requested during this period; 4 were missed. ACTION - 0018054 – LIBP schedule; 0008018, 0008019 & 0008017 – delays due to late preliminary design NTP; PCRFs to be submitted.

Metric #3 – No FFPR’s were schedule to be requested during this period.

Metric #4 – No concept reports were scheduled to be submitted during this period.

Metric #5  – 86% of cost estimates were updated during this period; ACTION – PMs are actively working to update all expired or soon to expire cost estimates.

| Total Program Amount | ROW Authorization Amount | CST Authorization Amount |
| --- | --- | --- |
| 1.3M | $23M | $259M |
| Total amt (SCP, PE, ROW, CST & UTL) active preconstruction projects | Amount programmed in the selected FY | Amount programmed in the selected FY |

| Project Manager (PM) | Number of Projects | # of Projects April‐22 |
| --- | --- | --- |
| Blocker, Brent (BB) | 11 | 11 |
| Edwards, Cassius (CE) | 11 | 11 |
| Johnson, Robert (RJ) | 13 | 13 |
| Smith, Andre (AS) | 11 | 11 |
| Williams, Samuel (SW) | 13 | 14 |
| Lovett, Christy | 0 | 0 |
| Team Total | 59 | 60 |

# PSRs, TPRO Comments, P6, TPRO Expanded Descriptions

## PSRs and TPRO Comments

All TPRO comments are reviewed by the Program Manager. Per the monthly PM compliance checks, the following table summarizes compliance with having the project manager field up to date including content and the contact information in TPRO. Note the percentages reflect  the average compliance for the reporting period.

| Project Manager | Number of Projects | Project Manager Field Up to Date |  | Notes | % Previous Average Compliance | % Average Compliance |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | May | June |  |  |  |
| Andy Clark | 11 | 11 | 11 |  | 100% | 100% |
| Bruce G. Anderson, Jr. | 11 | 11 | 11 |  | 100% | 100% |
| Frank Childs, Jr. | 13 | 13 | 13 |  | 100% | 100% |
| Travis McDonald | 9 | 9 | 9 |  | 100% | 100% |

The results of compliance audits can be found here: (provide location)

## TPRO Contact Information

Project Managers shall follow instructions for completing TPRO fields.

| Project Manager | Number of Projects | Consultant PM Name and Local Govt Blank |  | Notes | % Previous Average Compliance | % Average Compliance |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | May | June |  |  |  |
| Andy Clark | 11 | 0 | 0 |  | 100% | 100% |
| Bruce G. Anderson, Jr. | 11 | 0 | 0 |  | 100% | 100% |
| Frank Childs, Jr. | 13 | 0 | 0 |  | 100% | 100% |
| Travis McDonald | 9 | 0 | 0 |  | 100% | 100% |

## TPRO Expanded Descriptions

The following table summarizes compliance with the requirement to have the expanded project description field completed in TPro.

| Project Manager | Number of Projects | Projects with expanded TPRO fields |  | Status of Projects w/out expanded TPRO fields |  | %Previous Average Compliance | %Average Compliance |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | May | June |  |  |  |  |
| Andy Clark | 11 | 10 | 10 |  | 0% |  |  |
| Bruce G. Anderson, Jr. | 11 | 11 | 11 |  | 0% |  |  |
| Frank Childs, Jr. | 13 | 10 | 10 |  | 0% |  |  |
| Travis McDonald | 9 | 7 | 7 |  | 0% |  |  |

A copy of the TPRO expanded description data from the 411 query can be found here: (provide location)

## P6

The results of Compliance Audits are contained in the individual Project Manager (PM) compliance checks. The Program has recognized the P6 concerns related to schedule. Additional measures have been incorporated to the monthly project team meetings to address schedule issues. This schedule is to be reviewed as part of the monthly team meeting for accuracy for dates and percentage complete. The PM will then update P6 accordingly after the meeting. The following table summarizes compliance with having P6 updated for this grading period:

| Project Manager | Number of Projects | P6 is Updated |  | Notes | %Previous Average Compliance | %Average Compliance |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | May | June |  |  |  |
| Andy Clark | 11 |  |  |  |  |  |
| Bruce G. Anderson, Jr. | 11 |  |  |  |  |  |
| Frank Childs, Jr. | 13 |  |  |  |  |  |
| Travis McDonald | 9 |  |  |  |  |  |

# Financial Data

## Account Balances

Project Financial Reports are reviewed with each PM. The monthly budget totals are listed along with any PM actions needed flagged in red. The following data represents the Program financial estimates for projects by PM:

| Project Manager Name | Project Number | Activity | Contract Allotment | Inhouse Allotment | Balance | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Anderson Jr., Bruce G. | M006274 | MPE | $1,300,000.00 | $192,236.82 | $1,492,236.82 |  |
| Anderson Jr., Bruce G. | M006273 | MPE | $1,300,000.00 | $191,789.73 | $1,491,789.73 |  |
| Anderson Jr., Bruce G. | 0012865 | PE | $680,000.00 | $0.00 | $680,000.00 |  |
| Anderson Jr., Bruce G. | 0006253 | PESTP000600253 | $248,605.29 | $54,218.40 | $302,823.69 |  |
| Anderson Jr., Bruce G. | 0013617 | PE | $90,612.15 | $47,422.43 | $138,034.58 |  |
| Anderson Jr., Bruce G. | 0008017 | PE | $15,028.22 | $78,856.38 | $93,884.60 |  |
| Anderson Jr., Bruce G. | 0017970 | SCP | $46,642.52 | $18,627.76 | $65,270.28 |  |
| Anderson Jr., Bruce G. | 0013616 | PE | $4,475.67 | $41,907.45 | $46,383.12 |  |
| Anderson Jr., Bruce G. | 0013613 | PE | $2,015.26 | $35,670.30 | $37,685.56 |  |
| Anderson Jr., Bruce G. | 0010555 | PE | $0.00 | ($486.91) | ($486.91) |  |
| Childs Jr, Frank | 0013311 | PE | $1,676,245.98 | $511,357.72 | $2,187,603.70 |  |
| Childs Jr, Frank | 311400- | PENH0007502177 | $654,917.77 | $71,698.60 | $726,616.37 |  |
| Childs Jr, Frank | 222260- | SCP | $258,713.13 | $49,203.61 | $307,916.74 |  |
| Childs Jr, Frank | 0013628 | PE | $213,999.32 | $77,963.88 | $291,963.20 |  |
| Childs Jr, Frank | 0013578 | PE | $123,272.17 | $95,670.61 | $218,942.78 |  |
| Childs Jr, Frank | 262027- | PEEDS044100020 | $174,525.10 | $21,050.99 | $195,576.09 |  |
| Childs Jr, Frank | 231210- | PESTP092200006 | $8,509.66 | $100,232.57 | $108,742.23 |  |
| Childs Jr, Frank | 222260- | PEEDS054500038 | $95,369.53 | $21.52 | $95,391.05 |  |
| Childs Jr, Frank | 0013311 | SCP | $34,012.96 | $18,287.54 | $52,300.50 |  |
| Childs Jr, Frank | 231450- | PENH0008901026 | $3,026.34 | $12,702.05 | $15,728.39 |  |
| Childs Jr, Frank | 0012866 | PE | $0.00 | $0.00 | $0.00 |  |
| Childs Jr, Frank | 0012867 | PE | ($0.01) | $0.00 | ($0.01) |  |
| Childs Jr, Frank | 0013723 | PE | $1,312.55 | ($3,152.65) | ($1,840.10) |  |
| Clark, Jonathan Andrew | 0008019 | PE | $447,831.53 | $743,261.71 | $1,191,093.24 |  |
| Clark, Jonathan Andrew | 0008018 | PE | $776,091.46 | $1,747.04 | $777,838.50 |  |
| Clark, Jonathan Andrew | 0013577 | SCP | $0.00 | $364,554.30 | $364,554.30 |  |
| Clark, Jonathan Andrew | 0018007 | SCP | $280,000.00 | $0.00 | $280,000.00 |  |
| Clark, Jonathan Andrew | 0019043 | PE | $0.00 | $122,950.34 | $122,950.34 |  |
| Clark, Jonathan Andrew | 0015095 | PE | $55,707.20 | $0.00 | $55,707.20 |  |
| Clark, Jonathan Andrew | 0016829 | SCP | $989.93 | $13,684.34 | $14,674.27 |  |
| Clark, Jonathan Andrew | 0012868 | PE | $0.00 | $0.00 | $0.00 |  |
| Clark, Jonathan Andrew | 0013703 | PE | $0.00 | $0.00 | $0.00 |  |
| Clark, Jonathan Andrew | 0015959 | PE | $0.00 | $0.00 | $0.00 |  |
| Clark, Jonathan Andrew | 0017754 | SCP | $0.00 | $0.00 | $0.00 |  |
| McDonald, Travis S. | 0019181 | SCP | $1,800,000.00 | $199,170.47 | $1,999,170.47 |  |
| McDonald, Travis S. | 0018174 | PE | $50,000.00 | $231,025.92 | $281,025.92 |  |
| McDonald, Travis S. | 0018054 | PE | $49,576.25 | $181,155.82 | $230,732.07 |  |
| McDonald, Travis S. | 0018173 | PE | $50,000.00 | $156,880.87 | $206,880.87 |  |
| McDonald, Travis S. | 0018372 | PE | $0.00 | $154,362.03 | $154,362.03 |  |
| McDonald, Travis S. | 0018055 | PE | $50,000.00 | $103,130.43 | $153,130.43 |  |
| McDonald, Travis S. | 0018056 | PE | $0.00 | $147,576.51 | $147,576.51 |  |
| McDonald, Travis S. | 0017229 | SCP | $618.01 | $30,760.09 | $31,378.10 |  |
| McDonald, Travis S. | 0013704 | PE | $0.00 | $0.00 | $0.00 |  |
| McDonald, Travis S. | 0013707 | PE | $0.00 | $0.00 | $0.00 |  |

Location of PFR Reports: (Location)

| Total # Projects | # Negative PE Funds Balance | # FY23 PE Authorization Needed |
| --- | --- | --- |
| 60 | 7 | 1 (STIP amendment needed) |

## 1625 Requests

The following represents 1625 funding requests during this compliance period:

| Activity ID | Comment | Requested Date | Funding Status | Project Manager Name | PI Number |
| --- | --- | --- | --- | --- | --- |
| CST | Project has been completed and Final Acceptance received. | 8/17/2022 | Funds Denied | Anderson Jr., Bruce G. | 0007180 |
| PE | Requesting additional PE funding to advance through final design to construction. There are still outstanding reviews that will take place that will require funding (BFI/WFI, Bridge Plans, FFPR, etc...). The Let Date is moving to May 2024. | 8/30/2022 | New Request | Anderson Jr., Bruce G. | 0010555 |
| ROW | Additional funding is required to cover the current overdrawn balance on the project. | 7/19/2022 | Funds Denied | Anderson Jr., Bruce G. | 0007180 |
| ROW | Additional funding needed to cover inhouse ENG for project close out. increase by $1,453.46. | 8/31/2022 | Funding Verified | Anderson Jr., Bruce G. | 0007180 |
| ROW | CLEANING UP ROW CHARGES | 8/17/2022 | Funds Denied | Anderson Jr., Bruce G. | 0007180 |
| CST | Supplemental Agreement to add the missing pay item 441-0050 Concrete Slope Drain. The pay item for 441-0050 Concrete Slope Drain is required per plan Sheet 13-003. However, the Contract did not set up the line item for the Pay Item. The Concrete Slope, Drain is necessary to tie into the type 3 spillway per standard 9017J to convey the water down the slope. | 7/15/2022 | Funds Denied | Childs Jr, Frank | 0018218 |
| CST | THIS SUPPLEMENTAL AGREEMENT IS NEEDED TO ADD MISSING PAY ITEMS TO THE CONTRACT THAT WERE SHOWN TO BE PLACED PER PLANS AND ARE REQUIRED IN THE FIELD. THERE ARE FOUR (4) ITEMS THAT NEED TO BE ADDED AS FOLLOWS: (1) 550-3518 - SAFETY END SECTION 18 IN, SI, DE DRAIN, 6:1 SLOPE=42.00 EACH (2) 550-3524 - SAFETY END SECTION 24 IN, SIDE DRAIN, 6:1 SLOPE = 5.00 EACH (3) 550-3530 - SAFETY END SECTION 30 IN, SIDE DRAIN, 6:1 SLOPE - 2.00 EACH (4) 550-3430 - SAFETY END SECTION 30 IN, SIDE DRAIN, 4:1 SLOPE= 2.00 EACH, . ALSO, THESE ITEMS ARE NECESSARY FOR THE CONTINUITY OF OPERATIONS IN COMPLETING THE PROJECT. | 8/26/2022 | Program Confirmed | Childs Jr, Frank | 222170- |
| PE | Contract Balance: $468,931.33 Inhouse Balance: $52,914.29 This is a requested for additional PE of funds of $366,000.00 to fund the current task order #8 for Soil Survey work on this project. | 8/2/2022 | Funds Approved | Childs Jr, Frank | 222260- |
| PE | Contract: $1,300.55 Inhouse: -$700.94 This is a request to move $1300 dollars from contracts to inhouse to remove the negative balance of $700.54. | 7/15/2022 | Funds Denied | Childs Jr, Frank | 0013723 |
| PE | This is requested to authorize Preliminary Engineering (PE) for this passing lane project. This is an in-house design project in District 2(D2). Environmental is expected to be contracted through the Office of Environmental Services. | 9/6/2022 | New Request | Childs Jr, Frank | 0016818 |
| ROW | Additional funding is required for the continuation of ROW acquisition, for estimate judgement/settlement, relocation and other expenses. | 8/24/2022 | Funds Denied | Childs Jr, Frank | 0013614 |
| ROW | Additional funding required for the continuation of ROW acquisition, for estimate judgement/settlement, relocation and other expenses. | 8/24/2022 | Funds Approved | Childs Jr, Frank | 0013614 |
| CST | The Low Bid amount came in at $8,109,119.82 and the Locals requested and received additional funding from the ARC to cover the bid amount. Initially the project programmed amount ($6,619,095.13) was requested by 1625 and authorized. This request is for the remaining amount to cover the total cost. This is a bid adjustment request. | 7/26/2022 | Funds Approved | Clark, Jonathan Andrew | 0015096 |
| PE | 0015959 is a local let project that needed additional Archaeology work not previously scoped. The $11,500.00 has been added to the TIP and the admin mod was approved (email and project fact sheet attached) | 8/19/2022 | Funds Approved | Clark, Jonathan Andrew | 0015959 |
| PE | Need to move $50,000.00 from contract to in-house for charging | 9/2/2022 | New Request | Clark, Jonathan Andrew | 0008018 |

# One on One Meetings/PM Compliance Reviews

## One on One Meetings

Individual one-on-one meetings are held monthly by the District Program Manager with each PM. A Team SharePoint site was created to collect compliance data during these meetings. The data collected is reflected in this report. During the meetings, each project is discussed in detail and notes are added for each PI. The SharePoint site serves as a central location for all information associated with compliance tracking and allows for more efficient data collection as well as analysing historical data.

| Project Manager | Number of Projects | Meetings Held |  | Notes | %Previous Average Compliance | %Average Compliance |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | May | June |  |  |  |
| Andy Clark | 11 |  |  |  |  |  |
| Bruce G. Anderson, Jr. | 11 |  |  |  |  |  |
| Frank Childs, Jr. | 13 |  |  |  |  |  |
| Travis McDonald | 9 |  |  |  |  |  |
| Total | 44 |  |  |  |  |  |

## PM Compliance Reviews

All projects are reviewed by the District Program Manager to ensure OPD guidelines for updating project information are being followed. The Team SharePoint site is used to collect compliance data during these meetings. As part of compliance, PM’s are required to place in ProjectWise as part of updating the PMP, Project Status Updates Reports, whitepapers, progress reports, cost estimates, consultant progress reports, etc.

Program compliance reporting is located at the following link: (Location)

| Project Manager | Number of Projects | Team Meetings Held |  | %Previous Average Compliance | %Average Compliance |
| --- | --- | --- | --- | --- | --- |
|  |  | May | June |  |  |
| Andy Clark | 11 |  |  |  |  |
| Bruce G. Anderson, Jr. | 11 |  |  |  |  |
| Frank Childs, Jr. | 13 |  |  |  |  |
| Travis McDonald | 9 |  |  |  |  |
| Total | 44 |  |  |  |  |

| Project Manager | Number of Projects | PMP Updated |  | %Previous Average Compliance | %Average Compliance |
| --- | --- | --- | --- | --- | --- |
|  |  | May | June |  |  |
| Andy Clark | 11 |  |  |  |  |
| Bruce G. Anderson, Jr. | 11 |  |  |  |  |
| Frank Childs, Jr. | 13 |  |  |  |  |
| Travis McDonald | 9 |  |  |  |  |
| Total | 44 |  |  |  |  |

| Project Manager | Number of Projects | Project Status Reports Updated |  | %Previous Average Compliance | %Average Compliance |
| --- | --- | --- | --- | --- | --- |
|  |  | May | June |  |  |
| Andy Clark | 11 |  |  |  |  |
| Bruce G. Anderson, Jr. | 11 |  |  |  |  |
| Frank Childs, Jr. | 13 |  |  |  |  |
| Travis McDonald | 9 |  |  |  |  |
| Total | 44 |  |  |  |  |

# Cost Estimates

Utilizing the Program Delivery Cost Estimate Tracker, the status of updated cost estimates are tracked from date requested from SME through approval by Engineering Services. This can be further analyzed when reviewing PSR’s.  During the compliance review, the status of the cost estimates for ROW, CST, and UTL for each PM’s project are reviewed and recorded in the Team D2 Compliance Tracking. Details of the review and be found in the charts below:

| Project Manager | Number of Projects | Estimates in Compliance |  | Notes | %Previous Average Compliance | %Average Compliance |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | May | June |  |  |  |
| Andy Clark | 11 |  |  |  |  |  |
| Bruce G. Anderson, Jr. | 11 |  |  |  |  |  |
| Frank Childs, Jr. | 13 |  |  |  |  |  |
| Travis McDonald | 9 |  |  |  |  |  |
| Total | 44 |  |  |  |  |  |

*Cost estimate eligible projects

## 5.1	Cost Estimate Status

| Out of Date Cost Estimates |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Manager Name | Latest Estimate Date | Project ID | Short Description | Phase Code | Estimate Status |
| Anderson Jr., Bruce G. | 7/31/2021 | 0012865 | CR 102/HEREFORD FARM ROAD FROM SR 232 TO SR 383 - TIA | CST, UTL | Version 1 sent to Eng Svcs 8/29/2022 |
| Childs Jr, Frank | 7/24/2020 | 0013628 | SR 162 FROM CR 55/FLAT SHOALS ROAD TO CR 34/OLD SALEM ROAD | UTL | Version 1 submitted to Eng Svcs 9/6/2022 |
| Childs Jr, Frank | 7/24/2020 | 231450- | SR 49 FM JUST W. OF FELTON RD TO EAST OF MILLEDGEVILLE BYP | CST | Version 1 submitted to Eng Svcs 9/6/2022 |

# Milestone Queries (Including Escalations)

The Program has several controls in place to proactively assist Project Managers with upcoming milestones and missed milestones. The following is a summary of the milestone tracking:

- Utilized 411 queries for upcoming milestone.

- Baseline milestone dates are listed on the District SharePoint site.

- Review during PM on-on-one meetings

| Escalation Memo |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PM | Milestone Date | PI# | Description | To DPM | To AOH | To OH | Closed |  | Comment (s) | Outstanding |  |
| CE | 5/5/2022 | 0000821 | Missed Submit ROW Plans |  |  |  |  |  | late-need from PM | 1 |  |
| CE | 5/6/2022 | 0000820 | Missed Submit ROW Plans |  |  |  |  |  | late-need from PM | 1 |  |
| CE | 5/6/2022 | 0008666 | Missed Submit ROW Plans |  |  |  |  |  | late-need from PM | 1 |  |
|  |  |  |  |  |  |  |  | Outstanding Total |  |  | 3 |

# Schedule Tracking

## PCRFs

The Program utilizes the Action Tracker to track outstanding PCRFs. PCRF action items are closed when approval is received. Below is a summary of the open PCRF action items by project manager:

| PM | PI# | Date Initialed | Type/ Proposed Dates | SME Concurrence Request Date | To AOH | To OH | To Dir | To OPC | Comments/Reason | # Out- standing |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RJ | 17415 | 2/2/22 | ROW Auth - 12/15/23, Final plans 6/21/24, FFPR 7/1/24, Let 3/14/25 | 3/22/2022 | 4/12/2022 | 4/12/2022 |  | 5/17/2022 | Approved, Sch updated | 1 |
| BB | 0015955 | 5/16/22 | Row Auth - 6/2/22, Final plans 8/2023, FFPR 9/2023, Let 3/2024 | 5/26/2022 |  | 6/5/2022 |  | 6/13/2022 | Approved, Pending Sch updated | 1 |
|  |  |  |  |  |  |  | Total Outstanding |  |  | 2 |

## Initial Schedules

The Program utilized 411 queries to review projects without schedules reviewed with each PM. Details for PM compliance is shown on the compliance sharepoint site.

| Number of Projects with Schedules | Number of Projects Without Schedules |
| --- | --- |
| 45 | 14 |

- w/the Gov Est group developing schd/2 new projects & initial schd to be requested by PM/2 requests below

A copy of the 411 query is in the following folder on CDCOMMON (Y): (location)

# Tracking for Specific Issues

This Program utilizes document tracker on SharePoint and Asana Planner for tracking project issues such as external letters, decision matrix, cost comparisons. This should include any deliverables being tracked by OPD management.

The following details are from the current Programmatic Action Tracker:

| Task Name | Progress | Assigned To | Created Date | Due Date | Completed Date | Description |
| --- | --- | --- | --- | --- | --- | --- |
| US 441 RR Impacts Meeting - PI 0013613 & 0013617 | In progress | Anderson, Bruce G. | 05/24/2023 | 06/05/2023 |  | https://app.asana.com/0/1204746957331933/1204746957331936/f PM needs to complete Athens Railroad Package for Mrs. Nesbitt by June 5, 2023. |
| PI 0006253, 0019696, & 0019697 - SR 44 | In progress | Anderson, Bruce G. | 05/19/2023 | 06/02/2023 |  | https://app.asana.com/0/1204622221016517/1204622221016520/f 1) Mirror the amended changes in the design (Need to show representative trey Rhodes) - Roundabout showing landscaping in it – Grass/low bushes - Phase 1 showing brick pavers & sidewalks with sod - Ask VERG Office to be creative - Contact Tiffany Turner (Design Policy) to get VERG going – How long will it take? |
| Sexual Harassment Prevention Policy Memo FY23 | In progress | Troup, Marshall;Dempsey, Cherral M;Lovett, Christy | 02/10/2023 |  |  | https://app.asana.com/0/1203857814902573/1203857814902576/f Governor Brian P. Kemp signed an Executive Order for Preventing Sexual Harassment in the workplace, and an annual mandatory sexual harassment prevention training for all employees, as well as supervisor/manager-specific training is required. REQUIREMENTS: There are two different trainings, one for all employees and an another specifically for supervisors/managers. Both trainings can be completed anytime during the workday. The internal deadline for completion is Friday April 14, 2023. SUPERVISOR'S MUST TAKE BOTH TRAININGS in order to comply with the Governor’s policy. |
| Power BI Compliance Report Development - District Reps | In progress | Troup, Marshall;Dempsey, Cherral M;Lovett, Christy | 10/12/2022 | 01/20/2023 |  | https://app.asana.com/0/1203152553750115/1203152553750118/f The GDOT Program Managers and PMs in all 3 of the OPD South teams will have representation on the development of the Power BI Compliance Reports for the District 2, 3, 4 and 5 Capital Teams. Marshall Troup is the designated lead for the development and will keep Ms. Brown updated on the progress periodically. The representatives per group are as follows: District 2 Team Reps: Marshall Troup (Lead); Bruce Anderson District 3/4W Team Reps: Cherral Dempsey; Shanda Marsh; Antoinette Moseley District 5/4E Team Reps: Christy Lovett; Andre Smith |

# Contract Statuses

Project controls are being developed to effectively track the status of contracts. The following tables are comprised of the consultant contracts currently being managed by the District 2 team with the contract expiration dates. Monitoring this information will help ensure the team is aware of contracts due to expire and take action if needed.

## PM Managed Contracts

| Project ID | Contract Number | Prime Vendor Name | Project Manager Name | Current Contract Max Amount | Current End Date | Work Description | Days til Contract Expires |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 0008017 | 48400-265-MPOPD1800873 | TRANSYSTEMS CORPORATION | Bruce G. Anderson Jr. | $7,200,000.00 | 3/15/2024 | SR 15 from West Warthen Bypass to East Sparta Bypass | 276 |
| 0008018 | 48400-265-MPOPD1800874 | HNTB CORPORATION | Jonathan Andrew Clark | $7,700,000.00 | 12/31/2027 | SR 15 from CR 67/Ridge Road to North of CR 43/Mt Zion Road and West Warthen Bypass from North of CR 43/Mt Zion Road to SR 15 | 1662 |
| 0013311 | 48400-265-MPOPD1800871 | Mott MacDonald, LLC | Frank Childs Jr | $8,000,000.00 | 1/8/2024 | SR17 from Vinson Road/Wilkes Co. to N of Robinwood Lane/Elbert Co. | 209 |
| 0013578 | 48400-265-MPOPD1700813 | WSP USA, Inc. | Frank Childs Jr | $5,000,000.00 | 9/15/2025 | Engineering Design Services | 825 |
| 0013613 | 48400-265-MPOPDDES150163 | WSP USA, Inc. | Bruce G. Anderson Jr. | $8,000,000.00 | 6/16/2025 | Engineering Services for SR 24/US 441 from Madison Bypass to just North of Apalachee River/Ocone. Ref: RFQ-484-071514 | 734 |
| 0013616 | 48400-265-MPOPD1600452 | AECOM TECHNICAL SERVICES INC | Bruce G. Anderson Jr. | $3,790,337.94 | 12/15/2024 | Engineering Design Services, RFQ 484-111414 | 551 |
| 0013628 | 48400-265-MPOPD1700106 | PARSONS TRANSPORTATION GROUP | Frank Childs Jr | $6,570,000.00 | 6/30/2025 | SR 162 From CR 511/Brown Bridge Road To CR 34/Old Salem Road, SR 162 From CR 55/Flat Shoals Rd To CR 34/Old Salem Rd-GRTA | 748 |
| 0013628 | 48400-265-MPOPD2000314 | HDR ENGINEERING, INC. | Frank Childs Jr | $6,629,409.00 | 7/30/2024 | Right of Way Acquisition Services for SR 162; Newton/Rockdale Co; PI#0013628 and PI#231210- | 413 |
| 0013723 | 48400-265-MPOPD1700110 | AMERICAN ENGINEERS | Frank Childs Jr | $2,200,000.00 | 10/31/2024 | Engineering Design Services | 506 |
| 222260- | 48400-265-MPOPD1700814 | NV5 Engineers and Consultants | Frank Childs Jr | $9,100,000.00 | 7/21/2025 | Engineering Design Services | 769 |
| 262027- | 48400-265-MPOPDDES140583 | GRESHAM SMITH | Frank Childs Jr | $2,200,000.00 | 6/30/2026 | Engineering design services to widen 4.6 miles of SR 31/US441 | 1113 |

## Future Task Orders

| D2 Future Task Orders |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project ID# | Project Manager | Project Phase | Next OPD Metrics Milestone | Milestone BL Complete Date | Next Task Order | Proposed Scoping Meeting Date | Date Scoping Meeting Held | Status |
| 0008018/0008019 | Jonathan Clark | Preliminary Design | PM Request PFPR | 8/8/2022 | ​Final Design | 2/9/2022 | 3/3/2022 | Final Design package submitted to RTS 8/18/2022 |
| 0013311 | Frank Childs | Preliminary Design | PM Request PFPR | 6/28/2022 | ​Final Design | 7/15/2022 |  | Pending split and will absorb bridge project |
| 0013578 | Frank Childs | Preliminary Design | PM Request PFPR | 10/26/2022 | ​Final Design | 4/15/2022 | 6/15/2022 | PM determining type of task order needed |
| 0013628 | Frank Childs | Final Design | OPD Metrics Complete |  | Const Svcs | 9/2022 |  |  |
| 0013723 | Frank Childs | Preliminary Design | PM Request FFPR | 11/22/2021 | Const Svcs | 10/3/2022 |  |  |
| 231210- | Frank Childs | Final Design | OPD Metrics Complete |  | Const Svcs | 9/2022 |  |  |
| 262027- | Frank Childs | On Shelf | OPD Metrics Completed |  |  |  |  |  |
| 222260- | Frank Childs | Preliminary Design | PM Request PFPR |  | ROW Turnkey | 10/3/2022 |  | Confirming Scope with ROW |
| 0008017 | Bruce Anderson | Preliminary Design | PM Request PFPR |  | ROW Turnkey | 10/3/2022 |  | Confirming Scope with ROW |

## Regional Contracts (If Applicable)

|  | Expiration | # of TO | Contract Amt | Amount spent to date | Comments |
| --- | --- | --- | --- | --- | --- |
| Recompete- TOOPD1900741 (CHA) | 1/15/2024 | 12 active | $14 million | $4.5 million | No additional task orders to be added |
| TOOPD2101612 (Atkins) NTP 7/8/21 | 6/30/2024 | 16 active | $25 million | $2.4 million | 22 TO's being scoped (total projected $13.2 mill) |

# Local Government Coordination

The Program has multiple local government coordination efforts in place that individual Project Managers are responsible for organizing.

## Local Compliance Audits

During the first quarter of FY2023, local compliance was conducted by the District 2 team. The results are as follows:

| LAP Sponsor | P.I. No. | County | PM | Compliance Check - Mtg. Date | Compliance Check - Mtg. Location | OPD Findings - Compliant/Non-Compliant |
| --- | --- | --- | --- | --- | --- | --- |
| Columbia County | 0012865 | Columbia | Bruce Anderson | 7/29/2022 | Virtual | Compliant |
| Columbia County | 0008352 | Columbia | Bruce Anderson | 7/29/2022 | Virtual | Compliant |
| Columbia County | 0013704 | Columbia | Travis McDonald | 7/29/2022 | Virtual | Compliant |

| Projected Compliance Audit Schedule for Calendar Year 2022 |  |  |
| --- | --- | --- |
| Project Sponsor | Date of Compliance | Meeting Location |
| Augusta\Richmond | September 14, 2022 | Virtual |
| Columbia County | 7/29/2022 | Virtual |
| Barrow County | October 2022 | Virtual |
| Newton County | August 11, 2022 | Virtual |

## MPO and Local Government Coordination

The program provides status updates for numerous local governments and MPO’s on a quarterly basis. These updates incorporate all projects within the local area. The following table summarizes the number of projects by local sponsor. The final coordination spreadsheet for Q1 of FY 2022 can be found at the following link: (Location) The results are as follows:

| MPO Local Government Coordination |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Sponsor | Q1 |  | Q2 |  | Q3 |  | Q4 |  |
|  | Meeting | Distribution | Meeting | Distribution | Meeting | Distribution | Meeting | Distribution |
| Augusta\Richmond |  | Anticipate Sep 2022 |  |  |  |  |  |  |
| Columbia County |  | Anticipate Sep 2022 |  |  |  |  |  |  |
| Laurens County |  | Anticipate Sep 2022 |  |  |  |  |  |  |
| Newton County |  | Anticipate Sep 2022 |  |  |  |  |  |  |

# Program Manager Meetings with Project Managers

## Program Manager Meetings with Project Managers (At least once a month)

The Program has monthly team meetings that are organized and facilitated by the District Program Manager. These meetings have multiple objectives.

- Meeting with District personal for review of projects in program

- Review of OPD current policies/procedures

- Review of program’s let status projects

Some of the topics discussed at the meetings can are included in the following table:

| FY 2023 District 2 Team Meetings |  |
| --- | --- |
| Date | Topics |
| 7/30/2022 | Self Evaluations, Asana Tasks, Bi-annual Meetings, Contract Expirations, 18 mos Pre-Let Spreadsheet, ROW Status, Let Status, Local Gov’t Compliance and Coordination, New D2 Compliance Assignments, Cost Estimate Tracking, Procurement, PCRF’s |
| 8/23/2022 | EOY Evaluations, Asana Tasks, Bi-annual Meetings, Contract Expirations, 18 mos Pre-Let Spreadsheet, ROW Status, Let Status, Local Gov’t Compliance and Coordination, New D2 Compliance Assignments, Cost Estimate Tracking, Procurement, PCRF’s |

# Programmatic Meetings/Outreach/Roundtables

## ROW and Let Status Meetings

As part of the programmatic meetings, the applicable program projects are reviewed in ROW and Let Status. Meetings are not held for the months of November and December.

Summarization of FY 22 Status meetings to date:

| FY 2022 Month | # Projects ROW Status | # Projects Let Status |
| --- | --- | --- |
| July 2022 | 19 | 10 |
| August 2022 | 1 | 11 |

# CATS Tracking

| Requested By | Proj Id | Contract Num | Contract Description | TO# | Status | Type | Vendor | Executed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bruce G. Anderson Jr. | 0012865 | 48400-065-IGOFM1600206 | Additional federal funds have been added to the project. Supplemental PFA #2 is needed. |  | Submitted | PFA - Project Framework Agreement | COLUMBIA COUNTY |  |
| Frank Childs Jr | 0013578 | 48400-265-MPOPD1700813 | Supplemental Agreement No. 3 is being requested to correct the county project description for to complete the project. |  | Completed | MP - Multi-Phase Project Specific | WSP USA INC | 4/4/2023 |
| Frank Childs Jr | 0013578 | 48400-265-MPOPD1700813 | The purpose of this task order is to revise the Project Concept to split project PI 0013578 into two projects: PI 0013578 (SR 31 FROM S POPLAR SPRINGS CHURCH RD TO S OF SR 117 – PH II) and PI 0019465 (SR 31 FM S OF SR 46 TO N OF S POPLAR SPRINGS CHURCH RD-PH I). Total Value of Master Contract: $5,000,000.00 Value of Task Order Executed & Pending: $3,826,654.42 Value of Current Task Order: $355,076.11 Balance After Executing Task Order: $818,269.47 | 7 | Completed | MP - Multi-Phase Project Specific | WSP USA INC | 4/19/2023 |
| Frank Childs Jr | 0013628 | 48400-265-MPOPD2000314 | Total Value of Master Contract: $6,629,409 ; Value of Task Orders Executed & Pending: $6,387,184. ; Value of Current Task Order: $80,876. ; Balance After Executing Task Order: $161,349 ; | 29 | Completed | MP - Multi-Phase Project Specific | HDR ENGINEERING INC | 3/3/2023 |
| Frank Childs Jr | 222170- | 48400-265-TOOPDDES120041 | The purpose of this task order is to provide Construction Services support, develop Use on Construction plan revisions and provide plan shop drawing review for the widening and reconstruction of P.I. 222160 SR 4/US 1 FM LOUISVILLE BYP @ CR325 TO CR 138/MENNONITE CH in Jefferson County. Total Value of Master Contract: $6,380,000.00 Value of Task Order Executed & Pending: $5,868,098.53 Value of Current Task Order: $50,000.00 Balance After Executing Task Order: $461,901.47 | 20 | Completed | TO - IDIQ On Call Contract | KIMLEY-HORN AND ASSOCIATES INC | 3/15/2023 |
| Frank Childs Jr | 222170- | 48400-265-TOOPDDES120041 | The purpose of this task order is to provide Construction Services support, develop Use on Construction plan revisions and provide plan shop drawing review for the widening and reconstruction of P.I. 222170 SR 4/US 1 FROM CR 138/MENNONITE CHURCH ROAD TO SR 540 – TIA Jefferson County. Total Value of Master Contract: $6,380,000.00 Value of Task Order Executed & Pending: $5,918,098.53 Value of Current Task Order: $100,000.00 Balance After Executing Task Order: $361,901.47 | 21 | Completed | TO - IDIQ On Call Contract | KIMLEY-HORN AND ASSOCIATES INC | 3/7/2023 |
| Frank Childs Jr | 262027- | 48400-265-MPOPDDES140583 | The purpose of this task order is to provide design services to update plans from Construction Shelf to Letting for GDOT project PI Number 262027- in Laurens County. Total value of Master Contract: $2,200,000.00 Value of Task Orders Executed & Pending: $1,693,420.56 Value of current Task Order: $350,000.00 Balance after Executing Task Order: $156,579.44 | 6 | Submitted | TO - IDIQ On Call Contract | GRESHAM SMITH |  |
| Frank Childs Jr |  | 48400-265-MPOPD2301753 | This master agreement is provide Right of Way Acquisition services for PI# 222260-; SR 17 FROM WASHINGTON BYPASS TO N OF VINSON ROAD/NORMAN RD; Wilkes County. No funds will be encumbered as a result of this master agreement. Funds will be encumbered upon execution of subsequent task orders. |  | Completed | MP - Multi-Phase Project Specific | THC INC | 4/19/2023 |
| Jonathan Andrew Clark | 0008018 | 48400-265-MPOPD1800874 | The purpose of this task order is to perform specialized or support-type services and smaller basic tasks that are difficult or not possible at the time of procurement to estimate the extent or duration of the work or to estimate costs with any reasonable degree of accuracy. Total value of Master Contract: $7,700,000.00 Value of Task Orders Executed & Pending: $7,343,088.25 Value of current Task Order: $100,00.00 Balance after Executing Task Order: $256,911.75 | 13 | Submitted | MP - Multi-Phase Project Specific | HNTB CORPORATION |  |
| Jonathan Andrew Clark | 0008019 | 48400-265-MPOPD1800874 | The purpose of this task order is to perform specialized or support-type services and smaller basic tasks that are difficult or not possible at the time of procurement to estimate the extent or duration of the work or to estimate costs with any reasonable degree of accuracy. Total value of Master Contract: $7,700,000.00 Value of Task Orders Executed & Pending: $7,243,088.25 Value of current Task Order: $100,00.00 Balance after Executing Task Order: $356,911.75 | 12 | Submitted | MP - Multi-Phase Project Specific | HNTB CORPORATION |  |
| Jonathan Andrew Clark | 0013554 | 48400-265-MPOPD2301435 | The purpose of this task order is to provide a Project Execution Plan, which includes a procurement plan, communications plan, project milestone schedule, and attend meetings for PI # 0013554. Total Value of Master Contract: $5,000,000.00 Value of Task Order Executed & Pending: $0.00 Value of Current Task Order: $75,000.00 Balance After Executing Task Order: $4,925,000.00 | 1 | Submitted | MP - Multi-Phase Project Specific | HNTB CORPORATION |  |
| Jonathan Andrew Clark | 0018007 | 48400-425-PFAOPD2301893 | PI 0018007, Newton County, Brown Bridge Road from SR 162 to Jack Neely Road Scoping Only |  | Completed | PFA - Project Framework Agreement | NEWTON COUNTY | 4/12/2023 |
| Jonathan Andrew Clark |  | 48400-265-MPOPD2301435 | Master Agreement routing for 2022 Engineering Design Services - DUBLIN SE BYPASS FROM SR 31/US 441 TO SR 31/US 319. |  | Submitted | MP - Multi-Phase Project Specific | HNTB CORPORATION |  |
| Marshall Robert Troup Jr | 0014072 | 48400-265-MPOPD1701687 | This task order consists of construction support including shop drawing review, visits to construction site, responding to RFIs (Request for Information), NCR (Non-Conformance Reports) and minor plan revisions. Total Value of Master Contract: $5,900,000.00 Value of Task Order Executed & Pending: $5,254,236.22 Value of Current Task Order: $50,000.00 Balance After Executing Task Order: $5,204,236.00 | 22 | Submitted | MP - Multi-Phase Project Specific | NV5 ENGINEERS AND CONSULTANTS INC |  |  |
| Marshall Robert Troup Jr | 0015284 | 48400-265-MPOPD2301441 | Master Agreement MPOPD2301441 – RFQ-484-061322 Batch #1 – 2022 Engineering Design Services, Contract 8 - PI #0015284, Henry County. |  | Submitted | MP - Multi-Phase Project Specific | VANASSE HANGEN BRUSTLIN INC |  |  |
| Marshall Robert Troup Jr |  | 48400-265-MPOPD2301442 | Engineering Design Services - PI #0018402. Master being routed in anticipation of the first task order. |  | Completed | MP - Multi-Phase Project Specific | KCI TECHNOLOGIES INC | 3/16/2023 |
| Marshall Robert Troup Jr |  | 48400-265-MPOPD2301438 | Master Agreement |  | Completed | MP - Multi-Phase Project Specific | TRANSYSTEMS CORPORATION | 4/12/2023 |
| Marshall Robert Troup Jr |  | 48400-265-MPOPD2301440 | This Master Contract which supports Task Order #1 is routing separately. |  | Submitted | MP - Multi-Phase Project Specific | AMERICAN CONSULTING PROFESSIONALS LLC |  |  |
| Travis S. McDonald | 0019181 | 48400-265-MPOPD2301443 | The purpose of this task order is to provide a Project Execution Plan, which includes a procurement plan, communications plan, project milestone schedule, and risk assessment and mitigation strategy plan for PI # 0019181. Total Value of Master Contract: $5,000,000.00 Value of Task Order Executed & Pending: $0.00 Value of Current Task Order: $75,000.00 Balance After Executing Task Order: $4,925,000.00 | 1 | Submitted | MP - Multi-Phase Project Specific | ATKINS NORTH AMERICA INC |  |  |
| Travis S. McDonald |  | 48400-265-MPOPD2301443 | Engineering and Design Services for City of Millen Railroad Crossings @ 3 Locs-Scoping Only |  | Submitted | MP - Multi-Phase Project Specific | ATKINS NORTH AMERICA INC |  |  |

# 14. Special Assignments/Committee Status

## Special Assignments

- Marshall Troup

  - GPTQ

    - CRC ACEC Scheduling and Programming Committee

- Andy Clark

  - Local Gov’t Coordinator for D2

## OPD Committee Members

- Marshall Troup

  - LAP Committee (Co-Chair)

  - Training 	(Chair)

  - Procurement

- Bruce Anderson

  - Electronic Standardization (Chair)

- Frank Childs

  - LAP Committee

  - Electronic Standardization

- Andy Clark

  - LAP Committee

- Travis McDonald

  - Gov’t Estimator Team

# 15. Employee Training/Development (Certifications are required every 3 years)

## LAP\PDP Training Status

| Learner | Title | Date Taken | Cert Status | Comments |
| --- | --- | --- | --- | --- |
| Anderson Jr., Bruce G. | LAP Training | 11/3/2017 | Expired | Enrolled for 9/27 |
| Anderson Jr., Bruce G. | PDP Training | 2/19/2018 | Expired | Enrolled for 9/20 |
| McDonald, Travis S. | LAP Training | 10/1/2019 | Current | Expires 10/22 |
| Clark, Jonathan Andrew | LAP Training | 3/29/2021 | Current | Expires 3/29/2024 |
| Clark, Jonathan Andrew | PDP Training | 9/15/2021 | Current | Expires 9/15/2024 |
| Childs Jr, Frank | LAP Training | 9/28/2021 | Current | Expires 9/28/2024 |
| Childs Jr, Frank | PDP Training | 1/13/2022 | Current | Expires 1/13/2025 |
| Mcdonald, Travis S. | PDP Training | 1/13/2022 | Current | 1/13/2025 |
| Troup, Marshall Robert | PDP Training | 1/13/2022 | Current | 1/13/2025 |
| Troup, Marshall Robert | LAP Training | 7/26/2022 | Current | Expires for 7/26/2025 |