## UTILITY TIMELINE
-18 wk | -16 wk | -14 wk | -12 wk | -10 wk | -8 wk | -4 wk | 0 | 4 wk | 8 wk | 12 wk | 16 wk
Timeline is for informational purposes only and can be adjusted according to the project schedule
DU submit plans to
Utility companies
(start of preliminary relocation process)
PFPR
PFPR request
Preliminary Utility relocation team meeting
Utility Coordination Timeline/Process
RW/Utl
meeting
2nd Utility Submission
start/finish
Design
Submit 2nd
Utility
Submission
FFPR
request
RW plans submit
Coordination with Design/Utl Companies/DU/Right of Way
Receive Preliminary relocation plans and comments from Utility companies