## Slide 1: Cost Estimates & OPD Cost Estimate Tracker
09.09.2025
Office of Program Delivery
Notes: The purpose of this training is to understand the PM’s role for updating cost estimates and following Policy 3A-9. This version of the training is based on Policy 3A-9 as last updated on 2/24/25. The training also focuses on best practices for filling out the revision to programmed cost template.
Training Time: 1 hr

## Slide 2: Learning Objectives
Filling out a Revisions to Programmed Cost Form
Write a Justification Statement for Cost Changes
Upload to the OPD Cost Estimate Tracker
Understand Policy 3A-9
Notes: (click 1) There are 4 learning objectives for this training. The PM understand GDOT Policy 3A-9.
(click 2) The PM will learn how to fill out the form for updating the cost estimate.
(click 3) Within the form is a justification box. The PM will learn how to properly write a justification statement that explains any cost changes.
(click 4) The last objective is to know how to upload the updated cost estimate to the tracker for signature.

## Slide 3
Cost Estimates
Notes: To understand when cost estimates are due and who is responsible for what, the PM must understand GDOT Policy 3A-9. Accurate and up-to-date cost estimates are vital for GDOT to be able to manage the Fiscal Year budget and plan for other fiscal years.

## Slide 4: Cost Estimate: Policy
If a project has a funding phase that is not authorized, it must be updated.
Funding phases may include:
  ROW
  UTL
  CST
PDP section 6.4.14
Required Annually
Notes: (click 1) Per PDP section 6.4.14, cost estimates are required to be updated annually for active projects.
(click 2) If a project has a funding phase that is not authorized, it must be updated. Funding phases may include ROW acquisition, utility relocations, and construction. PE funds are not included because they are already authorized. PE funds are used to design the project.

## Slide 5
GDOT Policy 3A-9 provides guidance for estimating the cost prior to Letting of projects in the:
  STIP
  TIP (MPO’s plan)
  CWP
  LR
Cost Estimate: Policy
Notes: (click 1) GDOT Policy 3A-9 provides guidance for estimating the cost of reimbursable and non-reimbursable utilities, ROW, and construction prior to Letting of projects in the (Statewide Transportation Improvement Program), (Transportation Improvement Program) (MPO’s plan), (Construction Work Plan), and (Long Range program).

## Slide 6
GDOT Policy 3A-9 outlines the responsibilities for the Office of Program Delivery:
  Requests cost estimates for updates.
  Monitor project costs changes.
  Track and ensure the ROW cost estimate is submitted in time for ROW Authorization.
Cost Estimate: PM’s Responsibilities
Policy 3A-9
Notes: (click 1) GDOT Policy 3A-9 outlines the responsibilities for the Office of Program Delivery: PM requests cost estimates for updates for ROW, utilities, and construction from the GDOT office/Consultant responsible for preparing these.
(click 2) PM is responsible to monitor project costs changes.
(click 3) PM is responsible to track and ensure that the ROW cost estimate for ROW authorization is submitted in time to keep the schedule.

## Slide 7
Per Table 1 in GDOT Policy 3A-9, required program cost estimate updates are submitted by the PM based on the following:
Know this table!
Policy 3A-9
Cost Estimate: PM’s Responsibilities
Notes: (click 1) Per Table 1 in GDOT Policy 3A-9, required program cost estimate updates are submitted by the PM based on the following table. The PM must know this Policy and in particular this table for when cost estimates are needed. The annual update requirement is a minimum.
[click to transition to next slide to see table more clearly]

## Slide 8
Per Table 1 in GDOT Policy 3A-9: Concept Phase
Policy 3A-9
Cost Estimate: PM’s Responsibilities
After Concept Report Approval
Within 4 months
Notes: (click 1) The PM is responsible to submit the updated cost estimate after the concept report approval. This should be done no later than 4 months after the concept report approval per OPD metric guidance.
[click to transition to next slide to see next part of the table]

## Slide 9
Per Table 1 in GDOT Policy 3A-9:
Preliminary Design Phase
Policy 3A-9
Cost Estimate: PM’s Responsibilities
After PFPR Report Plan Revisions Affecting Costs have been made
Notes: (click 1) The PM is responsible to submit the updated cost estimate after the PFPR report plan revisions affecting costs have been made. This should be done as soon as possible after PFPR is held.
[click to transition to next slide to see next part of the table]

## Slide 10
Per Table 1 in GDOT Policy 3A-9: Final Design Phase
Policy 3A-9
Cost Estimate: PM’s Responsibilities
6 mos. Before FFPR request, if $10 million or greater since last update
After FFPR Report Plan Revisions Affecting Costs have been made
Notes: (click 1) The PM must submit the updated estimate 6 months prior to FFPR request if the cost has increased by $10 million or more since the last programmed cost estimate.
(click 2) The PM is responsible to submit the updated cost estimate after the FFPR report plan revisions affecting costs have been made. This should be done as soon as possible after PFPR is held.
[click to transition to next slide to see next part of the table]

## Slide 11
Per Table 1 in GDOT Policy 3A-9: Annual Update
Policy 3A-9
Cost Estimate: PM’s Responsibilities
Due between 120 and 60 calendar days prior to June 30th
Notes: (click 1) The PM must submit the annual update between 120 and 60 calendar days before June 30th. Remember that June 30th is the end of the fiscal year.
[click to transition to next slide to see next part of the table]

## Slide 12
Per Table 1 in GDOT Policy 3A-9:
Cost Increase/Decrease & STIP/TIP Amendment or
Modification
Policy 3A-9
Cost Estimate: PM’s Responsibilities
Scope or Design changes that Increase or Decrease the cost by ≥ 10%
Cost Increase > $4 million or differs by 20% or more from STIP/TIP
Notes: (click 1) The PM must submit the updated estimate if the cost increases or decreases by 10% or more. It applies to any phase of money: ROW, utilities, or construction.
(click 2) The PM is responsible to submit the updated cost estimate if the cost increases over $4 million or differs by 20% or more from STIP/TIP.

## Slide 13
Once PE is authorized, PM is responsible for directing the preparation of ROW, UTL, and CST cost estimates.
Policy 3A-9
Cost Estimate: PM’s Responsibilities
NOTE: If project will be twinned, cost estimates should be submitted together.
Notes: (click 1) Once the preliminary engineering funds are authorized, the PM is responsible for directing the preparation of the ROW, UTL, and CST costs. In other words, the PM will never have involvement with a cost estimate for the PE funds. Cost estimates are only needed for funds that are not authorized.
(click 2) If projects will be twinned together (i.e. let for construction together), the project cost estimates should be submitted together. This is per the cost estimate template.

## Slide 14
Directing cost estimates:
Policy 3A-9
Cost Estimate: PM’s Responsibilities
Cost Estimate | Who Prepares It
ROW | GDOT Consultant1 or State ROW Office
UTL | District UTL Office
CST | Designer
Projects with Federal/State Funds
1 State ROW Office will have to review the estimate.
Notes: (click 1) Once the preliminary engineering funds are authorized, the PM is responsible for directing the preparation of the ROW, UTL, and CST costs. In other words, the PM will never have involvement with a cost estimate for the PE funds. Cost estimates are only needed for funds that are not authorized. This table shows who the PM should coordinate with to receive the updated cost estimate.
(click 2) If ROW or UTL phase will be paid using local funds only, a cost estimate is prepared by the Locals but will be reviewed by GDOT. GDOT needs to ensure that local sponsor is planning to have enough funds available for that phase of work.

## Slide 15
Directing cost estimates:
Policy 3A-9
Cost Estimate: PM’s Responsibilities
Cost Estimate | Who Prepares | Who Reviews
ROW | Local Sponsor | State ROW Office
UTL | Local Sponsor | District UTL Office
CST | Local Sponsor | Office of Eng Services
Projects with Local Funds Only
* This only applies to the funding phase that is only using local money
Notes: (click 1) If a funding phase will be paid using local funds only, a cost estimate is prepared by the Local sponsor but will be reviewed by GDOT. GDOT needs to ensure that local sponsor is planning to have enough funds available for that phase of work.

## Slide 16
Engineering Services is responsible for reviewing and processing all cost estimates.
  Focus on construction cost estimates for pay item quantities and general assessment of price.
  Review ROW and UTL estimates for completeness only.
Policy 3A-9
Cost Estimate: Office of Engineering Services
Notes: (click 1) Per Policy 3A-9, the Office of Engineering Services is responsible for reviewing and processing all cost estimates.
(click 2) Although construction, ROW, and utility cost estimates may be submitted, Engineering Services only checks the construction cost estimate to ensure that the pay item quantities and general price make sense for the project. The ROW cost estimate and the Utility estimate are prepared by their respective SME. Therefore, Engineering Services only checks these estimates for completeness.

## Slide 17
The Final CST cost estimate is prepared by Engineering Services for GDOT Let projects.
Policy 3A-9
Cost Estimate: Office of Engineering Services
  Triggered by submission of CFFPR letter.
Notes: (click 1) The final cost estimate (aka engineer’s estimate) is what is used to determine the final amount of money needed for construction fund authorization. It is also used as a way to determine if the bid amounts that are received for constructing the project are too high compared. The PM does not need to request the final cost estimate from the Office of Engineering Services. The estimate is triggered by the submission of the corrected FFPR letter. No one outside the Office of Engineering, except the Chief Engineer, will see the final cost estimate.

## Slide 18
Chief Engineer approves all cost estimates.
Policy 3A-9
Cost Estimate: Chief Engineer
Notes: (click 1) Per Policy 3A-9, the Office of Engineering Services is responsible for reviewing and processing all cost estimates.

## Slide 19
What must a GDOT PM follow to determine when a revised cost estimate must be submitted?
  GDOT Policy 3A-9
  Cost Estimate Form
  PDP Manual
  A & C
Cost Estimate Review
Notes: (direction: Read question 1 and give participants time to respond. Answer: D.)

## Slide 20
Which GDOT office reviews and approves the revised cost estimates?
  Environmental Services
  Engineering Services
  Design Policy & Support
  Program Delivery
Cost Estimate Review
Notes: (direction: Read question 1 and give participants time to respond. Answer: B.)

## Slide 21
When does a cost estimate expire?
  Never
  After Concept
  6 months
  12 months
Cost Estimate Review
Notes: (direction: Read question 1 and give participants time to respond. Answer: D.) At a minimum, the cost estimate for any unauthorized phase of funds will expire annually. This is 1 year from the date that it was approved by the Office of Engineering Services. However, the PM should review table 1 of Policy 3A-9 to know other times that the revised cost estimates are due.

## Slide 22
If the local sponsor provides:
ROW estimate State ROW Office
UTL estimate State UTL Office
Policy 3A-9
Cost Estimate: Local Sponsor Provided
Then estimate can be submitted to the Office of Engineering Services
Notes: If the local sponsor provides the ROW or UTL cost estimate, these must be approved by the State ROW or State UTL office prior to submitting them with the updated cost estimate.

## Slide 23: Revisions to Programmed Costs
Notes: Next, we will discuss how to properly fill out the Revisions to Programmed Costs template. When the word “revised” is used by GDOT, it is referring to changing or revising something that has already been approved. Until funds are authorized for use, the cost of a particular funding phase is only programmed. In other words, GDOT is using the estimate or the programmed amount of funds to balance the budget. Once you understand the terminology, the name of the template makes sense.

## Slide 24
Notes: (click 1) The template is owned and approved by the Office of Engineering Services. Look under this folder, not Program Delivery, for the form.

## Slide 25
Notes: There are multiple tabs at the bottom of the form. The first one has instructions for filling out the cover letter.

## Slide 26
Fill out: Kimberly W. Nesbitt, State Program Delivery Administrator
Date should match Submittal #1 date
Notes: (click 1) The cover letter tab is the template that the PM must fill out. Follow the instructions from the 1st tab.
(click 2) For the “from” field, write Kimberly W. Nesbitt, State Program Delivery Administrator.
(click 3) On the form is a “date” field and a “date of submittal #1” field, these should be the same date. Make this the date that you put the form into the OPD cost estimate tracker for review.

## Slide 27
Notes: Although the instruction explain the cost change and contingency justification box, we are going to focus on how to properly write information.

## Slide 28: Revisions to Programmed Costs: Justification Box
The purpose of the justification box is to explain
  why a funding phase is changing; and
  what the cost is based on
The audience for this information is the Office of Engineering Services & the Chief Engineer.
Notes: (click 1) The purpose of the justification box is to explain
  why a funding phase (ROW, UTL, or CST) is increasing, decreasing, or not changing; and
  what the cost is based on
    (i.e. updated plans, annual update, scope change, etc.)
(click 2) The audience for this information is the Office of Engineering Services and the Chief Engineer.
  The Office of Engineering Services reviews all revisions to programmed costs and the Chief Engineer approves them.

## Slide 29: Revisions to Programmed Costs: Justification Box (continued)
Best Practice: Each funding phase is discussed as a separate paragraph or sentence.
  Not every project will have all 3 funding phases.
  May not require an update at the same time for ALL funding phases.
  For authorized funds or funds about to be authorized, do not submit an updated cost estimate.
Notes: (click 1) The best practice for writing the justification is to discuss each funding phase in a separate paragraph or sentence.
(click 2) Remember that Not every project will have all 3 funding phases.
(click 3) All applicable funding phases may not require an update at the same time.
(click 4) For authorized funds or funds about to be authorized, do not submit an updated cost estimate.

## Slide 30: Revisions to Programmed Costs: Justification Box (continued)
Information to include in the Justification Box:
  Annual update or based on a milestone
  Which funding phase is being discussed
Notes: (click 1) State if the revisions to cost are for an annual update or based on a milestone in the design development process.
(click 2) State in the sentence which funding phase is being discussed.

## Slide 31: Revisions to Programmed Costs: Justification Box (continued)
Information to include in the Justification Box:
  % of cost increase (or decrease) for that funding phase and
    Reason for the change
  For CST cost, state the % of contingency included in the revised cost.
    Include the type of project and design phase
    Reference the risk & contingency table in Policy 3A-9
Notes:   (click 1) State the % of cost increase (or decrease) for that funding phase and
    what is the reason for the change
  (click 2) For CST cost, state the % of contingency included in the revised cost.
    Include the type of project and design phase that was used for the information
    Reference the risk & contingency table in Policy 3A-9

## Slide 32: Revisions to Programmed Costs: Justification Box (continued)
Information to include in the Justification Box:
    If the increased/decreased cost is less than 10%, provide a statement explaining the cost change.
    If the increase/decrease is more than 10%, explain in a summary sentence what has caused the cost to increase.
Coordinate with the designer – Designer should provide the information related to any CST or UTL cost change.
Notes: (Read slide)

## Slide 33: Revisions to Programmed Costs: Justification Box (continued)
Information to include in the Justification Box:
    If the increase/decrease is more than 20%, explain in a summary sentence what caused the change.
      Option 1: A letter from the designer is required explaining the specifics of the changed costs.
      Option 2: The designer can complete the Cost Estimate Comparison Tool which will explain the changed costs.
Designer should provide the info related to any CST or UTL cost change.
Notes: (click 1) [read slide]

## Slide 34: Revisions to Programmed Costs: Justification Box Example 1
Excerpt from PI 0013171 (April 2023)
Information to include in the Justification Box:
  State if the revisions to cost are for an annual update or based on a milestone in the design development process.
  State in the sentence which funding phase is being discussed.
Notes:   (click 1) When preparing the justification statement, state if the revisions to cost are for an annual update or based on a milestone in the design development process.
  (click 2) State in the sentence which funding phase is being discussed.

## Slide 35: Revisions to Programmed Costs: Justification Box Example 1- CST Cost
Excerpt from PI 0013171 (April 2023)
Information to include in the Justification Box:
  State the % of cost increase or decrease for that funding phase.
  State the justification (reason) why the cost has changed for that funding phase
Notes: (click 1) For each funding phase, state the % of cost increase or decrease for that funding phase.
(click 2) Also, state the justification (reason) why the cost has changed for that funding phase.

## Slide 36: Revisions to Programmed Costs: Justification Box Example 1 – CST Contingency Cost
Excerpt from PI 0013171 (April 2023)
Information to include in the Justification Box:
  For CST cost, state the % of contingency included in the revised cost.
    Include the project type and risk that determined the % of contingency
Notes:   (click 1) For CST cost, state the % of contingency included in the revised cost.
  (click 2) Include the project type and risk that determined the % of contingency

## Slide 37: Revisions to Programmed Costs: Justification Box Example 1 – UTL Cost
Excerpt from PI 0013171 (April 2023)
Information to include in the Justification Box:
  State in the sentence which funding phase is being discussed.
  If the cost decreased and the scope has not changed, use the language for the “no-change” cost estimate.
Notes:   (click 1) State in the sentence which funding phase is being discussed.
  (click 2) If the cost decreased and the scope has not changed, use the language for the “no-change” cost estimate.

## Slide 38: Revisions to Programmed Costs: Justification Box Example 1 – ROW Cost
Excerpt from PI 0013171 (April 2023)
Information to include in the Justification Box:
  State in the sentence which funding phase is being discussed.
  If the estimate is needed but not available let the reader know the status of the estimate.
Notes:   (click 1) State in the sentence which funding phase is being discussed.
  (click 2) If the estimate is needed but not available let the reader know the status of the estimate.

## Slide 39: Revisions to Programmed Costs: Justification Box Example 2
Excerpt from PI 0019837 (Dec 2023)
Information to include in the Justification Box:
  State if the revisions to cost are for an annual update or based on a milestone in the design development process.
Notes:   (click 1) State if the revisions to cost are for an annual update or based on a milestone in the design development process.

## Slide 40: Revisions to Programmed Costs: Justification Box Example 2 – CST Cost
Information to include in the Justification Box:
  State in the sentence which funding phase is being discussed.
  State the % of cost increase or decrease for that funding phase.
  State the reason why the cost has changed for that phase.
Excerpt from PI 0019837 (Dec 2023)
Notes:   (click 1) State in the sentence which funding phase is being discussed.
  (click 2) State the % of cost increase or decrease for that funding phase.
  (click 3) State the reason why the cost has changed for that phase.

## Slide 41: Revisions to Programmed Costs: Justification Box Example 2 – CST Contingency Cost
Information to include in the Justification Box:
  For CST cost, state the % of contingency included in the revised cost.
    Include why this % was chosen
Excerpt from PI 0019837 (Dec 2023)
Notes:   (click 1) For CST cost, state the % of contingency included in the revised cost, include why this % was chosen

## Slide 42: Revisions to Programmed Costs: Justification Box Example 2 – ROW & UTL Cost
Information to include in the Justification Box:
  State in the sentence which funding phase is being discussed.
    If a funding phase is not applicable, acknowledge that it is not needed.
Excerpt from PI 0019837 (Dec 2023)
Notes:   (click 1) State in the sentence which funding phase is being discussed. If a funding phase is not applicable, acknowledge that it is not needed.

## Slide 43: Cost Estimate: Practice Exercise Writing a Justification for Updated Costs
Notes: The next section will practice how to properly write a justification statement for an updated cost estimate.

## Slide 44
  For this project, which funding phase(s) needs an annual cost estimate update?
  ROW
  CST
  UTL
How did you know that these phases still get cost estimate updates?
The funds for these phases are not authorized.
Also, based on the years that the funds are approved to be used, none of these phase are close to authorization.
Practice Exercise
Notes: [directions Question 1 – give participants time to write answer on dry erase board]
(click 1) [read the answers]
(click 2) [directions Question 2 – ask for volunteers to answer. ]
[click 3 & 4 to show answers]

## Slide 45
  Other information:
  Last cost estimate was from the concept report.
  PM has received the PFPR plans for the PFPR request.
  It is a safety (roundabout) project. Therefore, 5% contingency was used.
Check the Justification Box Response for:
Statement telling what plans the costs are based on or if it is an annual update
Each paragraph states which funding phase is being discussed
A percentage of cost change from the last cost estimate is stated
A justification (reason) is stated for the cost change or no-cost change
For CST funds, the % of contingency is stated & what criteria it met per Policy 3A-9
  Write a justification for the cost estimate.
Practice Exercise
Notes: Give the participants a few minutes to write a justification for this example on their dry erase board. [example answer is on the next slide]

## Slide 46
Reminder: The funding cost staying the same is NOT a no-change cost estimate.
Practice Exercise
Notes: Check the Justification Box Response for:
(click 1) Statement telling what plans the costs are based on or if it is an annual update
(click 2) Each paragraph states which funding phase is being discussed
(click 3) A percentage of cost change from the last cost estimate is stated
(click 4) A justification (reason) is stated for the cost change or no-cost change
(click 5) For CST funds, the % of contingency is stated & what criteria it met per Policy 3A-9
(clicks 1-4) each paragraph follows these rules and talks about a separate funding phase.
(click 1) If a cost estimate ends up being the same as the last approved estimate, it is still an updated cost estimate. Do not refer to it as a no-change cost estimate.

## Slide 47
Cost Estimate: Package Components
Notes: Next, we will focus on what information is needed for the OPD cost estimate tracker.

## Slide 48
Check that the Cost Estimate has the following before submitting it for review:
  Revisions to Programmed Costs (template)
    Cover Letter
    Validation to Final QC-QA (only if CST included)
    Cost Estimate Worksheet
    Optional Cost Explanations (if needed)
Cost Estimate: Package Components
Notes: [read slide]

## Slide 49
Check that the Cost Estimate has the following before submitting it for review:
  If CST increases by 20% or more, also include:
    Cover Page (also include if cost increase is >$2M)
    One of the following:
      Cost increase explanation letter (from designer) or
      Cost Estimate Comparison Tool (from designer)
Cost Estimate: Package Components (cont.)
Notes: [read slide]

## Slide 50
Notes: This is the cover page that is required if the cost increases by more than 20% or more than $2 million.

## Slide 51
Check that the Cost Estimate has the following before submitting it for review:
  Attachments include:
    Copy of UTL & ROW cost estimate (if applicable)
      Signed by either DUO or State ROW Office, respectively
    GDOT 411 Printout (CST cost)
    Copy of current PSR
Cost Estimate: Package Components (cont.)
Notes: [read slide]

## Slide 52: OPD Cost Estimate Tracker: Needed Information
Notes: Next, we will focus on what information is needed for the OPD cost estimate tracker.

## Slide 53
Notes: Prior to submitting a cost estimate to the Office of Engineering Services, the estimate must be reviewed and signed by the AOH. The process to submit it through the OPD Cost Estimate Tracker. Once it is placed in the tracker, it will be reviewed by the DPM & Assistant Office Head.

## Slide 54
Excerpt of the OPD Cost Estimate Tracking Form
Notes: The form has multiple fields for each funding phase that is being updated.

## Slide 55
What needs to be filled out?
All fields are to be filled in (not just the ones with an *).
  This includes the date an estimate was requested and the date it was received.
If edits or corrections are required, do not create a new form.
  Update the original Cost Estimate Tracking Form.
Notes: (click 1) [read bullet]
(click 2) [read bullet]

## Slide 56
What needs to be filled out? (continued)
PM is to continually update the “cost estimate status” box in the Project Details section.
In the “Program Delivery Routing” section, the PM only fills in the “date sent to DPM.”
  If the cost estimate must but resubmitted with corrections, do not forget to update the date.
Notes: (click 1) [read bullet]
(click 2) [read bullet]

## Slide 57
If a project is only LUMP Sum or has no federal money in any funding phase, the project will not be listed in the STIP/TIP.
Select “No”
If a project is in the STIP/TIP and the cost changes, then an amendment is needed.
Select “Yes”
HINT: Look at the funding box and the STIP box on the PSR.
Notes: (click 1) [for info about lump sum projects and the STIP/TIP – read bullet 1]
(click 2) [for info about other funds and the STIP/TIP – read bullets]
(click 3) [read the hint box to determine which response is appropriate]

## Slide 58
“Cost estimate status” must be constantly updated. PM is responsible for submission and approval status.
Notes: (click 1) [read bullet 1]

## Slide 59
This is referencing CST estimate total. It will include the contingency cost.
If the funding phase’s cost has decreased, this will be a no-change cost estimate.
Notes: (click 1) [read bullet 1]
(click 2) [read bullet 2]

## Slide 60
If the funding phase’s cost has decreased, this will be a no change cost estimate.
Notes: (click 1) [read bullet]

## Slide 61
If comments from Engineering Service are received, this information must be entered.
Enter date when it is being sent to Engineering Services (after OPD has signed it).
Notes: (click 1) [read bullet 1]
(click 2) [read bullet 2]

## Slide 62
If V2 is submitted to Engineering Service, this information must be entered.
Enter date when Engineering Services sends email stating that it is approved. (Don’t wait for it to update on PSR)
Leave as “none”
Notes: (click 1) [read bullet 3]
(click 2) [read bullet 4]
(click 3) [read bullet 5]

## Slide 63
If another submission (i.e. V2) is being submitted based on comments from Engineering Services, a new link needs to be included to the new document.
Notes: (click 1) [read bullet 1]

## Slide 64: Questions?