## Slide 1
Notes: The focus of this training is to set the expectations of the role for a new project manager.
Training Time: 30 min

## Slide 2: Overview
What is a GDOT Project Manager?
GDOT Project Manager’s Responsibilities
How to be a Superior Project Manager
Notes: The focus of this presentation is the Georgia Department of Transportation project manager. The training will
(click 1) explain what is a GDOT project manager;
(click 2) the responsibilities of a GDOT project manager; and
(click 3) the best practices that a superior project manager does.

## Slide 3: What is a GDOT PM?
Central Nervous System of the Project
Notes: What is a GDOT PM?
(click 1) The GDOT PM acts like the central nervous system of the project.

## Slide 4
Designer
Environmental
Utilities
Right-of-Way
Other GDOT Departments
GDOT Management
Office of Materials & Testing
GDOT PM
Policies
Manuals & Guides
Notes: The GDOT PM receives information from various office and subject matter experts and then send that information to the appropriate person or office. (click 1 for the SMEs to see where information is coming and going to)

## Slide 5
Scope
Schedule
Budget
Juggler of Many Tasks
Notes: The role of the PM is often a juggler of many tasks. The core pillars of GDOT management is
scope, schedule and budget.
(click 1) These pillars are constantly being influenced and informed by each other. The GDOT PM is responsible to be mindful and proactive in understanding how changing one of these pillars may affect the other two pillars.

## Slide 6
Notes: (click 1) Often as a GDOT PM, you will feel like you are juggling many balls at once. It can be quite challenging.

## Slide 7: Project Manager’s Responsibilities
PM Metrics
Documentation
Primavera P6 Schedule
Notes: [Each will be explained on future slides. Just list the items as shown]
The Project Manager’s responsibilities include but are not limited to
(click 1) PM metrics
(click 2) documentation
(click 3) Primavera P6 schedule

## Slide 8: Project Manager’s Responsibilities
Plan Development Process
Procurement Phase
Scope/Concept Phase
Notes: [Each will be explained on future slides. Just list the items as shown]
The Project Manager’s responsibilities include but are not limited to
(click 1) Plan Development Process
(click 2) Procurement Phase
(click 3) Scoping/Concept Phase

## Slide 9: Project Manager’s Responsibilities
Design Phase
Communication
Notes: [Each will be explained on future slides. Just list the items as shown]
The Project Manager’s responsibilities include but are not limited to
(click 1) Design Phase
(click 2) Communication

## Slide 10: PM Metrics
Various metrics including:
  TPro PM notes not older than 30 days
  TPro contact information
  Cost estimates no greater than 1 year old
  PM milestones
  Escalation memos for missed milestones
Notes: Project Manager metrics are job-related performance items that have been identified by the Office of Program Delivery (aka OPD). A PM’s compliance with the assigned metrics is formally evaluated biannually. However, the PM is to ensure that compliance is maintained each month. This includes being compliance with
(click 1) TPro PM notes not being older than 30 days,
(click 2) TPro contact information being up to date,
(click 3) cost estimates not exceeding 1 year old,
(click 4) PM milestones being submitted per baseline due date,
(click 5) and escalation memos written and submitted within 1 week of missing a milestone (if applicable),

## Slide 11: PM Milestones
PM submit
Concept Report
(CR)
PM request Preliminary Field Plan Review
(PFPR)
  PM request Final Field Plan Review (FFPR)
Notes: To ensure that a project is following the Plan Development Process and maintaining the project schedule, the PM must be compliant with submitting the milestones per the project’s baseline due date. There are 3 milestones that the GDOT PM must make and are evaluated as part of the PM’s metrics. The milestones are:
(click 1) PM submit Concept Report,
(click 2) PM request Preliminary Field Plan Review, and
(click 3) PM request Final Field Plan Review.

## Slide 12: Documentation
Constant Reporting and Documentation is Required
  Let Status Reporting
  ROW Status Reporting
  18-Month Spreadsheet
  District Project Status Meeting
Notes: (click 1) Along with the metrics that the PM must meet, another responsibility is documentation for each project. There are many different required methods of reporting and documenting the scope, schedule, and budget of a project. Examples include but are not limited to
either the monthly Let status or
the ROW status meeting,
18-month spreadsheet, and
district project status meetings.

## Slide 13: Documentation (continued)
  Meeting Minutes
  TPro PM notes
  Project Status Update (PSU) sheet
  Copies of PSR & PFR
  Escalation memos (missed milestones)
Notes: The PM is responsible to maintain a running history of the project through keeping thorough and accurate
(click 1) Meeting Minutes for Monthly Team Meeting, Various Discipline Meeting, and/or Decision Meetings
(click 2) updating the TPro PM notes on PSR,
(click 3) a monthly copy of both the PSR and PFR,
(click 4) monthly updates on the Project Status Update sheet, and
(click 5) preparing and submitting escalation memos for missed milestones.

## Slide 14: Documentation (continued)
  Save Emails and Other Correspondence/Decisions to Project Wise
  Performance Evaluation for Consultants
  Performance Evaluation for Local Designed Projects
  (Local Sponsor)
Notes: Project documentation also includes
(click 1) saving correspondence related to stakeholders or property owners, coordination with other GDOT offices for reviews and/or document approval, as well as important decisions related to the project’s scope, schedule, or budget. Check with your DPM on the policy for this.
The GDOT PM prepares performance evaluations for consultants who have been hired to perform work on GDOT’s behalf. The purpose of all of the various methods of documentation is to provide GDOT management access this information at a moment’s notice as well as to document the PDP process as part of compliance for GDOT using federal funds on a project.

## Slide 15: Primavera P6 Schedule
Notes: Primavera P6 is the scheduling software program that GDOT uses.

## Slide 16: Primavera P6 Schedule
Keep the Schedule Current
Update tasks assigned to OPD
  Coordinate with other offices
Notes: A PM must ensure that the Primavera P6 schedule is being maintained with accurate information. The schedule is one of the 3 management pillars. Without this information, it is not possible to truly understand if the project is on schedule or not. The PM must
(click 1) update all P6 tasks that are assigned to OPD.
(click 2) Although the PM is not responsible to physically update the P6 tasks, it is the responsibility of the PM to coordinate with other offices and SMEs to ensure that these tasks are up to date.

## Slide 17: Primavera P6 Schedule
PM responsible for developing all schedules
  Requests all schedules and schedule modifications
  Must get SMEs’ concurrence on every schedule and/or schedule change
Notes: The GDOT PM responsible for developing all schedules.
(click 1) If a schedule needs to be modified by either removing or adding a task, the PM will be responsible to request the schedule modifications.
If a project will change the baseline schedule through a Project Change Request Form (PCRF), the PM is responsible to create the proposed high-level schedule and get the subject matter experts (SMEs) to concur with the changed schedule.

## Slide 18: Plan Development Process (PDP)
Knowledge of steps
Timing of PDP components
Minimize risks
Follow new policies and guidance
Notes: The Plan Development Process or PDP is the oversight agreement between GDOT and the Federal Highway Administration (FHWA). GDOT must follow the steps of the PDP in order to use federal funds.
(click 1)It is the PM’s responsibility to know the PDP manual and applicable steps of the process for each project.
(click 2) Additionally, the PM must understand the timing of the various steps of the PDP.
(click 3) By utilizing the knowledge of the plan development process and communicating with the SMEs, the PM can lead the project team and ensure that risks are minimized. Consequently, this will help to ensure that the scope, schedule and budget of the project are maintained.
(click 4)When new/updated policies or guidance are provided by GDOT, the PM should communicate this to the appropriate subject matter expert to ensure that the project is being developed following the current policies and guidance.

## Slide 19: Procurement Phase
Evaluate the Project for Scope of Work (SOW) Tasks
Consultant’s SOW Is Dependent On:
  Funding Source
  Contract Type
Notes: (click 1) The PM is responsible to ensure that based on the needs of the project that all applicable scope has been included in the contract.
When developing a consultant contract or task order, the PM will evaluate the scope of work to ensure that it is compliant with the funding source and contract type for the project.

## Slide 20: Procurement Phase
  Write Scope for a Design Phase & Project Needs
    Concept
    Preliminary Design to ROW Authorization
    Final Design
Notes: (click 1) Generally, GDOT projects have 3 procurement phases. One to match each main design phases: concept, preliminary design, and final design.

## Slide 21: Procurement Phase
Scope Concurrence
Hours from GDOT
Procurement Package
Hours related to PM Work
Notes: The PM is responsible for:
(click 1) obtaining scope concurrence from both the consultant firm and the appropriate SMEs,
(click 2) requesting the GDOT SMEs to provide the hours for each task
(click 3) providing the number of hours that PM related activities will require for specific tasks, and
(click 4) submitting the entire procurement package to the GDOT procurement office. This will trigger negotiations to begin with the consultant firm.

## Slide 22: How to be a Superior Project Manager
Notes: Now we will discuss how to be a superior project manager.

## Slide 23: How to be a Superior PM
Respond within 24 hours
Identify Risks Early
Notify DPM of Changes
Consistent
Communication
Notes: An excellent PM possesses outstanding communication skills and does not assume that others know or thinks the way that the PM does. Some of the communication tools used by a superior PM are:
(click 1) Responding to all emails and phone calls within 24 hours even if it is just to notify the recipient that the information will be provided by a specific later date.
(click 2) Is knowledgeable about the project’s scope, schedule, and budget parameters; therefore, the PM can identify potential issues or risks early.
(click 3) Notify your District Program Manager of any changes that affect approved scope, schedule or budget. Leadership may be able to offer potential solutions to minimize the risk or issue if addressed early enough.
(click 4) Maintain constant and consistent communication with project team members and your DPM.

## Slide 24: How to be a Superior PM
Deliver on Baseline
Complete QAQC
Follow Up
Notes: If you are mindful and follow these simple rules, you will be a successful and excellent project manager.
(click 1) Deliver all submissions on baseline schedule. If you cannot deliver on baseline, then have a detailed plan ready for how to recover for the next critical task or milestone.
(click 2) Take the time to thoroughly complete quality assurance and quality control for all submissions. Mistakes and omissions will erode the level of trust and confidence that GDOT management has for a particular PM.
(click 3) Trust and partnerships with various SMEs and GDOT offices are built through PM’s actions. If a PM commits to providing information or coordinating about a particular issue, then the PM must follow through and complete the task as promised and by the agreed upon deadline, if applicable.

## Slide 25: How to be a Superior PM
Organize project files
Record & maintain documentation
Manage your time
Notes: Superior PMs demonstrate the following skills effectively:
(click 1) Organize project files well.
(click 2) Record and maintain documentation. Although this is part of the responsibility of a PM, what sets a superior PM apart is the ability to understand what document must be kept or recorded and does it regularly as information is generated. They do not wait for extended periods of time before updating the project’s documentation.
(click 3) Time management is a critical skill that is mastered by a superior PM. As previously discussed, GDOT PMs are responsible for a lot of different tasks simultaneously. Without time management, it is difficult to keep up with the requirements of the role and will lead to frustration, stress, and burn out.

## Slide 26: How to be a Superior PM
KNOW EACH PROJECT
SCOPE
SCHEDULE
BUDGET
+ RISK
Notes: At a minimum, a superior PM is always knowledgeable about each project that they are responsible for managing. To truly know a project, the PM must understand its:
(click 1) scope; schedule; budget, and risks.
The PM must also be constantly reviewing, evaluating, and communicating each of these.

## Slide 27
Stay prepared.
So you don’t have to get prepared.
Notes: [Animated – no click needed ]
Stay prepared so you don’t have to get prepared. The PM’s that follow this motto do not have to scramble to updated notes, find information when requested, and are generally very knowledgeable about their projects. In other words, by keeping up with the responsibilities of the PM role and using time management effectively, the PM will be less stressed. Furthermore, the PM’s ability to manage a project will be evident to others.