## Slide 1
Notes: The focus of this training is to provide a foundational level of knowledge that all project managers must have.
Training Materials: Copy of Slide 36 for each participant
Training Time: 2 hours

## Slide 2: Learning Objectives
Be able to list the PDP phases of a project.
Be able to list the milestones are part of the PM’s metrics.
Be able to identify a fiscal year from a date.
Know the time frames for information of the STIP, TIP, & CWP.
Know the minimum population requirement for an MPO.
Be able to list the 11 metrics that a PM is evaluated on.
Notes: In today’s training, you
(click 1) be able to list the PDP phases of a project.
(click 2) be able to list the PM’s milestones
(click 3) Understand what is a fiscal year and know what fiscal year a date is occurring
(click 4) know the time frames associated with various planning documents
(click 5) Know the minimum population requirement for an MPO
(click 6) be able to list the 11 metrics that a PM is evaluated on

## Slide 3
Planning a Project
Projects the OPD delivers are programmed by one of the following offices:
Office of Planning
Office of Traffic Operations
Office of Bridge Design & Maintenance
Notes: Projects that the office of program delivery manages are programmed by one of 3 offices.
(click 1) Office of Planning, Office of Traffic Operations, or Office of Bridge Design & Maintenance

## Slide 4: Plan Development Process (PDP) Phases
PTIP
Concept
Preliminary Design
Final Design
Let
Notes: (click 1) The OPD PM is responsible to ensure that the PDP process is followed, if federal funds are used for any funding phase of the project. There are 5 phases in the Plan Development Process: PTIP, Concept, Preliminary Design, Final Design, and Let. The next few slides will provide a general understanding of each phase.

## Slide 5: PDP Phases
PTIP
Uses input of the PM, Project Programming Manager, and various SMEs to:
(Project Team Initial Process)
understand and develop the project’s scope
begin schedule development
estimate the preliminary engineering budget.
Notes: The project team initial process uses the input of the project manager, project programming manager, and various GDOT subject matter experts to
(click 1) understand and develop the project’s scope.
(click 2) Through the PTIP process, a basic timeline for the schedule can be estimated.
(Click 3) With the basic information regarding the anticipated scope and schedule of the project, a preliminary budget is developed. It is a high-level estimate and not based on engineering design.

## Slide 6: PDP Phases
PTIP
Not every project programmed has a PTIP phase.
(Project Team Initial Process)
Notes: (click 1) Not every project programmed has a PTIP phase.

## Slide 7: PDP Phases
Concept
Objective of the Concept Phase is to develop a Concept Report (CR).
Purpose of the CR is to:
Identify the
Project Footprint
PJS
Address the Project Justification Statement
Recommend
the Preferred Design Alternative
Notes: (click 1) The objective of the Concept Phase is to develop a Concept Report (CR).
(click 2) The purpose of the CR is to:
(click 3) Describe a recommended project “footprint” including project termini.
(click 4) Recommendation will address the project justification statement (PJS). The PJS is the “why” of the project. Why is the project needed? What problem is the project solving?
(click 5) The CR provides a recommendation for the preferred design alternative which is based on analysis of various studies, impacts, and other considerations.

## Slide 8: PDP Phases
Preliminary Design
Preliminary design is based upon the scope of work as approved in the CR.
The preliminary design will continually evolve and incorporate information from various studies or design analysis.
Design related risks and issues should be vetted during the preliminary design phase.
Notes: (click 1) Preliminary design is based upon the scope of work as approved in the CR.
(click 2) The preliminary design will continually evolve and incorporate information from various studies or design analysis.
(click 3) Design related risks and issues should be vetted during the preliminary design phase.

## Slide 9: PDP Phases
Preliminary Design
Note: If no CR, the preliminary design will be based on the project charter or the scope of the programmed project.
WHAT (Scope)
HOW (Design)
Concept Report
Preliminary Design
Notes: (click 1) Remember that the concept phase or project charter sets the scope of the project and answers the question of “what” is the design solution.
(click 2) Preliminary design answers the question of “how” the project will be constructed to be compliant with the scope of the project.
(click 3) If a concept report is not required, the preliminary design is based on the project charter or the scope of the programmed project.

## Slide 10: PDP Phases
Final Design
The final design phase updates and finalizes the construction plans.
Avoid Significant Plan Changes
Obtain Permits (if needed)
Obtain
Certifications
Notes: The final design phase updates and finalizes the construction plans.
(click 1) Typically, significant changes to the plans should not occur during this phase.
(click 2) If permits are required for a project, they are obtained during this phase.
(click 3) All projects must obtain 3 certifications for authorization of the construction funds. The 3 certifications are environmental, utilities, and right-of-way.

## Slide 11: PDP Phases
Let
(Construction Phase)
Do Not Oversee Construction
Coordinate Design Changes
Listed as Project’s PM
PM
Notes: (click 1) Until construction is complete, the project remains listed under the PM’s name. This helps management to know who to contact with questions regarding the history of the project.
(click 2) The PM does not oversee the construction process. GDOT assigns a construction project manager.
(click 3) If design changes are required during construction, the PM will coordinate the changes and submit the updated construction plans to the contractor.

## Slide 12: Mgmt Let Date
Let (Construction Phase) vs Mgmt Let Date
Mgmt. Let Date = Ends the Bidding Process
Mgmt. Let Date is the date that all bids for construction have been received and the lowest qualified bidder is identified for the construction contract.
Construction does not start for several months after the Mgmt. Let Date. (need time for construction contracts to be finalized)
Notes: (click 1) Management Let Date is not the same as the baseline date. It the date assigned by GDOT executive management which signifies the end of the bidding process.
(click 2) Any contractor who wants to be considered for winning the construction work must submit their bid by this date. The contractor who is the lowest qualified bidder will be awarded the construction contract.
(click 3) Construction does not start for several months after the management let date.

## Slide 13: Mgmt Let Date
Let (Construction Phase) vs Mgmt Let Date
Phrases: A project has let. (or)
The project let in February 2024.
Meaning: The project has gone to construction.
Phrase: The project will let in January 2028.
Meaning: The project’s bidding process for construction will end in January 2028. Since the date is in the future, construction has not begun.
VS.
Referring to Mgmt. Let Date
Notes: The term “let” can be confusing when a PM begins work. The context of how the word “let” is used will determine its meaning.
(click 1) For example, A project has let. Or The project let in February 2024. Let is being used in the past tense. It means that it has gone to construction.
(click 2) The project will let in January 2028. This is telling someone that the bidding process will end in January 2028. Since the date in the future, construction has not begun.

## Slide 14: Learning Objective Review:
What is the order of the 5 Phases of the PDP Process?
  Concept, PTIP, Preliminary, Final, Let
  B. PTIP, Concept, Preliminary, ROW, Final
  C. PTIP, Concept, Preliminary, Final, Let
  D. Scope, Concept, Preliminary, Final, Let
Notes: [Have participants raise the paddle that matches their answer. Answer: C]

## Slide 15
Does every project have all 5 phases?
  True
  False
Learning Objective Review:
Notes: [Have participants raise the paddle that matches their answer. Answer: False.
Most projects have 4 phases. However, a project can have as few as 2 PDP phases. The minimum PDP phases are final design and let. This is only applied to projects with an expedited schedule. ]

## Slide 16: Project Manager Milestones
What is a milestone?
It is a project planning tool that is used to mark a point in a project schedule.
For OPD, it marks the completion of a major phase project deliverable.
Why is a milestone important?
By making a milestone on schedule, it helps to ensure that a project will be delivered on time.
For OPD, it ensures that the design phases are on schedule, which will translate to the Let date being on schedule.
Notes: (click 1) What is a milestone?
(click 2) It is a project planning tool that is used to mark a point in a project schedule.
(click 3) For OPD, it marks the completion of a major phase project deliverable.
(click 4) Why is a milestone important?
(click 5) By making a milestone on schedule, it helps to ensure that a project will be delivered on time.
(click 6) For OPD, it ensures that the design phases are on schedule, which will translate to the Let date being on schedule.

## Slide 17: Project Manager Milestones
OPD PMs have 3 milestones:
  PM submit Concept Report
  PM request PFPR
  PM request FFPR
All milestones must be submitted no later than the P6 baseline date.
Notes: (click 1) OPD PMs have 3 milestones. PM submit concept report. PM request PFPR. PM request FFPR. Other offices have their own milestones. However, as the PM, these are the 3 that you are responsible to make.
(click 2) All milestones must be submitted no later than the P6 baseline date.

## Slide 18
Which is NOT one of the 3 PM Milestones?
  PM submit CR
  PM request Scoping
  PM request PFPR
  D. PM request FFPR
Learning Objective Review:
Notes: [Have participants raise the paddle that matches their answer. Answer: B]

## Slide 19: Fiscal Year
GDOT has a fiscal year from July 1 – June 30
GDOT plans the budget for each phase of work based on fiscal years.
For example: Management Let Date
4/12/23 = FY23 (because it is before June 30 it is the same calendar year)
8/9/23 = FY24 (because it is after July 1 it is the not the same calendar year)
Notes: (click 1) GDOT has a fiscal year that does not follow the calendar year. It begins on July 1 and ends on June 30th.
(click 2) GDOT plans the budget for each phase of work based on fiscal years.
(click 3) Let’s look at a few examples of determining the fiscal year for the management let date.
(click 4) April 12, 2023 is FY23. Since the date is before June 30th, the fiscal year is the same year as the calendar year.
(click 5) August 9, 2023 is FY24. Since the date is after July 1st, the fiscal year is the next calendar year. When a PM mentions fiscal year in any notes, it can be abbreviated as capital FY and the last 2 digits of the year that applies.

## Slide 20
What is the Fiscal Year is 3/2/21?
  FY20
  FY21
  FY22
Remember: FY is July 1-June 30
Learning Objective Review:
Notes: [Have participants raise the paddle that matches their answer. Answer: B]

## Slide 21
What is the Fiscal Year for 12/23/27?
FY26
FY27
FY28
Learning Objective Review:
Notes: [Have participants raise the paddle that matches their answer. Answer: C]

## Slide 22: Project Planning
GDOT must decide which projects or project phases will be planned for a certain year.
An allotted budget is set for each year. Therefore, only a certain number of projects can be planned for each year.
To record which project will happen when, GDOT uses several different planning documents.
Notes: (click 1) GDOT must decide which projects or project phases will be planned for a certain year.
(click 2) An allotted budget is set for each year. Therefore, only a certain number of projects can be planned for each year.
(click 3) To record which project will happen when, GDOT uses several different planning documents.

## Slide 23: Project Planning: Statewide Transportation Improvement Program
STIP (and TIP)
Current Year
4-Year
Current + 3 years
Notes: The projects that are being actively designed or will have a funding phase authorized within 4 years, including the current year, are listed in the Statewide Transportation Improvement Program (aka STIP). We will discuss the difference between the STIP and TIP on the following slides.

## Slide 24: Project Planning
  MPO’s (Metropolitan Planning Organization) four-year transportation and capital improvement program.
  Lists federally-funded transportation projects for an MPO.
  Each MPO has its own TIP.
  TIP = Current + 3 years
TIP (Transportation Improvement Program)
Notes: (click 1) TIP stands for Transportation Improvement Program. It is a 4-year planning document for transportation and capital improvements. The TIP is created by a Metropolitan Planning Organization.
(click 2) Federally funded transportation projects for a particular MPO is in the TIP.
(click 3) Each MPO has its own TIP.
(click 4) The TIP document covers the current year plus an additional 3 years for phases of money that have been allocated to programmed projects.

## Slide 25: Project Planning
MPO
16 MPOs
Population of at least 50,000
Notes: (click 1) Georgia has 16 MPOs
(click 2) Each MPO must have a population of at least 50,000

## Slide 26: Project Planning
MPO
MPO is bound by population (NOT city or county boundaries)
Notes: (click 1) MPO is bound by population (NOT city or county boundaries)

## Slide 27: Project Planning
STIP (Statewide Transportation Improvement Program)
Georgia’s four-year transportation and capital improvement program.
STIP = Current + 3 years
Lists federally-funded transportation projects for the entire state, including MPOs’ TIPs.
Notes: (click 1) The STIP stands for statewide transportation improvement program. It includes programmed transportation and capital improvement projects that will be funded within the next 4 years.
(click 2) Just like the TIP, the STIP document includes the current year plus the next 3 years.
(click 3) The STIP lists federally funded transportation projects for the entire state, including the projects listed in each MPO’s TIP. It also includes projects that are not programmed in the TIPs.

## Slide 28: Project Planning: Construction Work Program
CWP
Current Year
+ 6 years
Current + 3 years
(STIP/TIP)
10-Year
Notes: The construction work plan is a 10-year planning document. It lists projects that are up to 6 years further out than what the STIP or TIP lists.

## Slide 29: Project Planning
CWP
(Construction Work Program)
State and federally funded projects that the GDOT Transportation Board has approved.
CWP = STIP/TIP + 6 years = 10 years
CWP project will be placed in the STIP when the project elements are proposed to be started within the current or subsequent 3 years.
Notes: (click 1) The CWP includes both State and federally funded projects that the GDOT Transportation Board has approved.
(click 2) The CWP programs projects for the next 10 years.
(click 3) CWP project will be placed in the STIP when the project elements are proposed to be started within the current or subsequent 3 years.

## Slide 30: Learning Objective Review:
What is the STIP?
  A 4-year program for all federal funded transportation projects.
  A 10-year program for all federal and state funded projects.
  A 4-year program for federal funded MPO
  projects.
  A document that tells GDOT which
  projects to pick.
Notes: [Have participants raise the paddle that matches their answer. Answer: A]

## Slide 31: Learning Objective Review:
Which is NOT true about the TIP?
TIP stands for Transportation Improvement Plan.
Each MPO has a TIP.
The TIP is the same as the STIP.
The TIP includes federal funded projects.
TIP only includes projects programmed for a particular MPO.
Notes: [Have participants raise the paddle that matches their answer. Answer: C]

## Slide 32: Learning Objective Review:
True
  CWP includes the STIP plus 6 years for a total of 10 years and must be approved by the GDOT Transportation Board.
or False
Notes: [Have participants raise the paddle that matches their answer. Answer: True]

## Slide 33: Learning Objective Review:
What is minimum population requirement for an MPO?
  5
  5,000
  50,000
  500,000
Notes: [Have participants raise the paddle that matches their answer. Answer: C]

## Slide 34: PM Metric Compliance
Milestones
TPro PM Notes
Primavera P6 Updates
Cost Estimates
TPro Contacts
Active Schedules
PCRFs
Escalation Memos
PSU
TPro Design Notes (if consultant or local designed)
TPro Expanded Description
Notes: (click 1) We will now discuss the 11 metrics that OPD project managers must keep compliant.

## Slide 35: 3 Pillars of Project Management
Scope
Schedule
Budget
Notes: What are the 3 pillars of project management? (give time for answers)
(click 1) scope, schedule, and budget

## Slide 36: Which PM Pillar Does Each Metric Correspond With?
Milestones
TPro PM Notes
Primavera P6 Updates
Cost Estimates
TPro Contacts
Active Schedules
PCRFs
Escalation Memos
TPro Expanded Description
TPro Design Notes (if consultant or local designed use for contract info)
Project Status Update (PSU)
HINT: More than one pillar may apply
Notes: [Directions: Pass out a copy of this slide to each participant. Give the participants 5 minutes to complete. Answers will be revealed on the next few slides. ]
Think about the 3 PM pillars. Which pillar is associated with each of these PM metrics? Write your answers beside each metric. Hint: There may be more than one pillar that applies to each.

## Slide 37: PM Pillar: Budget
TPro PM
Notes
Cost
Estimates
Escalation
Memos
Project Status
Update (PSU)
Notes: First, let’s focus on metrics related to the budget pillar. Which of the PM Metrics are related to this pillar? (give participants an opportunity to answer before revealing the answers)
(Click 1) TPro PM notes: In the PM notes, the PM must report on the current status of the PE budget.
(click 2) Cost Estimates: The cost estimates help GDOT to plan their budget for the program as well as the entire Department.
(click 3) Escalation Memos: If a milestone is missed, what are the ramifications? Are more funds needed? Do the funds need to be moved to another fiscal year? The memo explains how being behind schedule will affect the project’s budget.
(click 4) Project Status Update: This document is maintained and updated by the PM. Within the document is a section about the cost estimates.

## Slide 38: PM Pillar: Schedule
Milestones
TPro PM Notes
Primavera P6 Updates
Active Schedules
PCRFs
Escalation Memos
PSU
Notes: Next, let’s discuss the schedule pillar. Which metrics apply to the schedule pillar? (give them time to provide responses)
(click 1) Milestones: These are the determine if the project is on schedule or not. By making a milestone per the baseline date, the schedule is being met.
(click 2) Tpro PM Notes: Part of the notes that the PM must report include stating whether the project is on schedule, behind schedule, or at risk.
(click 3) P6 Updates: Primavera P6 is the scheduling software. P6 must be updated to accurately know if a project is on schedule.
(click 4) Active Schedules: As the metric’s name implies, every project must have a schedule that is being followed to deliver it.
(click 5) PCRF: This is must be submitted when a schedule’s baseline dates have to be changed. This is the form to request an schedule with new baseline dates.
(click 6) Escalation Memos: The memo is required when a milestone is missed. As previously discussed, the milestones are part of the schedule.
(click 7) Project Status Update: This is the document that the PM prepares and updates monthly for executive management. It contains a section that notes the schedule as being on schedule, behind schedule, or at risk.

## Slide 39: PM Pillar: Scope
TPro PM
Notes
Escalation
Memos
TPro Expanded
Description
Project Status
Update (PSU)
Notes: The final pillar is the scope pillar. Which metrics apply to the scope pillar? (give them time to respond)
(click 1) Tpro PM Note: The first thing in the PM notes is information about the type of project (scope) and the status of the concept report. The concept report sets the scope of the project.
(click 2) Escalation memos: When the milestone is missed, a reason for the miss must be documented. It may be due to a change in the scope. If it is, then it would be stated in the escalation memo.
(click 3) Tpro Expanded description: When the concept is approved, a description of the preferred alternative must be written in Tpro.
(click 4) Project Status Update: There is a section for the scope description.

## Slide 40: Which Metrics Have Expirations?
Milestones
TPro PM Notes
Primavera P6 Updates
Cost Estimates
TPro Contacts
Active Schedules
PCRFs
Escalation Memos
TPro Expanded Description
TPro Design Notes (if consultant or local designed use for contract info)
Project Status Updates (PSU)
Notes: Look at the same 11 metrics and consider which ones must be updated. Mark the ones that you think have expirations.
[Directions: Participants should use the same slide that was previously given. Give participants one minute to write down their answers. Reveal the answers on the next slide.]

## Slide 41: Which Metrics Have Expirations?
TPro PM Notes
Every 30 Days
TPro Design Notes
Every 30 Days
Cost Estimates
Annually
Project Status Update (PSU)
Every 30 Days
Notes: Which metrics have expirations? (ask for answers before revealing them)
(click 1) Tpro PM notes must be updated every 30 days at a minimum. The PM notes always end with the PM’s initials and the date the notes were last updated.
(click 2) Cost estimates must be undated annually at a minimum. The annual date is based on the date that the last cost estimate for that phase of funding was approved. In other words, it must be approved no later than one year after the last approved cost estimate.
(click 3) The Tpro Design Notes are used by the PM is a GDOT consultant or local sponsor is designing the project. If this is the case, then this field contains information related to who to contact about the design and any contracts with a consultant. Like the Tpro PM notes, the design field’s notes always end with the PM’s initials and the date the notes were last updated.
(click 4) The PSU must be updated every 30 days at a minimum. A copy of the PSU is saved each month. The expiration is to ensure that the notes are current and up to date when executive management reviews the document.

## Slide 42: Learning Objective Review:
Which are NOT OPD compliance metrics?
  TPro PM Notes, TPro Expanded Description, TPro Contacts
  Escalation Memo, PCRF, Active Schedule
  Milestones, Cost Estimates, Primavera P6
  Monthly Status Meeting, ROW Status Meeting, Let Status Meeting
Notes: [Have participants raise the paddle that matches their answer. Answer: D]