## Slide 1: GDOT Procurement Process Overview
10.04.2024
Notes: The purpose of the training is to provide an overview of the steps of procurement and the basic level of understanding of the various types of contracts.
Training Time: 30 min

## Slide 2: Learning Objectives
Contracts
Scoping Process
Procurement Requisition Package
Notes: In this lesson, you will:
(click 1) learn about the different types of contracts that may be used with a consultant;
(click 2) understand the basic steps of the scoping process for a contract or task order; and
(click 3) understand the required components of the procurement requisition package.

## Slide 3: Types of Contracts
Master Contract
Task Orders
  Lump Sum
  Cost Plus Fixed Fee (Firm Fixed Fee)
  Cost Per Unit of Work (Menu of Services)
  Specific Rate Compensation (Billable Rates)
Notes: (click 1) GDOT often has consultants compete for a master contract. A master contract outlines the parameters for the type of work services that a particular consultant can perform. The master contract is not assigned to anyone one project. Instead, it is a “pot” of money and services that can be utilized for specific projects. A consultant getting a master contract issued does not guarantee that they get paid.
(click 2) For that to happen, the consultant would need to be issued a task order. A task order is a subcontract of the master contract. It will require that money from the pot of money assigned to the master contract is withdrawn and used for the services related to the work of the task order.
(click 3) Task orders can be paid to the consultant using varying methods of payment such as lump sum, cost plus fixed fee, cost per unit of work, and a specific rate compensation. The next few slides will talk more about each of these methods of paying the consultant for the task order services.

## Slide 4: Contract Types: Lump Sum
  A fixed/negotiated price not subject to any adjustment;
  the Consultant agrees to fulfill its obligation under this agreement, regardless of cost
  with no expectation of additional compensation beyond the agreed upon lump sum price in the performance of the work.
Notes:   (click 1) A lump sum contract has a fixed/negotiated price not subject to any adjustment;
  the Consultant agrees to fulfill its obligation under this agreement, regardless of cost
  with no expectation of additional compensation beyond the agreed upon lump sum price in the performance of the work. In other words, if the consultant can do the work in less time or for a lower price than agreed upon, they stand to make a larger profit. However, if it takes more money than was agreed upon, the consultant must work at a loss of profit because they agreed to do the work for a set price.

## Slide 5: Contract Types: Cost Plus Fixed Fee (Firm Fixed Fee)
  An agreed-upon fixed fee amount (aka profit) for the Prime and Sub-consultants, together with all allowable incurred costs in the performance of the scope of services.
  Each individual consultant’s fixed fee amounts will not vary with the actual cost in the performance of work by the Prime and/or Sub-consultants.
(Fixed Fee = (Direct Labor + Overhead /Indirect Cost Rate) X 10%)
Notes:   (click 1) Another type of contract compensation is the cost plus fixed fee, also known as the firm fixed fee. An agreed-upon fixed fee amount (aka profit) for the Prime and Sub-consultants, together with all allowable incurred costs in the performance of the scope of services.
  Each individual consultant’s fixed fee amounts will not vary with the actual cost in the performance of work by the Prime and/or Sub-consultants. In other words, regardless of whether the consultant gets the work done under or over budget, they will receive a 10% profit based on the original contract amount.

## Slide 6: Contract Types: Cost Per Unit of Work (Menu of Services)
  An agreed-upon cost for an agreed-upon effort per unit of work.
  The GDOT Project Manager shall manage and request the unit of work (Menu Items) to be performed by the Consultant.
  The Consultant shall not be in direct control of the number or menu items worked.
Notes:   (click 1) A third type of contract payment is the cost per unit of work which is also known as the menu of services. An agreed-upon cost for an agreed-upon effort per unit of work.
  The GDOT Project Manager shall manage and request the unit of work (Menu Items) to be performed by the Consultant.
  The Consultant shall not be in direct control of the number or menu items worked. Think of this like going to a fast food restaurant and looking at the menu. Each item can be ordered individually and for a set price. You just need to order the items you want then pay for it. This is the same for GDOT. They have set prices for specific tasks with a consultant and only pay the set fee for the tasks they GDOT wants to have.

## Slide 7: Contract Types: Specific Rates of Compensation (Billable Hourly Rates)
An agreed-upon loaded fixed hourly rate for each classification of employees,
which will not change for the duration of this task order and
provides reimbursement to the Consultant based on the actual direct labor hours worked at specified fixed hourly rates.
Notes: (click 1) The fourth type of contract is the specific rates of compensation, which is also known as the billable hourly rates contract. An agreed-upon loaded fixed hourly rate for each classification of employees,
which will not change for the duration of this task order and
provides reimbursement to the Consultant based on the actual direct labor hours worked at specified fixed hourly rates. The loaded rate is the rate of the employee to cover their hourly rate, the company’s overhead expenses, and some profit for the company. If the employee gets a raise during the use of the task order, the loaded fixed hourly rate does not change. Consequently, the consultant will make less in profit from the loaded rate. For this contract, the consultant can only get paid for the hours that were actually worked. In other words, if they work 8 hours, then the consultant is paid for 8 hours only.

## Slide 8
Notes: There is a PDP workflow that shows the pre-negotiation and scoping process.

## Slide 9
Procurement Process Overview
PM Develops Scope of Work
PM Receives Scope Input from Consultant
PM Holds Scoping Meeting with SMEs & Consultant
PM prepares GDOT's man hours
PM assembles Procurement Package
PM submits package to RTS
GDOT Negotiator coordinates/negotiates with Consultant
Contract is executed in CATS
NTP is issued to Consultant
Notes: This slide provides an overview of the procurement process that the OPD PM will follow for all consultant contracts.
(click 1) The PM develops the scope of work for the contract or task order.
(click 2) The PM receives input regarding the draft scope of work from the consultant.
(click 3) the PM hosts a scoping meeting with other GDOT subject matter experts and the consultant. Everyone provides input to ensure that all tasks and assumptions have been covered properly.
(click 4) Once the scope of work is agreed upon, the PM solicits the GDOT SMEs to assign man hours to the various tasks. At this point, the consultant is working independently on the man hours that they think are needed to complete each task.
(click 5) The PM then assembles the procurement package for the negotiation with the consultant.
(click 6) When the procurement package is ready, the PM will submit it into the request tracking system. This will trigger the Office of Procurement to take over the procurement process.
(click 7) The Office of Procurement will assign a GDOT negotiator who will coordinate with the consultant to ensure the hours that GDOT thought the tasks would take are relatively similar to what the consultant has requested for the time to complete each task in the scope of work.
(click 8) Once the negotiations have concluded, the contract is submitted into the Contract Authorization Tracking System (aka CATS) to have the contract signed by GDOT administration as well as the consultant.
(click 9) After the contract is executed, GDOT will issue notice to proceed to the consultant. NTP means that the consultant may begin the work as outlined in the scope of the contract.

## Slide 10: Scope Process: PM Responsibilities
Coordinate with consultant PM to determine scope of work required
Develop the draft scope, task list and assumptions
Upload the Draft Scope of work and cost proposal into ProjectWise for SME review
Host the scoping meeting
Notes: The PM has several responsibilities in the scope process of a contract.
(click 1) The GDOT PM consultant coordinates with consultant PM to determine scope of work required
(click 2) The PM develops the draft scope, task list and assumptions
(click 3) The GDOT PM uploads draft scope, task list and assumptions into ProjectWise for GDOT SME review prior to scoping meeting
(click 4) GDOT PM conducts Scoping meeting

## Slide 11: Scope Process: Concurrence
Upload FINAL DRAFT Scope and assumptions into ProjectWise for SMEs
GDOT SMEs provide email concurrence for scope and assumptions
GDOT SMEs enter man hours in cost proposal
Notes: (click 1) The scope concurrence process involves the GDOT PM Uploading FINAL DRAFT Scope and assumptions into ProjectWise for GDOT SMEs. It is the final scope because it has not been negotiated by the Office of Procurement. Therefore, it is still a version of the draft scope.
(click 2) After the final draft scope is available on ProjectWise, the GDOT SMEs will review it one last time and provide email concurrence for scope and assumptions
(click 3) After concurrence has been received from all of the GDOT SMEs, the SMEs, will enter the man hours for each task in the cost proposal.
GDOT SMEs enter man hours in cost proposal

## Slide 12: Procurement Requisition Package
GDOT PM assembles procurement requisition package
  OPD PRF Checklist
  Draft scope
  Scope concurrence emails
  Completed cost proposal
  Preconstruction status report
Notes:   (click 1) The PM is responsible to assembler the procurement requisition package. The package must include the following components:
  OPD Procurement Request Form (PRF) Checklist
  Draft scope which was agreed upon by both the SMEs and the consultant
  Scope concurrence emails from all of the GDOT SMEs
  Completed cost proposal with the man hours from the GDOT SMEs and the GDOT PM
  Preconstruction status report

## Slide 13: Procurement Requisition Package
GDOT PM routes package to DPM then AOH for review and signature
Once signed, GDOT PM uploads package into RTS for further processing by the office of procurement
Procurement negotiates contracts and issues notice to proceed once contract is executed
Notes: (click 1) Once the procurement requisition package is assembled, the GDOT PM routes package to DPM then AOH for review and signature.
(click 2) Once it is signed, GDOT PM uploads package into RTS for further processing by the Office of Procurement.
(click 3) GDOT Procurement negotiates contracts and issues notice to proceed once contract is executed.

## Slide 14: Questions