## Slide 1: NEPA 101: Environmental Overview for Federally Funded Projects
09.25.2025
Office of Program Delivery
(Part 2)
Notes: The purpose of this presentation is to provide an overview of the environmental process for federally funded projects.
Training Time: 1.5 hour

## Slide 2: Learning Objectives
Critical Path
Components of the NEPA document
NEPA
PDP & Permits
Notes: (click 1) You will learn the overview of the components needed for the NEPA document.
(click 2) You will understand why the environmental process is critical path for ROW authorization and Let.
(click 3) You will understand the PDP process related to the environmental permits.

## Slide 3
What are the levels of a NEPA documents?
A. CE, Technical Studies, EA
B. Resource ID, Technical Studies, CE
C. CE, EA, EIS
D. PCE, CE, EA
NEPA Review of Part 1
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: C - There are 3 levels. PCE is a subcategory of a CE. It is not a separate level of document. Resource ID and Technical Studies are part of the special studies which must be completed and approved before the NEPA document is prepared.

## Slide 4
Which statement is not true about NEPA?
A. It is needed to document the results (i.e. decisions) related to the environmental process.
B. NEPA stands for the National Environmental Policy Act.
C. It is required for projects that involve federal funds or want to maintain eligibility for federal funds.
D. It is required on all GDOT projects.
NEPA Review of Part 1
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D - Not all GDOT projects have federal funds or need to maintain eligibility for federal funds. Those project would use state funds and require the GEPA process.

## Slide 5
Which is the correct order for the environmental special studies process?
A. Field work, technical studies reports, resource ID reports, A3M
B. Resource ID reports, field work, A3M , technical studies reports
C. Field work, A3M, resource ID reports, technical studies reports
D. Field work, resource ID reports, A3M, technical studies reports
Field Work
Resource ID reports
A3M
Technical studies reports
NEPA Review of Part 1
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D - Ecologist, archaeologist, and historian must go to the site and survey the area within the environmental survey boundary (ESB) to determine what resources are there and the boundary of each resource. The resources are documented in the resource identification reports. After the reports are approved by the appropriate agency, the avoidance & minimization measures meeting is held with the designer. The plans are updated based on the A3M. Then the technical studies which explain the impacts to any resource and/or ways that impacts were avoided or minimized will be prepared for ecology, air, noise, and cultural resources (includes both archaeology and history).

## Slide 6
Components of the NEPA document
NEPA
Notes: From the training in Part 1, you should understand the environmental processes for the special studies. Also, you should know that the NEPA document is written after the technical studies have been approved. In this section, we will discuss some of the components of the NEPA document including community impacts and the public involvement process.

## Slide 7: What is evaluated under NEPA?
Environmental studies include, but not limited to:
Historical & Archaeological Resources (aka Cultural Resources)
Air & Noise Quality
Ecology
Land Use
Community Impacts
Public Involvement
Notes: (click 1) The National Environmental Policy Act requires that consideration to many different aspects of the environment be considered. The environmental studies under NEPA include but are not limited to cultural resources, air & noise quality, ecology, land use, and community impacts.

## Slide 8: What is Community Impacts?
Community Impacts ensure fair distribution of environmental:
Benefits &
Burdens
With respect to minority & low-income populations
Notes: (click 1) Environmental Justice was part of an executive order which has recently been rescinded. NEPA still evaluates the community impacts.
(click 2) Community Impacts refers to the fair distribution of environmental benefits and burdens, particularly with respect to minority and low-income populations. There are several federal laws that require this consideration, including but not limited to Title VI of the Civil Rights Act and NEPA. Many GDOT projects are minor in scope and their potential to adverse impacts to surrounding communities, including minority and low-income communities, is low. Even if adverse impacts to these communities is not anticipated, outreach in languages other than English may still be required.

## Slide 9: What is Public Involvement?
Encourages and solicits public input
Notes: (click 1) Public involvement encourages and solicits public input while providing an opportunity for the public to become informed about project development.

## Slide 10
Provides the public access to the decision-making process.
What is Public Involvement?
Notes: (click 1) Public involvement activities are also intended to provide the public access to the decision-making process.

## Slide 11: What is Public Involvement?
Fosters two-way communication and trust
Notes: (click 1) The goal of public involvement is to foster two-way communication and trust between governing agencies and the public.

## Slide 12: Types of Public Involvement: PIOH
Purpose is to:
  Inform the public
  Gather information
  Receive comments
Public Information Open House (PIOH)
Notes: (click 1) The purpose of a PIOH is to:
Inform the public of a project that is proposed in their area;
Gather information from the public; and
Receive comments from the public about the proposed project.

## Slide 13: Types of Public Involvement: PIOH
The PIOH is an informal meeting
  two to three hours (in-person)
  may hold meeting virtually
Formal presentations are not usually made
Public Information Open House (PIOH)
Notes: (click 1) The PIOH is an informal meeting with an open house format.
  Generally, it lasts two to three hours.
  GDOT may opt to hold these meetings virtually.
(click 2) Formal presentations are not usually made at these meetings.

## Slide 14: Types of Public Involvement: PHOH
Exchanges information prior to deciding on location and design
Approved draft NEPA document must be made available
Usually informal and lasts 2-3 hours
(Generally) Formal presentations are not made
Public Hearing Open House (PHOH)
Notes: (click 1) A Public Hearing Open House is different from a PIOH because the exchange of information between GDOT and the public occurs prior to making a commitment to the location and design of the project. The approved draft NEPA document must be made available at this meeting.
The PHOH is conducted in the same manner as the PIOH and generally last three hours. Generally, formal presentations are not made at these meetings.

## Slide 15: PIOH vs PHOH
 | CE | EA | EIS | Controversy | Adverse impacts to community | PDP Timing | In-person | virtual
PIOH | x |  |  |  |  | anytime | x | x
PHOH |  | x | x | x | x | After draft NEPA doc is approved | x | 
Notes: Public Information Open House (PIOH)
PIOH are generally held for CEs.
However, the project cannot have adverse effect on the community, or be controversial.
PIOHs may be held at any time during the preparation of the draft NEPA document.
They can be held in-person or virtually and method of hosting should be assessed for each project.
Public Hearing Open House (PHOH)
PHOH should be held if adverse impacts to community or if there is controversy on the project on small projects.
PHOH is held for EA and EIS documents.
PHOH meetings are held in person.

## Slide 16: NEPA document is developed after Technical Studies are approved.
Technical Studies
NEPA Document
Notes: (click 1) Until the environmental studies (resource ID and technical studies) are complete, the NEPA document cannot be written and approved.

## Slide 17: PDP Environmental Process
Distribute PFPR Report
Prepare NEPA document*
NEPA document approval*
ROW Authorization
ENV Cert for ROW Auth
Final Design
Prelim.
Begin
NEPA document prepared after:
Technical studies are approved
Plans are updated after PFPR
Notes: (click 1) NEPA documentation begins after the PFPR report has been accepted and the plans where it affects environmental resources have been updated. After PFPR, the plans are updated based on review comments. When the comments have been addressed, the project is in final design.

## Slide 18: Schedule Recovery (Potential Solution)
Distribute PFPR Report
Review NEPA doc
NEPA document approval*
ROW Authorization
ENV Cert for ROW Auth
Final Design
Prelim
Tech Studies Approval
Prepare NEPA doc
Request Concurrent Reviews
Notes: (click 1) If trying to recover the schedule, request permission from OES to overlap the technical studies approval and the review of the draft NEPA document.

## Slide 19: Design Changes & Technical Studies
Approved
Addendum
Technical Studies Reports
Design Changes
Review/Approval Process
Notes:     (click 1) Caution: Do not allow the designer to make changes that would impact the approved technical studies prior to ROW Authorization. If there are changes, the NEPA document and technical studies have to be amended; therefore, it would cause delays to environmental certification for ROW Authorization. Changes should be made after ROW Authorization and prior to FFPR, if possible. Any design changes should be communicated to the NEPA team (both consultant and OES) that may affect an environmental resource.

## Slide 20
NEPA Doc
approval
Design Changes & Technical Studies
Approved
Addendum
Design Changes
Review/Approval Process
Notes: (click 1) Remember that the project cannot proceed with the NEPA document approval until there are approved technical studies and no pending addendums.

## Slide 21: NEPA Document & ROW Authorization
ENV Cert
L&D approval
ROW plan approval
NEPA doc
approval
ENV approval date
L&D approval date
Notes: (click 1) The location and design (L&D) notification must include the date of the approved NEPA document. The ROW plans cannot be approved until the L&D is approved; hence, the ROW plan approval is dependent on NEPA approval.

## Slide 22
OES cannot certify for ROW Authorization until the NEPA document is approved.
.
ENV Cert
NEPA Doc
approval
ROW Auth
NEPA Document & ROW Authorization
Notes: (click 1) OES cannot certify for ROW Authorization until the NEPA document is approved.

## Slide 23
Environmental is a CRITICAL PATH item to ROW Authorization.
ENV Cert
Approved ROW Plans
ROW Auth
NEPA Document & ROW Authorization
Notes: (click 1) For the ROW Authorization, the approved NEPA document is needed for both the approved ROW plans and the environmental certification. Therefore, environmental is a critical path item to ROW Authorization. Remember that ROW plans are not approved and environmental certification cannot be obtained without an approved NEPA document. Both of these items plus a detailed ROW cost estimate are needed to authorize the funds to purchase ROW.

## Slide 24: NEPA Re-evaluation Document & Let
Approved NEPA doc
NEPA re-eval approval
CST Authorization
ENV Cert for CST Auth
Final Design
FFPR
Special Studies re-eval approval
*graphically representation only – not to true timeline
ENV Lockdown Plans
Notes: (click 1) If a project does not have ROW, a NEPA document still needs to be approved prior to FFPR. The exception is if the project has an expedited schedule. After FFPR, the plans are updated based on review comments. When the comments have been addressed, the plans are provided to the environmental SMEs to prepare re-evaluations. Basically, the SMEs review the previously approved technical studies against the updated final plans. Then, the reports are updated to match the current impacts or state that they have not changed. After the special studies reevaluations have been approved by the appropriate agency, then the NEPA reevaluation is prepared. Remember the NEPA document always summarized the impacts as listed in the latest approved version of a technical study report.
(click 2) The designer should provide environmental lockdown plans either 31 or 38 weeks prior to the management let date. The reevaluation reports are based on the lockdown plans.
Any design changes should be communicated to the NEPA team (both consultant and OES) that may affect an environmental resource.
(click 3) If a project does not have ROW, a NEPA document needs to be approved prior to FFPR. If there was a ROW Authorization, the NEPA document would be approved prior to the authorization.

## Slide 25
NEPA re-evaluation purpose:
Review of the final plans
Document changes or no changes since NEPA approval
Special Studies Re-evaluations
Agency Approvals
NEPA Re-evaluations
FHWA Approval
ENV Certification
If there are permits, approval is needed before ENV cert
NEPA Re-evaluation Document & Let
Notes:   (click 1) NEPA re-evaluation is the review and documentation of the final plans as related to environmental resource impacts. The review is to determine if there are any impacts changes from what was previously documented and approved.
  (click 2) Step 1: All environmental SMEs must review the plans to ensure that the approved technical studies are still valid. Then the SME will write an addendum or memo stating the changes since the technical study was approved.
  (click 3) Step 2: the NEPA re-evaluation document is written and approved by FHWA.
  (click 4) Step 3: Once all re-evaluations are complete, the project can be environmentally certified.
  (click 5) Remember that project cannot be certified environmentally without the approved environmental permits, if applicable.

## Slide 26
*graphically representation only – not to true timeline
Concurrent Processes
NEPA Permits & Environmental Certification
CST Authorization
Final Design
FFPR
ENV Lockdown Plans
NEPA re-eval approval
ENV Cert for CST Auth
Special Studies re-eval approval
Permit(s) Prepared
Permit(s) Approved
Approved NEPA doc
Notes: (click 1) When the environmental lockdown plans are received the ecologist will prepare both the ecology reevaluation and any required environmental permits. The permits will be submitted to appropriate agency for approval. Both the NEPA re-valuation and approved permits are required for environmental certification.

## Slide 27
What are the 3 main steps of the NEPA process?
(list the 3 steps in order)
Resource ID
Technical Studies
NEPA Document
Environmental Process Review
Notes: (Give them time to write down answers.)
(Click 1) Resource ID is the first step. You need to know what the environmental resources are that are located on or near the project.
(click 2) Technical studies is the 2nd step. These are the reports that document the impacts to the resources.
(click 3) NEPA document is the last step. It summarizes the information from the special studies (resource ID & technical studies) plus adds additional information on subjects like public involvement and community impacts.

## Slide 28
What two items are required for ENV certification for Let?
Approved Permit(s) (if applicable)
Approved NEPA Reevaluation
Environmental Process Review
Notes: (give the participants time to write down the answers.)
(click 1) The order of the answer does not matter. Both the approved permits, if applicable, and the approved NEPA re-evaluation are required for the environmental certification for let.

## Slide 29
Why is the environmental process critical path to ROW authorization? (list 2 reasons)
Without an approved environmental document, environmental certification cannot be issued.
The L&D needs the environmental approval date. The ROW plans need the L&D approval date.
Environmental Process Review
Notes: (give participants time to write down answers)
(click 1) Without an approved environmental document, environmental certification cannot be issued. The environmental certification is a requirement to authorize the funds for ROW.
(click 2) Withing the L&D document, the date for the environmental approval is required. Until the L&D has this date, the L&D cannot be approved. The ROW plans’ cover sheet requires the L&D approval date to be filled out. Wihtou.

## Slide 30
Why is the environmental process critical path to CST authorization? (list 2 reasons)
Without an approved environmental document or reevaluation, environmental certification cannot be issued.
CST fund authorization requires an environmental certification.
Environmental Process Review
Notes: (give participants time to write down answers)
(click 1) Without an approved environmental document or reevaluation, environmental certification cannot be issued.
(click 2) CST fund authorization requires an environmental certification.

## Slide 31: Environmental Permits
Permit | Agency | Permitted Activity
Section 404 of the Clean Water Act | US Army Corps of Engineers (USACE) | Impacts to waters of the US (wetlands, open waters, & streams)
Stream Buffer Variance (SBV) | Georgia Environmental Protection Division (GAEPD) | Impacts to state mandated buffers
Section 408 of the Rivers & Harbors Act | USACE | Impacts to USACE owned-land
Section 26a of TVA | Tennessee Valley Authority Act (TVA) | Impacts to Tennessee River, its floodplain, or its tributaries
Notes: This slide is intended to expose the PM to the various types of permits and permit activities that may be triggered on a project. The PM is not expected to memorize this information. (read the slide)

## Slide 32: Environmental Regulations
Permit | Agency | Permitted Activity
Section 4(f) of the US Department of Transportation Act of 1966 | Federal Highway Administration (FHWA) | Publicly owned parks and recreation lands, wildlife and waterfowl refuges, and any public or private historic site listed or eligible for listing on the National Register of Historic Places.
Section 106 of the National Historic Preservation Act of 1966 | Coordination between FHWA, SHPO, tribal historic preservation office (THPO); and other project specific consulting parties | Identifies and assesses the effects of a listed and eligible historic properties (buildings, structures, archaeological sites, districts, and landscapes) including public views and concerns about preservation.
Notes: This slide is intended to expose the PM to the various types of permits and permit activities that may be triggered on a project. The PM is not expected to memorize this information. (read the slide)

## Slide 33: Questions?