## Slide 1: P6 Compliance
09.17.2025
Office of Program Delivery
Notes: Note: The training course P6 Basics should be taken prior to this course.
The purpose of this training is to provide the PM with the skills to update Primavera P6 and meet their metric for P6 compliance.
Training Time: 1.5 hours

## Slide 2: Learning Objectives
OPD Metrics Related to P6
Basic P6 Schedule Components
Why Is Accuracy Needed?
P6 Update Responsibility
P6 Compliance
Notes: The learning objectives for this trainings are:
* Understanding the relationship of some of the OPD metrics with P6
*Understanding the basic components of a GDOT Schedule
Understanding why P6 information being accurate is important.
Understand how to determine who is responsible for updating P6.
Understand how to check that P6 is being maintained and compliant.

## Slide 3
P6 Basics Recap
What is the terminology for organizing tasks into a more manageable system?
Hierarchy
B. Schedule Program
C. Task & Driver
D. Work Breakdown Structure
Notes: [Directions: Give participants time respond.)
(click 1) Answer: D -This is the WBS or work breakdown structure. It subdivides tasks into smaller tasks.

## Slide 4
What is the terminology for days left to complete an activity?
Planned Duration
B. Remaining Duration
C. Baseline Finish Date
D. Expected Finish Date – Actual Start Date
P6 Basics Recap
Notes: [Directions: Give participants time respond.)
(click 1) Answer: B -The number of days left to complete an activity is the remaining duration. Answer D was the formula for how to calculate the remaining duration.

## Slide 5
What is the terminology determining the order of tasks?
Predecessor-Successor
B. Old-New
C. Start-Finish
D. Because I Said So
P6 Basics Recap
Notes: [Directions: Give participants time respond.)
(click 1) Answer: A - Predecessors are tasks that either start before or must be completed before another activity. Successors either start after a predecessor has started or after the predecessor has completed.

## Slide 6
The P6 Schedule is just a project manager tool.
True
or
False
P6 Basics Recap
Notes: [Directions: Give participants time respond.)
(click 1) Answer: False - Although the PM does use it as a tool to help accurately report the project’s status, evaluate risk, and develop a recovery plan if needed, it is also used by GDOT management. GDOT management uses the schedule to determine if funds will be authorized on time, to plan the budget for letting projects, and to provide information to people outside of GDOT.

## Slide 7: P6 Schedule: OPD Metric
Notes: Next, we discuss in a little more depth the parts of the schedules that are involved on all OPD delivered projects.

## Slide 8: Why does OPD evaluate the Metrics?
Clear Communication
Measure Performance
Build Trust & Reputation
Assess Area of Improvement
Notes: (click 1) Metrics provide a way for the PM have clear communication with OPD management. This check and balance system that provides a way for the PM to understand what expectations are for their role.
(click 2) It also is way for management to measure performance for specific tasks.
(click 3) Through the evaluation of metrics, a PM can build trust and a positive reputation with leadership.
(click 4) It also provides an assessment of where improvement may be needed for the PM.

## Slide 9: OPD’s Metric: P6 Related
Approved Schedule
TPro PM & ROW/Let Notes
PCRF (if needed)
PM Milestones
Notes: There are several metrics that the PM must keep compliant that involve Primavera P6.
(click 1) Every project must have an approved schedule. There is a formal process of preparing the initial schedule and then submitting it to the Schedule Review Committee for approval. How can a project be managed properly if it is missing the schedule pillar of the project management?
(click 2) The schedule sets the baseline dates which the PM must meet for the three milestones. The three PM milestones are PM submit concept report, PM request PFPR, and PM request FFPR.
(click 3) The PM must update the TPro PM notes, as well as the ROW/Let Notes monthly. Part of the reporting is using the information from the P6 schedule to determine if the project is on baseline, off baseline, or at risk.
(click 4) Sometimes it is not possible to recover the schedule. When recovery is not possible, then a project change request form may be required. If it is known that a PCRF is required, the PM is responsible to prepare and submit the PCRF as soon as possible to avoid further delays.

## Slide 10: P6 Schedule: What Is It?
Notes: Next, we discuss the parts of the schedules that are involved on all OPD delivered projects.

## Slide 11: P6 Schedules
PDP Tasks
OPC Template
Preconstruction Schedule
Notes: All of the P6 schedules that OPD uses have the following items in common:
(click 1) The schedule is comprised of a work breakdown structure based on the plan development process.
(click 2) The schedule is developed using a template that has been created by the Office of Program Controls.
(click 3) The schedule is for activities related to the preconstruction process only. It does not include activities that will occur during construction of the project.

## Slide 12: P6 Schedules: Main Components
Design Phases
Environmental Process
Utility Coordination
ROW Design & Acquisition (if applicable)
Certifications
Procurement
Notes: All of the P6 schedules that OPD uses have the main activities related to:
(click 1) The steps needed for each design phase of project. The design phases may include concept, preliminary, and final design.
(click 2) The steps needed for utility coordination are included.
(click 3) The various components of the environmental process are detailed as tasks in the schedule.
(click 4) All projects must receive certifications in order to authorize funds. There are different certifications required for ROW fund authorization and Let or construction fund authorization.
(click 5) If a project is going to acquire or use land that is outside of the existing GDOT property limits, then ROW plans will need to be designed and time to acquire the ROW or easements will need to be included with the schedule.
(click 6) If GDOT is hiring a consultant to perform work on the behalf of GDOT, then steps and time in the schedule will be allotted for the procurement process.
Each project has to be evaluated to determine what other tasks specific to that project would be required beyond these basic components.

## Slide 13: P6 Schedule: Why Must It Be Accurate?
Notes: As a PM, it is important to understand why the accuracy of the information in P6 is important.

## Slide 14: P6 is a Communication Tool
Notes: P6 is the communication tool. This is not a project diary or record.
Rather, this is a method of communicating the status and health of the project to GDOT executive management.

## Slide 15: P6 Schedule: 3 Sets of Dates
Baseline Start & Baseline Finish | Start & Finish | Actual Start & Actual Finish
Planned dates Approved schedule dates No PM action | Projected dates Info that is entered into P6 No PM action | Task occurred dates Dates that are entered into P6 PM or SME updates info
Follow these dates
Notes: There are 3 sets of date on a P6 schedule: Baseline dates, start & finish dates and actual dates. The baseline start and finish dates are planned dates that keep the project on schedule. These dates were determined when the schedule was approved.
The start and finish dates are projected dates. As dates for various tasks are entered into P6, the schedule projects when the outstanding tasks will start and finish. These dates are automatically populated. No action is needed by the PM. However, if the P6 information is being kept current and accurate, these dates will let the PM know how each task is affected by late or missing tasks.
The actual start and finish dates are based on when a task occurred. This information is entered into P6 by the PM or another SME.
(click 1) The PM should always make every effort to follow the baseline dates.

## Slide 16: P6 Schedule: 3 Sets of Dates
Baseline
Projected
Actual
Excerpt of P6 printout
Notes: This is an excerpt from a P6 printout for a project. There are 3 sets of dates included.
(click 1) As the PM, you should look at the baseline dates to determine when a task is due and how to communicate the due date to the appropriate team member, if applicable.
(click 2) Be careful that you do not look at the projected dates instead of the baseline dates. These are dates that are generated (aka projected) based on the actual information as entered into P6.
(click 3) If the schedule is behind, look for tasks that are missing either an actual start or actual finish date. Ask yourself if this is something that should be updated? Cross reference the baseline date to see if the activity should have started or finished by now.

## Slide 17
Excerpt of GDOT Mgmt. PSR
Notes: The PSR always includes some activities from the P6 schedule. The schedule table on the PSR always includes baseline dates, start & finish dates and actual dates.

## Slide 18
Excerpt of GDOT Mgmt. PSR
Notes: At the top right side of every PSR are 3 different Let dates. One is baseline, one is schedule, and one is the management let date.

## Slide 19
Baseline Let Date = Approved date in P6 Schedule
Schedule Let Date = Projected date based on info in P6
Management Let Date = Date based on let calendar
Notes: The baseline and schedule let date information is imported for the P6 schedule.
(click 1) Baseline let date is the date that is listed for the let task in the approved P6 schedule.
(click 2) The schedule let date is the projected let date based on the information that has been entered into P6.
(click 3) The management let date is based on a let calendar.
(click 4) The baseline let date and Management let date may not be the same date. They will be in the same month and year. The PM is to manage the schedule for the management let date not the baseline let date.

## Slide 20
Schedule Let Date – Mgmt Let Date = On or Off Schedule
Example: 9/6/27-5/15/27 = 4 months
Interpretation:
P6 is not up-to-date; or
Project is not on schedule for let
GDOT Mgmt
Notes: The date difference between the schedule let date and the management let date is used by the PM as a tool to aid in deciding if the project is on schedule for let.
(click 1) For this project the schedule let date is 9/6/24 and mgmt. let date is 5/15/27. That is a 4-month difference. In other words,the project is projected be 4 months late for the let date.
(click 2) If the project is more than 1-2 months difference, it tells the PM that either 1) P6 is not up-to-date or 2) that the project is not on schedule for let.
(click 3) The schedule is being communicated to GDOT management each time that they look at a PSR regardless of what the PM’s TPro notes say.

## Slide 21: P6 Schedule: Whose Responsibility?
P6 Schedule: Whose Responsibility?
Notes: There are many activities in a P6 schedule. Next, we will discuss who is responsible for updating the P6 activities.

## Slide 22: P6 Responsibility
GDOT SME
GDOT Office
Consultant
OPD PM
Notes: (click 1) Every project will have multiple subject matter experts working on the project. For example, environmental staff, District ROW coordinator, District Utility Coordinator, and possibly an in-house designer.
(click 2) Various GDOT offices will have the responsibility of reviewing and approving documents and plans.
(click 3) Some project have a consultant hired to complete specific tasks. These tasks could include design and environmental studies.
(click 4) The PM is responsible to maintain current and accurate information for the P6 tasks that are assigned to OPD. In addition, the PM must continually review the schedule and coordinate with other SMEs to ensure that the other tasks are being properly updated in a timely manner. Ultimately, the PM is responsible for the accuracy of the schedule.

## Slide 23: P6 Responsibility
Responsible Office
Notes: (Click 1) Primavera P6 can tell you who is doing the work or what office coordination may be needed with. This is also telling the PM who is to update the P6 information related to these tasks. The PM is not to fill in the information for other offices. However, the PM may need to remind a SME to update P6.
(click 2) The PM is to fill in information for the office listed as PRG DEL which is short for program delivery. The exception to this rule is if the project is designed by a consultant. Then the PM will need to collect the P6 information from the designer and enter it.

## Slide 24: P6 Data Entry Responsibility: PM
Consultant Designer
In-house or consultant Environmental
Program Delivery Tasks
Notes: (Click 1) The PM is responsible to update all tasks that are assigned to Program Delivery.
(click 2) If a consultant designer is hired by GDOT or by a local sponsor, the designer does not have access to P6. Therefore, the PM will have to update any design related tasks in P6. This is why it is important to discuss P6 at the monthly team project meetings.
(click 3) PM do NOT update environmental tasks. Both GDOT SMEs and consultant environmental SMEs have access to P6.

## Slide 25: P6 Data Entry Responsibility: PM
Other GDOT Offices
Exception: If a task is scoped to be completed by the consultant, then the PM would enter the information.
Example:
Responsible Office says OMAT. However, consultant may have been hired to prepare the report.
Notes: (Click 1) The PM does not update P6 tasks that belong to other offices.
(click 2) The exception is if a consultant has been hired to perform the task. Then the PM would update P6 on behalf of the consultant.
(click 3) For example, the Phase I ESA report (aka hazardous waste report) is to be prepared by the Office of Materials and Testing. However, the PM should know what the consultant is contracted to complete as part of the scope of work. If the scope includes the Phase I ESA, then the PM would be responsible to update P6 for this task.

## Slide 26: Updating a P6 Schedule – HOW TO BE COMPLIANT
Updating a P6 Schedule:
How to Be Compliant
Notes: Next, we will discuss how to keep compliant with the P6 information.

## Slide 27
Notes: Get ready to eat the frog and get P6 updated. For those that may not be familiar with the phrase “Eat that Frog”, it means to tackle the work or life items that you don’t want to do first. In other words, get the challenging tasks finished and then move onto easier tasks that need to be completed.

## Slide 28: Common Reasons for Noncompliance
Project has NTP but no start date or % complete shown for next phase
Inconsistency between PM/SME Comments and P6
Milestone updated but predecessor are not
Notes: There are some common reasons why the P6 schedule may not be compliant.
(click 1) The project has received notice to proceed but the PM has not entered a start date or a percentage complete for the phase of work related to the NTP. If NTP has been issued, the percentage complete should not be zero.
(click 2) The SME may have updated P6, but the PM has not either reviewed the P6 updates or recently communicated with the SME about the status of the task. This can lead to inconsistencies between the PM and SMEs comments and reporting to GDOT management.
(click 3) The PM entered the information into P6 for the milestone but did not update the information related to the milestone’s predecessors.

## Slide 29
BL Start
BL Finish
Level of Effort (LOE) Activity
Notes: (click 1) Some P6 activities are denoted as LOE which stands for Level of Effort. LOE activities are not updated directly by the PM or SME. These activities are a summary of the work that is occurring in the WBS subtasks. If the subtasks are not updated, then the LOE is not updated.
(Click 2) In this example, the LOE starts when the first activity for the concept phase starts.
(click 3) The LOE ends with the date of the last concept activity. The predecessor and successor subtasks between these activities all contribute to the LOE.

## Slide 30
BL Start
BL Finish
Summary Activity
Notes: (click 1) A summary activity is similar to a LOE activity. However, it is used for a subset of tasks. It is not an activity that the PM or SME can update. The information for the actual dates are rolled up from subtasks and the % complete is based on the predecessors to the final task in the summary.
(Click 2) In this example, the LOE starts when the first activity for the environmental resource identification starts. Receiving the environmental survey boundary (aka ESB) triggers the start.
(click 3) The summary’s end date is based on the finish date of the last activity. In this case, seasonal studies for protected species may cause it to the be last activity completed as part of resource identification. The predecessor and successor subtasks between these activities all contribute to the summary’s actual P6 information.

## Slide 31
PSR P6
Notes: (click 1) The information in P6 is then generated on the PSR which GDOT executive management will review. Remember for LOE and Summary activities, the PM should review them for missing actual start, actual finish, and % complete. If the percentage complete is missing or too low for the activity, the schedule’s projected dates will be pushed out. If any of it is not shown correctly, this is a trigger that the PM should review P6 and find out what information has not been properly entered.

## Slide 32
PSR P6
Notes: (click 1) Remember that the information in P6 will determine the schedule let date. When the schedule let date is compared to the management let date, it should accurately reflect the status of the project as on schedule or off schedule.

## Slide 33
Which items on the PSR does the PM and GDOT Management Review to know if a project is on schedule?
P6 Table
B. Schedule Let Date
C. PM Notes
D. All of the Above
P6 Schedule Review
Notes: [Directions: Give participants time respond.)
(click 1) Answer: D - The information from P6 is provided in the table and as the Baseline Let Date and the Schedule Let Date. The PM reviews the Schedule let date with the Management let date to determine if the project is on schedule or not. Then the PM puts writes this in the TPro PM Notes. Each time the PM updates the TPro notes, the schedule portion of the notes should be reviewed to make sure that it is still accurate.

## Slide 34
Is the project on schedule for Let?
True
or
False
P6 Schedule Review
Notes: [Directions: Give participants time respond.)
(click 1) Answer: False (proceed to next slide to ask how many months off it is)

## Slide 35
How many months off the let schedule is the project?
4 months
9 months
It is ahead of schedule
7 months
P6 Schedule Review
Notes: [Directions: Same PSR as the previous slide. Give participants time respond.)
(click 1) Answer: 7 months - Don’t forget that the schedule let date is the projected date and the management let date is one that is set by the let calendar. The difference between the two dates is how many months ahead or behind the schedule is.

## Slide 36
The project is on schedule.
True
or
False
P6 Schedule Review
Notes: [Directions:. Participants should have a copy of this slide/PSR to help them read it better. Give participants time respond.]
(click 1) Answer: False (go to the next slide to demonstrate how the PM will know it is false)

## Slide 37
The next activity to be completed that is associated with the next milestone is what?
Concept Report Development LOE
Environmental Resource Identification Summary
PFPR Inspection
FFPR Inspection
P6 Schedule Review
Notes: [Directions: Same PSR as the previous slide. Give participants time respond.]
(click 1) Answer: C - Both the concept report and the environmental resource ID are shown as being 100% complete and an actual start and finish date. After PM submits Concept Report, the next milestone for a PM is to request PFPR. Since PFPR has not been completed yet per the information in the schedule, it is the next activity to be associated with the milestone. PFPR inspection is the meeting that is held after the PM requests the meeting.

## Slide 38
Is the PFPR inspection on schedule?
True
or
False
BL start/finish = 7/25/24
(Projected) Start/finish = 9/12/25
2 months behind BL (potentially at risk of missing BL date)
P6 Schedule Review
Notes: [Directions: Same PSR as the previous slide. Give participants time respond.]
(click 1) Answer: False - Per the information on the schedule, PFPR inspection is projected to be held almost 2 months late.

## Slide 39
Based on what you have reviewed on the PSR, are the PM Notes accurate?
True
or
False
P6 Schedule Review
Notes: [Directions: Same PSR as the previous slide. Give participants time respond.]
(click 1) Answer: False - The schedule is showing as 4 months behind for let. The PFPR inspection was to be held by 7/24/24 per BL. The PM requesting PFPR comes before the inspection. The notes state that the request will not be until 10/17/25. None of the P6 information supports that the project is on schedule as stated in the PM notes.

## Slide 40
Actual Start
B. Actual Finish
C. % Complete
D. It is up to date.
What has the PM not updated for the roadway plans?
P6 Schedule Review
Notes: [Directions: Same PSR as the previous slide. Give participants time respond.]
(click 1) Answer: C - There is an actual start date. This means that some work has been completed. When a task has an actual start date, it cannot show as 0% complete.

## Slide 41: Questions?