## Slide 1
Notes: This training is part 1 of a 5-part series related to the PDP process. The purpose of this training series is to provide a foundation level of understanding of the PDP process. It will cover every process or study that a project may require per the PDP process. For additional information, the PDP manual should be referenced. In PDP Overview #1, the training will cover the Project Team Initiation Process, commonly referred to as PTIP.
Training Time: 45-60 minutes

## Slide 2: Learning Objectives
Purpose of PTIP
What PTIP Does NOT Do
Government Estimator Role
PDP Process
P
D
P
Notes: The learner will understand where PTIP fits into
(click 1) the Plan Development Process
(click 2) its purpose, and
(click 3) the key aspects of what it does—and does not—cover.
(click 4) Finally, this training will examine the role of Government Estimator Consultants in the process.

## Slide 3
Plan Development Process
PTIP Phase
Preliminary Design
Final Design
Construction
Concept Phase
Project Team
Initiation Process
Notes: (click 1) PTIP takes place before the concept development phase begins. It should commence no later than one year prior to the authorization of PE.

## Slide 4: When is PTIP Required?
PDP Chapter 4.6
Project is GDOT Sponsored
Project in Capital, Safety and Bridge Programs
NOT required on all OPD projects
Notes: (click 1) PTIP is conducted solely for projects sponsored by GDOT within the capital and bridge programs.
(click 2) It is not applied to projects from the safety or operations programs and
(click 3) is not a mandatory step for all projects.

## Slide 5: PTIP: Purpose
Standardizes roles
PDP Section 4.6
Schedule Timeline
Prepares Project
On schedule, on scope, & on budget
Notes: (click 1) The Project Team Initiation Process (PTIP) was developed to establish a standardized framework for defining the roles of Project Managers, Program Management Contract (PMC) Program Managers, and GDOT Subject Matter Experts.
(click 2) The information gathered during PTIP provides a basic understanding of the general timeline for the proposed project. Team members will provide input on schedule durations during the PTIP meeting.
(click 3) This process helps projects stay on schedule, within scope, and on budget, setting them up for success!!

## Slide 6: PTIP: “Why” Is It Needed?
Reduce Time to Begin the Project
Focus the Project Development
Better Understanding for Consultant Selection
Notes: (click 1) The primary goal is to streamline the transition from Preliminary Engineering (PE) funding authorization to the initiation of project development activities. This applies to both in-house efforts and consultant-led services, helping to reduce delays and improve efficiency. (Better Starts)
(click 2) To more narrowly focus the approach for project development and eliminate extraneous work.
(click 3) To provide the Consultant Selection Committee and GDOT Management a better understanding of the project in order to make more informed decisions when selecting or assigning the project team.

## Slide 7: PTIP: “Why” Is It Needed? (continued)
Introduction to the Project
Suitability for Preliminary/ Scoping Phase
Understanding of Risks
Notes: (click 1) Additionally, the purpose of PTIP is to give the project team a comprehensive introduction to the project,
(click 2) offering insight into potential risks and strategies for avoidance and mitigation.
(Click 3) It also includes an assessment to determine the suitability of incorporating a Phase I – Preliminary/Scoping Phase.

## Slide 8
PDP Process: When is PTIP?
PM ENTERS HERE
PTIP begins:
After the project is added to CWP and assigned to GDOT office
PTIP will begin no less than 1 year prior to PE authorization
WE
Excerpt of PDP PTIP Flowchart
Notes: (click 1) Once a project has been added to the CWP and assigned to a GDOT office
(click 2) PTIP will begin no less than 1 year prior to PE authorization

## Slide 9
PM ENTERS HERE
PTIP ends:
When the project is assigned and transitioned to the PM
WE
Excerpt of PDP PTIP Flowchart
PDP Process: When is PTIP?
Notes: (click 1) PTIP ends when the project is assigned and transitioned to the PM

## Slide 10
  What does PTIP stand for?
  A. Planning Time Implementation Process
  B. Project Team Initiation Process
  C. Preliminary Training Interview Plan
  D. Project Teammates Instruction Plan
PTIP Review
Notes: (direction: Read question 1 and give participants time to respond. Answer: B)

## Slide 11: PTIP Review
PTIP starts when it is assigned and transitioned to a PM.
True
False
or
ends
Notes: (direction: Read question 1 and give participants time to respond. Answer: False.) PTIP ends when it is assigned to the PM.

## Slide 12
Which is NOT a purpose of PTIP?
  A. Identify the basic timeline for the project’s schedule.
  B. Standardizing the roles of the PM, OTO, and SMEs.
  C. Assign GDOT staff to the project.
PTIP Review
Notes: (direction: Read question 1 and give participants time to respond. Answer: C)

## Slide 13: Who Conducts PTIP Activities?
Government Estimator
Project Manager
Project Info
Start Project
PTIP Process
Notes: GDOT uses two Government Estimator teams to conduct PTIP activities.
(click 1) The government estimator teams help provide the GDOT PM a more comprehensive understanding of the project prior to PE authorization.

## Slide 14: PTIP Activities
Government Estimator
Schedule Creation
PTIP Evaluation
RFQ Development (if needed)
Transition to PM
Notes: (Click 1) The government estimator is involved with 4 main PTIP activities: evaluation of the project, schedule creation, request for qualification development if a consultant is needed, and transitioning the project to the PM after PE is authorized.

## Slide 15: PTIP: Evaluation Activities
Request PJS
Review traffic and safety info
Site Visit
Gather existing information
Interviews
Environmental Screening
High-level review of Programmed Funding
Identify Project Goals
Identify Risks
Identify Project Delivery Discussion Points
Notes: (click 1) The PTIP evaluation activities include
Request PJS
Review traffic and safety info
Site Visit
Gather existing information
Interviews
Environmental Screening
High-level review of Programmed Funding
Identify Project Goals
Identify Risks
Identify Project Delivery Discussion Points

## Slide 16: PTIP: Risk Evaluation
Risk impact:
  Scope
  Schedule
  Budget
Notes: (click 1) As Risks have the potential to impact Scope, Schedule, and Budget at any time throughout the project lifecycle, they are a key focus of the PTIP as well. In order to fully understand and address risks, it is critical that the appropriate Subject Matter Experts are involved in the Risk Assessment process.

## Slide 17: PTIP: Team Members (SMEs)
Environmental
Roadway
Bridge/structures/hydrology/hydraulics
Geotechnical
Traffic
Utilities
Railroads
Right-of-Way
Construction
Notes: (click 1) The team members are comprised of various subject matter experts.

## Slide 18
PTIP Presentation
Notes: Once all the data collection is complete, the Government Estimator Consultant will present their findings at the PTIP meeting. The next few slides are snapshots from a PTIP presentation.

## Slide 19
PTIP Presentation
Notes: This slide conveys the project justification statement which is discussed in detail during the meeting.

## Slide 20
PTIP Presentation
Notes: These slides discusses some of the existing traffic and roadway conditions. The existing right of way conditions are also discussed.

## Slide 21
PTIP Presentation
Notes: These slides convey the utility risks as well as the overall risk summary. Potential risks to the project is a major topic during the PTIP meeting discussion.

## Slide 22: What PTIP Does Not Do
Not Solely Done by Gov’t Estimator
Make Final Decisions
Develop ESB
Develop or Evaluate Alternatives
Notes: (click 1)The PTIP process does not involve developing or evaluating alternatives for the proposed project.
(click 2) It is not solely conducted by the government estimator; rather, subject matter experts (SMEs) actively contribute their insights.
(click 3) Any decisions made during PTIP remain open for reconsideration in the concept phase.
(click 4) Additionally, the environmental survey boundary is not established as part of the PTIP process.

## Slide 23: What Happens After PTIP? (Before PM Transition)
Request SMEs’ Schedule Approval
SRC Reviews the Schedule
Activate Approved Schedule
Develop Schedule
Notes: (click 1) The government estimator develops the anticipated P6 schedule durations.
(click 2) SMEs are requested for review and input related to the schedule.
(click 3) Once the SMEs approve the developed schedule, the schedule is submitted for the schedule review committee to approve.
(click 4) If SRC approves the schedule, it is then activated.
(click 1) The government estimator develops the anticipated P6 schedule durations, (click 3) with SMEs providing review and input.
(click 2) Once the SMEs approve the developed schedule, it is submitted to the schedule review committee (SRC) for final approval.
(click 4) If the SRC grants approval, the schedule is then activated.

## Slide 24: What Happens After PTIP? (During PM Transition)
Share Information
Assist with Procurement Activities
Notes: (click 1) Following the PTIP meeting, if procurement activities are required, the Government Estimator supports the GDOT PM in preparing requests for qualifications, task orders, or other procurement-related documents as needed. Given their familiarity with the project's scope and any missing but necessary information or studies, the Government Estimator provides valuable insight to help develop a comprehensive procurement document.
(click 2) Additionally, they facilitate a transition meeting with the PM and DPM, allowing the PM to review available project information and ask questions.

## Slide 25
Which of the following is NOT done as part of PTIP?
  A. Develop and evaluate alternatives
  B. Develop a schedule
  C. Evaluate potential risks or challenges
PTIP Review
Notes: (direction: Read question 1 and give participants time to respond. Answer: A)

## Slide 26: PTIP Review
The government estimator is responsible for the PTIP process.
True
False
or
Notes: (direction: Read question 1 and give participants time to respond. Answer: True) PTIP ends when it is assigned to the PM.

## Slide 27: PTIP: Summary
Keeps Project on schedule, scope, & budget
Starts the Project Lifecycle
Promotes a Good Project Start
Notes: (click 1) The PTIP process can initiate the project's lifecycle, though not every project requires PTIP.
(click 2)It helps maintain alignment with schedule, scope, and budget
(click 3) while ensuring a strong project start with valuable input from experienced SMEs.