## Slide 1
Notes: This training is part 2 of a 5-part series related to the PDP process. The purpose of this training series is to provide a foundation level of understanding of the PDP process. It will cover every process or study that a project may require per the PDP process. For additional information, the PDP manual should be referenced. In PDP Overview #2, the training will cover the PDP process between scope development and concept report submission.
Materials: Provide copies of PSR and P6 excerpt for PI 0017959 & 0017693 (see slides 37, 40, & 47) for engagement learning activity. Also provide hand paddles for participants to use with the “review” slides.
Training Time: 1.5 hours

## Slide 2: Learning Objectives
What is the Concept Report & Why it is Important
5 Basic Design Steps
How to Reference a PSR and/or P6 Activities
Common Templates for the Concept Phase
Notes: (click 1) The learning objective is to understand what is a concept report and why it is important.
(click 2) The learning objective is to learn the 5 basic design steps of the concept phase.
(click 3) The learning objective is to understand how to reference a Preconstruction Status Report (PSR)and/or Primavera P6 activities for information that is needed to fill out the template documents.
(Click 4) The learning object is to be familiar with some of the common templates that are used during the Concept Phase.

## Slide 3
Plan Development Process
Concept Phase
Preliminary Design
Final Design
Construction
PTIP
Notes: (click 1) This training is going to focus on the Concept Phase of the PDP process. It is the first phase of the design process.

## Slide 4: Concept Phase
Federal $ Must
Follow
PDP
P
D
P
MOST = ALL
Have a Concept Phase
PDP Chapter 5
Concept Report
Notes: (click 1) If any federal money will be used on the project, GDOT must follow the Plan Development Process (PDP) per the oversight agreement with Federal Highway Administration (FHWA).
(click 2) Most but Not all projects have a concept phase.
(click 3) If there is a concept phase, it will be documented in a Concept Report.
Read Chapter 5 of the PDP manual for information about the Concept Phase. See Section 5.5 of the PDP manual for a list of projects that do not require concept report or meeting.

## Slide 5: Concept Report: “Why” Is It Needed
Project Justification Statement (PJS)
brief statement identifying and explaining the major issue(s) that the project is intended to address.
PDP Sections 5.2 & 5.3
“WHY”
Notes: (click 1) Project Justification Statement (PJS)
(click 2) PJS explains why a project is needed.
(click 3) The PJS is a brief statement identifying and explaining the major issue(s) that the project is intended to address.

## Slide 6: Concept Concept: “What” Is Proposed
CR Objective:
Make a project recommendation for either:
  a “Build Alternative” to address the “Project Justification Statement (PJS)”; or
  a “No-Build Alternative” of the programmed project after appropriate analyses has been investigated.
Describe the recommended “footprint” including project termini.
PDP Sections 5.2 & 5.3
“WHAT”
Notes: (click 1) The objective of the Concept Phase is explain what is the proposed design solution for the project.
(click 2) The Concept Report will make a recommendation for either
(click 3) a “Build Alternative” to address the “Project Justification Statement (PJS)”; or
(click 4) a “No-Build Alternative” of the programmed project after appropriate analyses has been investigated.
(click 5) The Concept Report that will describe the recommended “footprint” including project termini (aka end points).

## Slide 7: Concept Report Review
PJS explains the “what” the project will be doing (aka scope).
True
False
or
PJS explains WHY the project is needed.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: False – The project justification statement explains why the project is needed.

## Slide 8: Concept Report Review
All projects must have a concept report.
True
False
or
Most projects do have a Concept Report, but per Section 5.5 of the PDP manual, there are exceptions.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: False – Most projects do have a Concept Report, but per Section 5.5 of the PDP manual there are exceptions.

## Slide 9: Concept Report Review
The concept report recommends the preferred design alternative and the footprint.
True
False
or
The CR explains WHAT is to be designed and limits of the work. In other words, it states the scope of the project.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: True -The CR explains WHAT is to be designed and limits of the work. In other words, it states the scope of the project.

## Slide 10
Overview of Concept Design Process
(5 basic design steps)
Concept Layout
Draft CR
CTM
Final CR
Approved CR
Notes: (click 1) During the concept phase, there are 5 basic design steps.
Concept Layout; Draft concept report; concept team meeting; final concept report; approved concept report. Each step will be discussed in more detail in the next few slides.

## Slide 11
Notes: This slide and the next 3 slides are from the PDP workflow for the Concept Phase. The concept phase starts with the PE (preliminary engineering) funds for design being authorized. The pale blue items represent design steps in the process.

## Slide 12
Notes: There are multiple assessments occurring at the same time during the concept phase. In addition to the design analysis, the green activities represent environmental tasks and analysis.

## Slide 13
Notes: The data gathering from early in the process leads to the development of the layout. The layout identifies the potential footprint of the project including the logical termini. After the data gathering has happened, the draft concept report is prepared.

## Slide 14
Notes: Some projects may be controversial or potentially controversial. If they are, a public information open house (PIOH) may need to be held during the concept phase. Generally, PIOHs are held during the preliminary design phase. After the draft concept report has been reviewed by the PM and is in good shape, a concept team meeting is usually scheduled. Based on the input from the attendees at the CTM, the report may be updated before the final version is submitted for approval.

## Slide 15
Overview of Concept Design Process
(5 basic design steps)
Concept Layout
Draft CR
CTM
Final CR
Approved CR
Notes: Now, we will look at the 5 main design steps by starting with the concept layout.

## Slide 16: Concept Layout
The layout is a drawing representing:
  the basic location; and
  proposed design of the project.
It is NOT a detailed engineered plan.
  It is a high-level figure placed on an aerial photograph.
Notes: (click 1) The layout is a drawing representing the basic location and proposed design of the project.
(click 2) It is not a detailed engineered plan. It is a high-level figure placed on an aerial photograph.

## Slide 17
Example Concept Layout
Notes: This graphic represents what a concept layout may look like.

## Slide 18
Overview of Concept Design Process
(5 basic design steps)
Concept Layout
Draft CR
CTM
Final CR
Approved CR
Notes: After the concept layout is prepared based on the preferred alternative, the draft concept report is written.

## Slide 19: (Draft) Concept Report
Draft Concept Report (CR) outlines and explains:
  Why is the project needed?
  What is the existing design or site conditions?
  What are the proposed alternatives?
  What is the preferred alternative and why?
    This will determine the scope of the project’s work.
Notes: (click 1) Draft Concept Report (CR) outlines and explains:
(click 2) Why is the project needed?
(click 3) What is the existing design or site conditions?
(click 4) What are the proposed alternatives?
(click 5) What is the preferred alternative and why?
(click 6) This will determine the scope of the project’s work.

## Slide 20: (Draft) Concept Report
The concept report and the detailed information help to
Minimize Risks
Determine Decisions
The concept report is prepared as early in the process as possible.
Notes: (click 1) The concept report and the detailed information help to determine better decisions and help to minimize project risks.
(click 2) The concept report is prepared as early in the process as possible.

## Slide 21
Overview of Concept Design Process
(5 basic design steps)
Concept Layout
Draft CR
CTM
Final CR
Approved CR
Notes: After the draft concept report has been reviewed by the PM and has been determined that it is ready to be reviewed by other subject matter experts (SMEs), then a concept team meeting is scheduled and held.

## Slide 22: Concept Team Meeting(s)
If there is a concept phase, then the following meetings may be required:
  Initial Concept Team Meeting (ICTM)
  Concept Team Meeting (CTM)
Notes: (click1) If there is a concept phase, then the following meetings may be required:
(click 2) Initial Concept Team Meeting (ICTM)
(click 3) Concept Team Meeting (CTM).
[Presenter Note: Each will be discussed on the following slides.]

## Slide 23: Initial Concept Team Meeting
ICTM is usually needed for complex projects and projects where the PJS needs to be validated.
PDP Section 5.7
Initial Data Gathering
ICTM (if warranted)
Layout
(draft) CR
Notes: (click 1) ICTM is usually needed for complex projects and projects where the PJS needs to be validated.
(click 2) If the ICTM is warranted, it is held prior to moving into the concept report preparation.

## Slide 24: Initial Concept Team Meeting
Purpose is to:
  better understanding of the project scope,
  identification of information, and
  next steps
Notes: Purpose is to:
(click 1) provide a better understanding of the project scope,
(click 2) identification of information that is available and what is needed, and
(click 3) the next steps to be accomplished in the concept development.

## Slide 25: Concept Team Meeting
The CTM is held prior to submitting the Concept Report for approval.
The Concept Report may be updated based on the outcome of the discussions from the CTM.
(draft) CR
CTM
(final) CR
PM Submit CR (to DPS)
PM Submit CR (to DPS)
Notes: (click 1)The CTM is held prior to submitting the Concept Report for approval.
(click 2) The Concept Report may be updated based on the outcome of the discussions from the CTM.
(click 3) PM submit concept report to the Office of Design Policy and Support is a milestone metric for the PM.

## Slide 26: Concept Team Meeting
The purpose of the CTM is to:
Present Concept Report & Alternatives
Facilitate Discussions
Notes: The purpose of the CTM is to
(click 1) present the concept report & alternatives and
(click 2) to facilitate discussions with the attendees for information or issues that may not have been considered and addressed in the concept report.

## Slide 27
Overview of Concept Design Process
(5 basic design steps)
Concept Layout
Draft CR
CTM
Final CR
Approved CR
Notes: After the CTM has been held, the designer updates the concept report.

## Slide 28: (Final) Concept Report
CR
(final version)
PM reviews and signs
OPD reviews and signs
PM submits CR to DPS
PM submits CR to DP&S
Notes: (click 1) After the CTM is held, the CR is updated and finalized and submitted to the PM for review and signature. Then it is submitted to OPD for review and signature. Once the CR has been signed by the PM and OPD, the PM submits the CR to Office of Design Policy & Support for review. Reminder that submitting the CR to DP&S is a milestone for the PM.

## Slide 29
Overview of Concept Design Process
(5 basic design steps)
Concept Layout
Draft CR
CTM
Final CR
Approved CR
REVIEWED
DP&S
Chief Engineer
Notes: After being reviewed by the Office of Design Policy & Support, the concept report is routed to the Chief Engineer for approval the report.

## Slide 30: Concept Report Approval
The Office of Design Policies & Support coordinates with GDOT SME and reviews the report.
Once the CR is approved by the Chief Engineer, the scope of the project must be followed.
Any deviation from the scope may require additional approval.
Notes: (click 1) The Office of Design Policies & Support coordinates with GDOT SME and reviews the report.
(click 2) Once the CR is approved by the Chief Engineer, the scope of the project must be followed.
(click 3) Any deviation from the scope may require additional approval.

## Slide 31: Concept Phase Review
What is the order of the 5 basic design steps of the Concept Phase?
Draft CR, Layout, CTM, Final CR, Approved CR
Layout, CTM, Draft CR, Final CR, Approved CR
Layout, Draft CR, CTM, Final CR, Approved CR
Layout, Draft CR, Final CR, CTM, Approved CR
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: C

## Slide 32: Concept Phase Review
  The concept report is important because it sets the scope of the project’s work.
True
False
or
PM must know the project’s scope to ensure that the design is aligning with it as the PDP process continues.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: True - PM must know the project’s scope to ensure that the design is aligning with it as the PDP process continues.

## Slide 33
Which office reviews the Concept Report?
  A. Engineering Services
  B. Materials and Testing
  C. Design Policy & Support
  D. Roadway Design
Concept Phase Review
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: C

## Slide 34: Project Charter
Some projects have a project charter instead of a concept report.
No Concept Phase = No Concept Report
Do NOT Follow Concept Phase Steps
Notes: (click 1) Some projects do not have a concept phase. Consequently, there isn’t a concept report prepared.
(click 2) Some projects have a project charter instead of a concept report. These projects do not follow the design steps of the concept phase.

## Slide 35: Project Charter
Approved by the office that owns the project.
Notes: (click 1) a project charter is approved the office that owns the project.

## Slide 36
Plan Development Process
Concept Phase
Preliminary Design
Final Design
Construction
PTIP
Notes: As previously discussed, the concept phase is a high-level of engineering. The detailed engineering will begin in the preliminary design phase. There are a few non-design activities that may take place concurrently with the concept phase and will help the project to begin the preliminary design phase quickly after the concept phase is completed. (go to next slide)

## Slide 37
Plan Development Process: Environmental
Resource ID
ESB
ENV field work
(draft) resource survey reports
(final) resource survey reports
Approval
Note: Concept & ENV activities usually run concurrently. Check P6.
Concept Phase
Layout
(draft) CR
(final) CR
submit to DPS
Approval
CTM
Notes: (click 1) The orange bar represents the order of the main steps for the concept report. This is not scaled to represent the duration between activities.
(click 2) While the steps of the concept report are progressing, most projects will also begin the environmental studies. The first step of the environmental process is resource identification. The green bar represents the main steps for resource ID. This is not scaled to represent the duration between activities.
(click 3) The concept steps and the resource ID steps usually occur concurrently. However, there are schedules where this does not apply. The PM should check the project’s schedule to understand the timing of the activities for both.

## Slide 38: Environmental: Resource ID
The purpose of resource identification is to:
Determine the ENV resources
Determine the boundary of each resource
Notes: The purpose of the environmental resource identification is to
(click 1) determine what environmental resources are potentially within the limits of the projects.
(click 2) and to determine the boundary of each resource that is found. In the next PDP phase, this information will guide the designer on where or how to design the project.

## Slide 39: Environmental: Resource ID
Three different ENV SMEs must go the field and write a report:
Ecology
History
Archaeology
Notes: During the resource ID step, there are 3 different environmental subject matter experts that must physically go to the project site and evaluate whether there are any eligible resources. After the field work is complete, each SME must write a survey report about what resources were identified.
(click 1) This work is done for ecology, history, and archaeology. This information will be needed for when the project moves into the next PDP phase for preliminary design.

## Slide 40
Plan Development Process: Survey Database
Survey Database
Survey Layout
Survey field work
Submit Survey database
1st fold acceptance
Note: Concept & database activities usually run concurrently. Check P6.
Concept Phase
Layout
(draft) CR
(final) CR
submit to DPS
Approval
CTM
Notes: (click 1) The orange bar represents the order of the main steps for the concept report. This is not scaled to represent the duration between activities.
(click 2) While the steps of the concept report are progressing, most projects will also begin the survey database work. The blue bar represents this process. The first step of the survey database process is field work. This is not scaled to represent the duration between activities.
(click 3) The concept steps and the survey database steps usually occur concurrently. However, there are schedules where this does not apply. The PM should check the project’s schedule to understand the timing of the activities for both.

## Slide 41: Survey Database
The purpose of survey database is to:
Map the topography (elevation)
Locate
property
lines
Determine
ROW limits
Locate structures
Notes: The purpose of the survey database is to collect information related to
(click 1) topography or elevation. This information is needed for a designer to know if the land is low and needs fill add to raise it up or if it is too high and needs to be cut down to a lower elevation.
(click 2) the exact location of the adjacent property lines is needed to determine if the project will need to acquire additional land.
(click 3) It is important to know the exact location of structures that are on a property within the study area. This information will aid the designer in determining if the structure should be avoided or how it will be impacted by the project.
(click 4) Surveying allows GDOT to confirm the boundaries (aka right-of-way limits) that is owned by the state. The field work (aka survey work) collects all of this information.

## Slide 42
Plan Development Process: Survey Database
Survey Database
Survey Layout
Survey field work
Submit Survey database
1st fold acceptance
Prelim.
Dsgn
Concept Phase
Notes: The collected information is put into a database and then provided to GDOT for review. Once GDOT has reviewed and accepted the 1st of 2 checks of the database, the design work proceeds. Survey database is usually required before the detailed design work can begin. Hence, starting the survey database work on schedule will help to ensure that preliminary design starts on time.

## Slide 43
Information to Fill Out Templates:
PSR & P6 Schedule
Notes: Next, we are going to practice using a preconstruction status report and the Primavera P6 schedule to find information that is needed to fill out templates for the concept phase. [Directions: Be sure that all participants have copies of slides 35-38 & 40-41 without the answers. This will be active engagement with the participants to learn how to use these resources.]

## Slide 44
What design phase is this project in?
Notes: Look at the PSR for PI 0017959, Mitchell Co. What Phase is it in?
[Direction: Participant should have a copy of this PSR. Next slide provides choices for the answer.]

## Slide 45
Look at PI 0017959 Mitchell Co. What design phase is the project in?
  A. Concept
  B. Preliminary Design
  C. Final Design
PSR Review: Example #1
Notes: (direction: Read question 1 and give participants time to respond. Answer: A – Go to next slide to review how to know this. )

## Slide 46
How did you know that it is in the concept phase?
Notes: How did you know it was concept?
(direction: ask participants to raise hand and share the answers)
(Answer: click 1) Look at the PM notes. This project states that concept is in development.
(Answer: click 2) Look at the P6 schedule. The first 2 lines are about the concept report. Neither activity is at 100% which would indicate that the concept phase is complete.

## Slide 47
Objective:
Determine the date the CTM is to be Held
Determine the date the CTM invite is to be prepared
Understand how to fill out the CTM invite
Template Example #1: CTM Invite
Notes: A skill possessed by excellent project managers is knowing what templates are needed and when on the project the template should be completed. We are going to start with the template for the concept team meeting. Through this template, the PM will
(click 1) determine the date the CTM is to be held.
(click 2) determine the date the CTM invite is to be prepared.
(click 3) understand how to properly fill out the CTM invite.

## Slide 48
3 Weeks BEFORE the CTM Date
Notes: This is an excerpt from the CTM invite template letter.
(click 1) The letter provides direction that the CTM letter must be sent out at least 3 weeks in advance.
(click 2) This direction influences when the project can be scheduled.

## Slide 49
When will the CTM be held?
Cannot tell from PSR – not a listed P6 activity
Notes: If you are filling out a CTM letter, according to the PSR for this project when should the concept team meeting be held?
(Direction: Give participants time to look at the P6 schedule from the PSR for PI 0017959. This is just the PSR enlarged. Ask the participants for an answer.)
(click 1) This PSR has activities listed that are important to GDOT executive management. CTM is not an activity that management is monitoring. Therefore, the PM cannot find this information on the PSR. Instead, the PM must look at the full P6 schedule to find the answer.

## Slide 50
*excerpt of P6 for PI 0017959
When will the CTM be held?
March 10, 2023
Notes: [Direction: Have the participants review this pdf excerpt of the schedule.]
When will the CTM be held?
(Answer: click 1 & 2) Look at full P6 schedule. Hint: Meetings are always the same BL start and finish date. Task activity #02600 Concept Meeting is when the CTM should be held. This is 3/10/23.

## Slide 51
*excerpt of P6 for PI 0017959
When does the CTM invite need to be sent out?
HINT #1: It is not listed on the P6 schedule
HINT #2: Template provided directions on the timing of the invite.
Notes: When does the CTM invite need to be sent out?
[Direction: Pause for a few seconds and let participants look for answer.]
(click 1) Hint #1: It is not listed on the P6 schedule.
(click 2) Hint #2: PM must look at the template for the direction on the timing of the CTM invite.
[Answer is provided on next slide.]

## Slide 52
*excerpt of P6 for PI 0017959
CTM = BL 3/10/23
What date does the CTM invite need to be sent to participants?
3 weeks before = 2/17/23
BEGIN with the END in MIND
Notes: When working on a task or moving towards the next milestone, the PM should always “Being with the End in Mind.”
(click 1) The PM should know when the CTM should be held which is an activity on the P6 schedule.
(click 2) For this project, it has a baseline date of 3/10/23.
What date does the CTM invite need to be sent by? Per the template, it must be sent a minimum of 3 weeks before the CTM meeting is held.
(click 3) Do the math by beginning with the end in mind. CTM is the end and work backwards 3 weeks. The CTM invite is due no later than 2/17/23.

## Slide 53
*excerpt of P6 for PI 0017959
CTM = BL 3/10/23
When should the PM start the preparation of the CTM letter?
CTM invite must be sent by = 2/17/23
Factor time for PM’s efforts, QAQC process, & signature (min. approx. 1-2 weeks before invite due date)=
2/3/23 - 2/10/23
BEGIN with the END in MIND
Notes: When should the PM start the preparation of the CTM letter? As a PM you should be proactive. A letter cannot be prepared, reviewed, and signed on the same day. Therefore, if the day an activity is due has been determined, the PM should factor in time for the steps to meet a specific date. A best practice is to prepare letters and other templates 1-2 weeks prior to when they are due.
(click 1) For this CTM letter, a best practice would be to have the letter prepared and ready for review and signature between 2/3/24-2/10/23. This proactive planning will help to ensure that the schedule remains on baseline.

## Slide 54
Fill out anything that is highlighted in gray. Remove the highlight when done.
Yellow highlight are
directions for the preparer and should be removed along with the red text.
Don’t forget to update this to be relevant to the project
PM must provide this after coordinating with designer to determine a date and time.
Title on PSR
Use the date that you anticipate the letter will be submitted into the OPD tracker.
How to Fill Out a Template Letter
Notes: This is the template for the CTM invite letter. However, the guidance that will be discussed should be applied to all templates.
(click 1) Any items highlighted in gray is information that is needed. The gray highlight should be removed after the information is provided.
(click 2) The yellow highlighted text is directions for the preparer and should be removed along with the red text.
(click 3 & 4) Templates ask for a project description. This is referencing the title of the project as listed on the PSR. It is not written description such as the one for the expanded description in TPro.
(click 5 & 6) This is the date that you are submitting it into the OPD tracker. This date is to be written out as the name of the month, day, and year.
(click 7 & 8) This information is provided by the PM after coordinating with the designer to determine a date and time. Remember, the PM should have reviewed the P6 schedule to ensure that the CTM date will be held on or before the baseline date for the meeting.
(click 9 & 10) Read the entire template, there may be sections that need to be updated and made relevant to the project.

## Slide 55
Initials are always
Office Head: Asst. Office Head: District Program Manager: Project Manager
Do not remove – part of template
Calculated based on the CTM date
Don’t forget to fill out the header
Notes: This is the continuation of the CTM letter.
(click 1) This is directing the preparer that they must provide a date which will be based on the date for CTM as set by the PM.
(click 2) This is the initials of all who have created, reviewed, and signed the letter. The initials are always in this order.
(click 3) Do not remove the footer from the templates. This is how management knows that the correct version of the template is being used.
(click 4) If there is more than one page of a letter, there will be a header. Do not forget to fill it out.

## Slide 56
Look at PI 0017963 Colquitt Co. What design phase is the project in?
  A. Concept
  B. Preliminary Design
  C. Final Design
PSR Review: Example #2
Notes: (direction: Read question 1 and give participants time to respond. Answer: A – Go to next slide to review how to know this. )

## Slide 57
What design phase is this project in?
CONCEPT
Notes: (direction: ask participants to raise hand and share the answers)
How did you know it was concept?
(Answer: click 1) Look at the PM notes. This project states that concept is in development.
(Answer: click 2) Look at the P6 schedule. The first 2 lines are about the concept report. Neither activity is at 100% which would indicate that the concept phase is complete.

## Slide 58: Where to Find OPD Templates
ROADS
  www.dot.ga.gov/GDOT/pages/DesignResources.aspx
Reference Tool: OPD Index Library (located on CD_Common/Administration/OPD Library

## Slide 59
Objective:
Determine with type of property access letter is needed.
Determine the date the property access letters are needed.
Determine the date the property access letter is to be prepared.
Template Example #2:
Property Access Letter
Notes: Using the skills that were learned for the concept team meeting letter, we will now apply them to property access letters.
(click 1) Through the property access letter example, the PM will be able to determine what type of property access letter is needed for each project.
(click 2) The PM will be able to identify the date the letters are needed.
(click 3) The PM will be able to plan and determine when the letter needs to be prepared.

## Slide 60
Property access letters are required on any project where field work will be conducted outside of the existing ROW.
Resource ID and survey database both may involve field work outside of existing ROW.
When does a project need property acces letters?
Notes: Before you can determine when a template is needed, you must understand what the template is for on the project.
(Click 1) Property access letters are required on any project where the field work will be outside of the existing ROW.
(Click 2) Resource ID (env) and survey database are activities may involve field outside of the existing ROW. If the field work for either activity is outside of the existing GDOT ROW, then a property access letter is required for that activity.

## Slide 61
Does this project need property access letters for environmental field work, survey database, or both?
Hint: Look at P6 to see if these activities are needed.
Notes: Would you need to send out a property access letter for environmental field work, survey database, or both?
[Direction: Give participants a few seconds before displaying the hint.]
(click #1) Hint: Look at the P6 schedule to see if these activities are needed.
[Next slide provides the answer.]

## Slide 62
Does this project need property access letters for environmental field work, survey database, or both?
The P6 is showing that both Env Resource ID & survey database are part of the project.
Notes: (click 1) The P6 excerpt on the PSR lets the reader know that there is survey database (aka database) and environmental resource ID activities in the schedule.
(click 2) Since there are P6 activities for both, then both letters are needed for this project. If only one of the activities was listed, then only that activity would need the letter.

## Slide 63
What is the P6 start date for the environmental resource ID? For the survey database?
Survey Database= BL start 4/5/23
Resource ID = BL start 8/17/22
Notes: According to the P6 schedule when should the environmental resource ID begin? When should the survey database work begin?
[Directions: Give participants time to look at the schedule and try to find the answer.]
(click 1) Always look for the baseline start date to know when an activity will begin.
(click 2) Resource ID has a baseline start date of 8/17/22.
(click 3) Survey database has a baseline start date of 4/5/23.

## Slide 64
Resource ID =
BL start 8/17/22
When should the environmental property access letter be prepared by the PM?
BEGIN with the END in MIND
PM prepare letter = 7/27/22
Best Practice: Mail out letters 1 week before field work starts.
Factor time for QAQC, signature, & mail to property owner (min. approx. 3 weeks before BL start due date)
Notes: Using the knowledge that you learned from the CTM invite letter, when should the environmental property access letters be prepared by the PM?
[Directions: Give participants a minute to figure out a date.]
(click 1) Always begin with the end in mind.
(click 2) The baseline start date is 8/17/22.
(click 3) The letters must be signed and mailed to property owners on or before this date. It is best practice to mail them at least 1 week in advance. This will allow time for the post office to deliver the letters. Property access letters should be received by property owners prior to field staff accessing private land.
(click 4) The PM should be proactive in planning the time need to prepare the letter, get it QAQC reviewed, and signed.
(click 5) The PM should start preparing the letter around 7/27/22.

## Slide 65
Database =
BL start 4/5/23
When should the survey database access letter be ready for signature?
BEGIN with the END in MIND
PM prepare letter = 3/15/23
Best Practice: Mail out letters 1 week before field work starts.
Factor time for QAQC, signature, & mail to property owner (min. approx. 3 weeks before BL start due date)
Notes: When should the survey property access letters be prepared by the PM?
[Directions: Give participants a minute to figure out a date.]
(click 1) Always begin with the end in mind.
(click 2) The baseline start date is 4/5/23.
(click 3) The letters must be signed and mailed to property owners on or before this date. It is best practice to mail them at least 1 week in advance.. Property access letters should be received by property owners prior to field staff accessing private land.
(click 4) The PM should be proactive in planning the time need to prepare the letter, get it QAQC reviewed, and signed.
(click 5) The PM should start preparing the letter around 3/15/23. However, if it is decided to begin the survey work with the resource ID work, then both letters would need to start being prepared around 7/27/22.

## Slide 66
WHERE TO FIND:
PROPERTY ACCESS TEMPLATE LETTER
This template is owned by DP&S
(not OPD)
Notes: For the property access template letter, go to the same page as the OPD template on ROADS.
(click 1) However, the template is not created or owned by OPD. It is a template from the Office of Design Policy & Support. Therefore, you must look in the DP&S folder to find the template.

## Slide 67
PROPERTY ACCESS LETTER
Property Access Standard Letter
Use This Link
Note: The template is an Adobe form. It cannot be used if opened in Revu Bluebeam.
Notes: Directions: Click on “Property Access Standard Letter” It will link the user to the page where this is located. Then open the form in Adobe. It cannot be used if it is opened in Bluebeam.

## Slide 68
Determine the purpose of the access
Select from this column if the work is being done by a consultant
Select from this column if work is being done in-house
Notes: When you open the template in Adobe, you will have options to select to auto-populate information in the letter. Before you can select, you need know what the property access is for and who needs the access.
(click 1) Determine the purpose of the access that the project needs. Why will someone be on the private property?
(click 2 & 3) Be sure to choose from the correct column. The language is different depending on whether a consultant will be performing the field work or a GDOT staff member will be completing it. After you select the appropriate text for the letter, then go through the letter and fill out the blue boxes.

## Slide 69
Delete blue boxes. These are just directions
Delete green box unless mailing to a single property owner
Yellow box: If sending to multiple property owners, remove gray highlight. If sending to single property owner, use their name.
Update pink box based on template form information.
Fill in info for any remaining gray highlighted items
Notes: (click 1) Delete when done following the instructions.
(click 2) Delete unless letter is only going to one property owner.
(click 3) Address letter to the general term of “property owner”. The exception is if the letter is going to a single property owner. In that case, include the property owner’s name.
(click 4) Update these text boxes based on the missing information which is in gray highlight.
(click 5) Fill in the information for any remaining gray highlighted items.

## Slide 70: Templates Used During the Concept Phase
The following is a list of potential templates that may be needed for a project:
Initial Pavement Evaluation Summary (IPES) Request or Review
Initial Pavement Design Request or Review
Intersection Control Evaluation (ICE)
Concept Report
ICTM/CTM Letter
Concept Report Submission Letter
Cost Estimate
Property Access Letter (Survey Database and/or Environmental)
Traffic Data and Projection Request or Review
Interchange Modification Report (IMR) or Interchange Justification Report (IJR)
REMEDY Resource ID Request
Notes: These are some of the common templates that are needed during the concept phase. Each project must be evaluated to determine which templates are applicable. This list is not all inclusive and should be used as a guide only.

## Slide 71: Filling Out Templates
Be Proactive!
Review P6 and the PDP manual/workflow
Plan ahead
Have the template ready for review in advance
Notes: Be Proactive!
(click 1) Look at the schedule & know the which PDP steps will apply.
(click 2) Plan ahead. If you know what PDP steps are needed and when, then create a plan for the project to allow yourself time to get the templates done.
(click 3) Have the templates ready for review in advance of the submission date. Don’t forget that there may be several team members that must review the document prior to it being submitted to another office. Quality assurance and quality control is going to require time to complete.

## Slide 72: Filling Out Templates
NEVER change any wording on the template without the District Program Manager’s permission
If reviewing a letter, always cross reference the original template.
Always refer to the latest template when creating a letter. NEVER use a saved copy from another project.
Notes: (click 1) NEVER change any wording on the template without the District Program Manager’s permission. There are instances when editing the language is applicable to the project. However, it should not be changed without letting management know that this has been done intentionally.
(click 2) To ensure that the current template is being used, open the document to be QAQC’s and compare it to the template. Never accept a document that is using an old template.
(click 3) As part of the QAQC process, open the current template from its original location. Do not open a version of the template that you have saved to your C drive or another project. Templates are updated periodically. It is important that the current version is being used.

## Slide 73
Where does the PM locate templates?
  ROADS
  Computer Desktop
  Thumb drive
  Dark Web
Learning Objective Review
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: A

## Slide 74
Which two resources may be helpful to complete a template?
  P6 & PSU
  PSR & PFR
  GeoPi & ROADS
  P6 & PSR
Learning Objective Review
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D