## Slide 1
Notes: This training is part 3 of a 5-part series related to the PDP process. The purpose of this training series is to provide a foundation level of understanding of the PDP process. It will cover every process or study that a project may require per the PDP process. For additional information, the PDP manual should be referenced. In PDP Overview #3, the training will cover the PDP process between concept report approval and PFPR request.
Materials: Each learner should have copies of slides 67 & 69 without the answers.
Training Time: 1.5 hours

## Slide 2: Learning Objectives
Preliminary Design Phase & Why it is Important
Critical Path Activities for PFPR Request
How to Reference a PSR and/or P6 Activities
Common Templates for the Preliminary Design
Notes: (click 1) Be able to explain what is a preliminary design phase and why it is important
(click 2) Be able to identify the critical path activities to request PFPR on time
(click 3) Be able to reference a PSR and/or P6 activities for information for the templates
(click 4) Be able to locate the templates that a PM will need during the preliminary design phase

## Slide 3
Plan Development Process
Concept Phase
Preliminary Design
Final Design
Construction
PTIP
Notes: (click 1) Before we can move into discussing preliminary design, we need to recap what was learned about the PDP process for the concept phase.

## Slide 4: Concept Phase Recap Review
Which statement is true about the concept phase?
It determines the alternative based on what GDOT tells the designer to do.
It identifies the preferred alternative based on the PJS.
It determines the scope without considering other factors such as cost and environmental resources.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: B - It identifies the preferred alternative based on the Project Justification Statement. Remember that the PJS is the reason “why” the project is needed.

## Slide 5: Concept Phase Recap Review
Why is the concept phase important?
It sets the scope of the project.
It determines the schedule of the project.
It provides the name of the project.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: A - It sets the scope of the project and determines what needs to be designed.

## Slide 6: Concept Phase Recap Review
What is a survey database?
It is the data collected that tells the designer where to build the project.
It is the data collected that tells the designer the existing topographic information.
It is the data collected that tells the designer how to build the project.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: B - It is the data that is collected on the project site that provides the existing elevations and structure locations.

## Slide 7: Concept Phase Recap Review
What is not true about the survey database?
It is needed before preliminary design can start.
It influences how the project must be designed.
It is collected at the project site and then compiled into a database.
It is needed before the concept report can start.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D - D is not the correct answer because survey database work can be done concurrently with the concept report process.

## Slide 8
Plan Development Process
Preliminary Design
Concept
Final Design
Construction
PTIP
Notes: This training is going to focus on the Preliminary Design Phase of the PDP process. It is the first phase that involves detailed engineering.

## Slide 9: Preliminary Design Phase
Federal $ Must
Follow
PDP
P
D
P
MOST = ALL
Preliminary Phase Starts After Concept Phase
PDP Chapter 6
Engineering Starts After Survey Database Work
Notes: (click 1) If any federal money will be used on the project, GDOT must follow the Plan Development Process (PDP) per the oversight agreement with Federal Highway Administration (FHWA).
(click 2) If the project has a concept phase or a project charter, the design phase starts after the concept report or charter is approved. There are some projects that do not require a concept report or charter. For those projects, preliminary design would be the first PDP phase of the project. All projects must go through a preliminary design phase. Think of writing a book. To be a good writer, you should first draft the book or at least outline it. This is the preliminary phase. Note: Most projects require a PFPR inspection; however, there are some types of projects with expedited schedules that will not require this. Regardless, the project will start with preliminary design before moving into final design.
(click 3) For most projects, the preliminary engineering work begins after the survey database field work is done. Survey database is the topographic survey work. We will discuss this more later. Read Chapter 6 of the PDP manual for information about the Preliminary Design Phase.

## Slide 10
Plan Development Process: Environmental & Design
Resource
ID
Approval
Note: Design & ENV activities usually run concurrently. Check P6.
Concept
Approval
Preliminary Design
Technical Studies
NEPA Doc
Approval
PFPR
Notes: After approval of the CR and concurrent with the environmental studies, the preparation of preliminary design and construction plans will begin.

## Slide 11: Preliminary Design Phase
Preliminary design will try to avoid or minimize impacts to
PDP Section 6
Environmental Resources
Utilities
Notes: (click 1) During the preliminary design phase, the design will take into consideration environmental resources and existing utilities and how to design to avoid or minimize impacts to these things. Refer to the PDP manual Section 6 for more detailed information.

## Slide 12
Concept Approval
ENV Studies
Geometry Design
Utilities
PFPR Request
Note: not in sequential order – many are done concurrently
Preliminary Design
(Basic Activities Required for PFPR Request)
(SUE or 1st Submission)
Notes: This slide is a simplified version of the Preliminary Design PDP flowchart. Geometry design, environmental studies, and utilities are all required to be completed prior to the PFPR request. Additional activities may be required depending on the type and scope of the project.

## Slide 13: Preliminary Design Phase
PFPR cannot be requested if:
1. Environmental technical studies (impacts) are not approved (or almost approved); or
2. Utility coordination (1st submission or verification) is not complete; or
3. Preliminary Plans are not complete
PDP Section 6
Notes: (bullet 1) PFPR cannot be requested if
(bullet 2) Environmental technical studies are not approved. Tech studies identifies the impacts to environmental resources. The reports have to be approved (or with OES’s permission they are almost approved) prior to the PFPR request.
(bullet 3) Utility coordination for 1st submission or verification is complete.
(bullet 4) Preliminary plans are complete. The purpose of the PFPR meeting is to review the preliminary plans.

## Slide 14
Concept Approval
ENV Studies
Geometry Design
Utilities
PFPR Request
Note: not in sequential order – many are done concurrently
Preliminary Design
(Critical Path for PFPR Request)
(SUE or 1st Submission)
Notes: (click 1) Completion of the environmental studies completion is required to develop the preliminary plans. This information is critical path to requesting PFPR on time. The next few slides will discuss the environmental process in more detail.

## Slide 15
Resource ID Complete
Generally completed prior to CR approval
Hold A3M
Provide Plans to Start Technical Studies
Conduct Air & Noise Studies
Cultural Resources AOE
Ecology AOE
Agency Concurrence
Receive OES Permission to Request PFPR
Preliminary Design – Environmental Process
These are the technical studies.
Notes: This is a simplified flowchart for the environmental process up to PFPR request. For many projects, the resource identification is completed, and agency approved during the concept phase. The brown boxes are reminder notes for understanding the process.

## Slide 16
Resource ID Complete
Generally completed prior to CR approval
Hold A3M
Provide Plans to Start Technical Studies
Conduct Air & Noise Studies
Cultural Resources AOE
Ecology AOE
Agency Concurrence
Receive OES Permission to Request PFPR
Environmental Process: A3M
Notes: As a general rule, if resources are present, an A3M (avoidance & minimization measures meeting) will be held.

## Slide 17: Environmental Studies: A3M
The purpose of the A3M is for the designer and the Office of Environmental Services (OES) to coordinate very early in the design process.
This result of the coordination will either avoid impacts to environmental resources or minimize the impacts.
Notes: Bullet 1: The purpose of the A3M is for the designer and the Office of Environmental Services (OES) to coordinate very early in the design process.
Bullet 2: This result of the coordination will either avoid impacts to environmental resources or minimize the impacts.

## Slide 18: Environmental Studies: A3M
If resources are present and there are impacts or potential impacts, an A3M meeting is needed.
  No formal request letter is needed.
  A meeting invite is all that is required.
    Send invite 2 weeks before A3M is held
    Include Plans with ESAs shown
Notes: Bullet 1: If resources are present and there are impacts or potential impacts, an A3M meeting is needed.
Bullet 2: No formal request letter is needed.
Bullet 3: A meeting invite is all that is required.

## Slide 19
Resource ID Complete
Generally completed prior to CR approval
Hold A3M
Provide Plans to Start Technical Studies
Conduct Air & Noise Studies
Cultural Resources AOE
Ecology AOE
Agency Concurrence
Receive OES Permission to Request PFPR
Environmental Process: Technical Studies
Notes: After the A3M meeting, the designer will provide updated plans to write the Assessment of Effect (AOE) reports for archaeology, history, and ecology. The plans will also start the air and noise studies.
(click 1) The AOE reports are normally approved or close to agency approval before the Office of Environmental Services will grant permission to submit the PFPR request.

## Slide 20: Environmental Studies: Technical Studies
The technical studies are the reports that document the impacts to environmental resources.
Impact(s) Documented = Assessment of Effect (AOE) Report
Ecology
Cultural Resources (History & Archaeology)
Notes: (bullet 1) The technical studies are the reports that document the impacts to environmental resources
(bullet 2) The documents that report the impacts are called Assessment of Effect or AOE reports.
(bullet 3) The Ecology AOE report will document impacts to ecological resources such as wetlands, streams, and protected species.
(bullet 4) History & archaeology are cultural resources. If there are any impacts to either history or archaeology resources, it will be documented in a combined report known as the cultural resource AOE.

## Slide 21: Environmental Studies: Technical Studies
  Technical Studies also include:
Air Study
Noise Study
  Air & Noise do NOT have an AOE report.
Notes: (click 1) Technical studies also include air and noise studies. These are separate reports.
(click 2) Air & noise studies do not have an AOE report.

## Slide 22
Resource ID Complete
Generally completed prior to CR approval
Hold A3M
Provide Plans to Start Technical Studies
Conduct Air & Noise Studies
Cultural Resources AOE
Ecology AOE
Agency Concurrence
Receive OES Permission to Request PFPR
Environmental Process: Technical Studies
Technical Studies
OES Approval
Notes: (click 1) The Assessment of Effect (AOE) reports and air & noise reports are based on the plans that are developed as a result of the A3M meeting. Collectively these reports are known as the technical studies.
The AOE report(s) are to be approved by the corresponding agency prior to requesting PFPR. Air & Noise reports are approved by OES.

## Slide 23: Environmental Studies Review
  The purpose of the A3M meeting is to discuss potential design solutions to avoid or minimize impacts to environmental resources.
False
True
or
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: True

## Slide 24: Environmental Studies Review
After A3M is held, what environmental work happens?
A. Preliminary Design
B. Agency Approval
C. Survey Database
D. Technical Studies
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D

## Slide 25: Environmental Studies: Technical Studies
The technical studies reports should be submitted from the consultant to the OES reviewer directly.
  No letters or emails are needed.
Notes: Read slide

## Slide 26: Environmental Studies: Technical Studies
If a technical study (or studies) are to be completed in-house:
  PM should fill out the “Environmental Technical Studies (AOEs) Request” letter.
    Found under Program Delivery templates online.
  Also fill out “Request to Complete Technical Studies” form.
    Found on OES website in Resources box.
Notes: Read slide

## Slide 27
Concept Approval
ENV Studies
Geometry Design
Utilities
PFPR Request
Note: not in sequential order – many are done concurrently
Preliminary Design
(Critical Path for PFPR Request)
(SUE or 1st Submission)
Notes: (click 1) Besides ENV studies being critical path to requesting PFPR on time, Utility coordination is also critical path.

## Slide 28
Incorporated mark ups into design
Utility Companies Review/Mark Up Plans
1st Submission
SUE (if applicable)
1st Verification
Utility Plans
District Utility Office
Preliminary Design: Utilities Process
Only do 1 of these 2 processes
Notes: This slide represents the utility coordination steps to request PFPR on time.
(click 1) SUE stands for subsurface utility engineering. It is not required on all projects. It is for gathering information related to mostly utilities which are buried beneath the ground such as cables, water and sewer.
(click 2) If SUE is not required, the first step in utility coordination is called the 1st utilities submission. If SUE is required, then the first step in utility coordination is called the 1st utilities verification. It is verification because the designer has already collected some utility information from the SUE work. The Utility companies are being requested to verify that information.
(click 3) Each project will only do either 1st submission or 1st verification (not both).
(click 4) The utility plans are submitted by the PM to the District Utility Office (aka DUO).
(click 5) The DUO submits the plans to the utility companies and requests marks up for the existing utility locations.
(click 6) The utility companies provide their review mark ups and this information is sent to the designer to incorporate into the plans.

## Slide 29
Incorporated mark ups into design
PURP or UFM (if needed)
PFPR Request
Preliminary Design: Utilities Process (cont.)
*DUO will determine if PURP or UFM is required.
Notes: (click 1) Once the designer has incorporated the mark ups for existing utility locations into the preliminary plans, then a PURP or UFM meeting may be held. PURP stands for preliminary utility relocation plan. UFM stands for utility field meeting.
(click 2) After the PURP or UFM is held (or waived), the plans are updated, and the utility coordination is complete.
(click 3) Therefore, allowing the design to proceed to PFPR.
(click 4) The DUO will let the PM know which meeting is needed, if applicable.

## Slide 30: Utilities: 1st Submission Importance
  The design of the project must know the exact location of all utilities.
  Then the design can determine if any of the utilities need to be relocated.
Notes:   (Bullet 1) The design of the project must know the exact location of all utilities. (Bullet 2) Then the design can determine if any of the utilities need to be relocated.

## Slide 31: Utilities: 1st Submission vs 1st Verification
1st Submission
1st Verification
Plans do not have SUE info
DUO submits plans to UTL companies
Companies confirm existing UTL location
Approved SUE plans
DUO submits plans to UTL companies
Companies verify UTL location
Notes: (Bullet 1) read slide
(Bullet 2) read slide
(bullet 3) read slide
1st Verification of the Utility Plans replaces 1st Submission

## Slide 32: Utilities Coordination Review
  The purpose of 1st submission is to coordinate with the utility companies and verify the utility relocations.
False
True
or
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: False - It is to coordinate with the utility companies and verify the existing utility locations.

## Slide 33: Utilities
  PM is to fill out the “Utilities Request 1st Submission” Letter.
    Letter is located online under ROADS in the Program Delivery folder.
    Letter is used for both 1st submission and 1st verification.

## Slide 34
Concept Approval
ENV Studies
Geometry Design
Utilities
PFPR Request
Note: not in sequential order – many are done concurrently
Preliminary Design
(SUE or 1st Submission)
Notes: As we have discussed, environmental technical studies and utility 1st submission or verification coordination are critical path activities to request PFPR on schedule.
(click 1) Now, we will discuss some of the common studies or design processes that affect the geometric design of the preliminary plans. These are not necessarily critical path but may be required to be assessed or approved prior to have the preliminary plans ready for the PFPR request.

## Slide 35: Preliminary Design Phase
Geometry Design is influenced by:
1. Environmental technical studies;
2. Utility coordination (1st submission or verification) is not complete; and
3. Other design elements
PDP Section 6
Notes: (bullet 1) Geometry Design is influenced by:
(bullet 2) 1. Environmental technical studies;
(bullet 3) 2. Utility coordination (1st submission or verification) is not complete; and
(bullet 4) . Other design elements. Refer to Section 6 of the PDP manual for more information.

## Slide 36
Concept Approval
Traffic Studies
ENV Studies
Lighting Design
Drainage
Design
Geometry Design
Erosion Control Plan
Utilities
PFPR Request
Note: not in sequential order – many are done concurrently
Phase I ESA (Phase II ESA)
Preliminary Design
(SUE or 1st Submission)
Notes: (click 1) Many of GDOT’s projects involve traffic studies.

## Slide 37: Traffic Studies
Collected and approved traffic data is valid for 5 years.
Traffic projections are based on an Open Year and a Design Year
  Open Year (OY) = when it will be open for traffic to use
  Design Year (DY) = Open Year + 20 years
  Example: Let date March 2023; OY 2025/DY 2045
Notes: (click 1) Traffic data is only valid for 5 years. Traffic cannot expire before the project goes to Let.
(click 2) Traffic projections are based on an Open Year and a Design Year.
(click 3) Open Year is when a project has completed construction and is now available for use. A general rule for our projects is that it will be open within 2 years after the Let date.
(click 4) Design Year is the projected traffic in 20 years after it is open for use. This is due to the average life of a project being valid for 15-20 years after construction is complete.
(click 5) Any time that the traffic must be update, the projections must also be updated.

## Slide 38: Traffic Studies
If traffic data must but updated, then traffic projections will be updated.
If traffic data is valid but the let date move, updated traffic projections may be required.
Notes: (click 1) If traffic data must but updated, then traffic projections will be updated.
(click 2) If traffic data is valid but the let date move, updated traffic projections may be required. If the schedule changes and this causes the Open Year to change, then just the traffic projections must be update provided that the traffic counts are still valid. Most of our projections have a +2-year built into the projections. Therefore, if the Open Year was 2024, the projections are valid until 2026. As long as the let date is by 2026, the projections would still be valid even if the let date shifted.

## Slide 39: Traffic Studies Request
If new or updated traffic data or projections are required, the PM must fill out the traffic request package.
To make the request:
  Fill out the “Request Traffic Projections and Diagram” letter on ROADS. (OPD folder)
  Fill out the “Traffic Projections Request Form” on ROADS.
    Located online under Manuals & Guides/Planning/Category: Design Traffic Forecasting
  Submit the request or approval request through the OPD Document Tracker.
    Include an email response from the District Traffic Engineer or Area Engineer about known development in the area.
Notes: Read slide

## Slide 40: Traffic Studies Request (cont.)
If new or updated traffic data or projections are required, the PM must fill out the traffic request package.
  PM must submit the traffic request to either the office of Planning or the Office of Traffic Operations.
  The correct office is the one that planned the project.
  If the Office of Bridge programmed the project, then submit it to the Office of Planning.
Notes: Read slide

## Slide 41
Preliminary Design
Concept Approval
Traffic Studies
ENV Studies
Lighting Design
Drainage
Design
Geometry Design
Erosion Control Plan
Utilities
PFPR Request
Note: not in sequential order – many are done concurrently
Phase I ESA (Phase II ESA)
(SUE or 1st Submission)
Notes: (click 1) Another study that is conducted either during the concept phase but no later than prior to PFPR is the Phase I ESA. ESA stands for Environmental Site Assessment. This is for hazardous waste and is not an OES activity.

## Slide 42: Phase I ESA
The Phase I ESA (environmental site assessment) identifies the site(s) that need further investigation.
It is a site visit and database search of land that is proposed to be acquired and land adjacent to the project for potential soil contamination from hazardous waste material and underground storage tanks (USTs).
Notes: (click 1) The Phase I ESA (environmental site assessment) identifies the site(s) that need further investigation.
(click 2) It is a site visit and database search of land that is proposed to be acquired and land adjacent to the project for potential soil contamination from hazardous waste material and underground storage tanks (USTs).

## Slide 43: Phase II ESA
The Phase II ESA is physical soil testing of land that is known or suspected of having contaminated soil.
If a Phase II ESA is required, it must be completed prior to authorizing ROW because that is the start of purchasing land for the GDOT project.
Notes: (click 1) The Phase II ESA is physical soil testing of land that is known or suspected of having contaminated soil.
(click 2) If a Phase II ESA is required, it must be completed prior to authorizing ROW because that is the start of purchasing land for the GDOT project.

## Slide 44: Phase I ESA
If GDOT is preparing the Phase I Environmental Site Assessment (ESA) report, the “UST Phase I Request Letter” is required.
  This will be submitted to the District Planning & Programming Engineer (DPPE).
If the consultant has prepared the Phase I ESA, the “UST Phase I Approval Request” is required.
  This will be submitted to OMAT.
  Include the OMAT checklist too.
    ROADS/Design Related Resources/Additional Resources/GEOTECH Consultant Submittal Checklist
Notes: (click 1) If GDOT is preparing the Phase I Environmental Site Assessment (ESA) report, the “UST Phase I Request Letter” is required. This will be submitted to the DPPE.
(click 2) If the consultant has prepared the Phase I ESA, the “UST Phase I Approval Request” is required. This will be submitted to OMAT. Both letters are located online under Program Delivery.
(click 3) In addition to the letter, the PM must submit the OMAT checklist. The checklist is located on ROADS.

## Slide 45
Preliminary Design
Concept Approval
Traffic Studies
ENV Studies
Lighting Design
Drainage
Design
Geometry Design
Erosion Control Plan
Utilities
PFPR Request
Note: not in sequential order – many are done concurrently
Phase I ESA (Phase II ESA)
(SUE or 1st Submission)
Notes: (click 1) There are many other studies or design related approvals that may be required for a project. We will discuss a few of them including design variances or design exceptions, various pavement design related analysis, and soil survey. Not all will apply to any project. Each project is unique and must be evaluated for the appropriate design review requirements. PM should be aware of the common types of analysis and then can coordinate/discuss them with the designer or other SME during the monthly status meetings.

## Slide 46: Design Variance or Exception
Design Exception (DE) = a design feature does not meet controlling criteria
  Approved by the Chief Engineer
  Exception: For PoDI projects, FHWA is the agency which grants design exceptions.
Notes: (bullet 1) A design exception is a design feature that does not meet the controlling criteria in the current edition of the AASHTO Green Book and the AASHTO publication A Policy on Design Standards – Interstate System, then a DE is required from the Chief Engineer.
(bullet 2) PoDI stands for Project of Division Interest. When a PM receives a project, they will be notified if it is a PoDI project. The majority of GDOT projects are not.

## Slide 47: Design Variance or Exception
Design Variance (DV) = design feature that is not a controlling criteria and does not meet GDOT standard criteria
  Requested from the Chief Engineer
Notes: (bullet 1) If a design feature that is not a controlling criteria and does not meet GDOT standard criteria, the a DV shall be requested from the Chief Engineer.

## Slide 48: Design Variance or Exception
DV or DE should be submitted as soon as possible
(may be able to do this during concept phase)
Notes: (click 1) DV or DE should be submitted as soon as possible (may be able to do this during concept phase)

## Slide 49: Design Variance or Exception
If a design variance (DV) or design exception (DE) is required, PM will fill out the “Design Exception or Variance” letter.
  Letter located online under Program Delivery.
The form that the designer should fill out is located in Appendix D of the PDP Manual.
Notes: (click 1) If a design variance (DV) or design exception (DE) is required, PM will fill out the “Design Exception or Variance” letter. The letter is located online under Program Delivery.
(click 2) The form that the designer should fill out is located in Appendix D of the PDP Manual.

## Slide 50: Pavement - PES
Pavement Evaluation Summary (PES) may be needed if a project proposes to retain and overlay existing pavement.
  For non-linear projects (intersection improvements, passing lanes, roundabouts, bike/ped, etc.) request is usually needed if continuous inlay/overlay exceeds 0.5 miles.
  For a linear project, a PES report should be requested for a length of continuous inlay/overlay greater than 0.25 miles.
Notes: (click 1) Pavement Evaluation Summary (PES) may be needed if a project proposes to retain and overlay existing pavement.
(click 2) For non-linear projects (intersection improvements, passing lanes, roundabouts, bike/ped, etc.) request is usually needed if continuous inlay/overlay exceeds 0.5 miles.
(click 3) For a linear project, a PES report should be requested for a length of continuous inlay/overlay greater than 0.25 miles.

## Slide 51: Pavement - PES
Cover letter is not required.
“Pavement Design Package Submittal Checklist” is required and filled out by PM and designer.
  See Section 6.3.4 of PDP manual for link to checklist.
Notes: (click 1) Cover letter is not required.
(click 2)“Pavement Design Package Submittal Checklist” is required and filled out by PM and designer. See Section 6.3.4 of PDP manual for link to checklist.

## Slide 52: Pavement - PTS
Pavement Type Selection (PTS) may be needed if a project proposes to replace or install new pavement
“Pavement Design Package Submittal Checklist” is required and filled out by PM and designer.
  Cover letter is not required.
  See Section 6.3.4 of PDP manual for link to checklist.
Notes: (click 1) Pavement Type Selection (PTS) may be needed if a project proposes to replace or install new pavement. This is part of the pavement design package.
(click 2) “Pavement Design Package Submittal Checklist” is required and filled out by PM and designer. Cover letter is not required. See Section 6.3.4 of PDP manual for link to checklist.

## Slide 53: Soil Survey
It determine the geotechnical features of the soil including but not limited to:
  subgrade requirements
  moisture content
  areas of unsuitable soil
These are items that need to be understood for designing the project.
Notes: (click 1) Soil Survey tests the soil to determine the geotechnical features of the soil including but not limited to subgrade requirements, moisture content, areas of unsuitable soil, etc.
(click 2) These are items that need to be understood for designing the project.

## Slide 54: Soil Survey
The Soil Survey Report documents the results of the field testing.
It is approved by the Office of Materials and Testing (OMAT).
Notes: (click 1) The Soil Survey Report documents the results of the field testing.
(click 2) It is approved by the Office of Materials and Testing (OMAT).

## Slide 55: Soil Survey
See Section 6.3.2 of the PDP manual to determine if a Soil Survey Report is required.
It is required for major projects such as:
  widening projects,
  new alignments, and
  projects that have a significant change in grade (5ft raising or lowering of the existing profile grade line).
Notes: (click 1) See Section 6.3.2 of the PDP manual to determine if a Soil Survey Report is required.
(click 2) It is required for major projects such as widening projects, new alignments, and projects that have a significant change in grade (5ft raising or lowering of the existing profile grade line).

## Slide 56: Soil Survey
See Section 6.3.2 of the PDP manual to determine if a Soil Survey Report is required, check PDP to see if the project is located within a county that requires and approved report prior to PFPR.
  If a report is needed and it is not required prior to PFPR, it would be required prior to FFPR.
Notes: (click 1) If a Soil Survey Report is required, check PDP to see if the project is located within a county that requires and approved report prior to PFPR.
(click 2) If a report is needed and it is not required prior to PFPR, it would be required prior to FFPR.

## Slide 57: Soil Survey
If it is required:
  Fill out “Soil Survey Request (In-House)”
    If it is a consultant prepared report, use same letter but modify it.
  Include the OMAT checklist.
  Follow the PW workflow OMAT Geotechnical & Environmental Submittals
Add note in OPD tracker of any change to templates.
Notes: If it is required:
(click 1) PM to fill out “Soil Survey Request (In-House)” letter. The letter is a request for the Office of Materials & Testing to complete the soil testing and write the report.
(click 2) If a consultant has been scoped to prepare the soil survey report, fill out the same template. However, updated the language to request a review of the report instead of a request to do the work.
(click 3) Be sure to include the OMAT checklist [Next slide will discuss the checklist]
(Click 4) Follow the ProjectWise workflow entitled OMAT Geotechnical & Environmental Submittals.

## Slide 58: Soil Survey: OMAT Checklist
Notes: (click 1) The OMAT checklist is located online at ROADS/Design Related Resources/Additional Resources.
(click 2) The PM will need to choose the consultant or in-house version of the checklist. The correct checklist is based on who is preparing the soil survey report.

## Slide 59
Preliminary Design
Concept Approval
Traffic Studies
ENV Studies
Lighting Design
Drainage
Design
Geometry Design
Erosion Control Plan
Utilities
PFPR Request
Note: not in sequential order – many are done concurrently
Phase I ESA (Phase II ESA)
(SUE or 1st Submission)
Notes: (click 1) This slide is a simplified version of the Preliminary Design PDP flowchart. Once the design has incorporated all of the required analysis and information from various studies, the plans will be complete and ready for the PFPR request.

## Slide 60
Plan Development Process: Preliminary Design
Preliminary Design
PFPR inspection
PFPR Request
A3M
(if needed)
PM Milestone
Notes: (click 1) PFPR Request is a milestone that must be submitted per the baseline date.

## Slide 61: Preliminary Field Plan Review (PFPR)
The focus of the review is to ensure that the design has continued in a direction that:
Meets the Need & Purpose
Can be
Built & Maintained
Preliminary ROW Identified
Notes: The focus of the preliminary field plan review is to ensure that the design has continued in a direction that:
(click 1) Satisfies the purpose and need of the project,
(click 2) Can be built and maintained,
(click 3) And the preliminary right-of-way identified provides the required area.

## Slide 62: PFPR Request
PM needs to prepare the “PFPR Request Letter”
  Letter is online under the Program Delivery folder.
PM and Designer need to fill out the “Preliminary Field Plan Review (PFPR) Checklist”
  Checklist is online on Design Related Resources page in the Additional Resources box.
Notes: (click 1) PM needs to prepare the “PFPR Request Letter”. The letter is located online under the Program Delivery folder.
(click 2) PM and Designer need to fill out the “PFPR Checklist”. The Checklist is located online on Design Related Resources page in the Additional Resources box.

## Slide 63: Learning Objective
Generally, what two processes are complete, and mark start of the preliminary design phase?
  A. Resource ID approved & Technical Studies complete
  B. Concept Report approved & Survey Database field work complete
  C. 1st UTL submission complete & Concept Report approved
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: B

## Slide 64: Learning Objective
Which statement is true about the preliminary design phase?
It is a collection of information and studies that determine how the design of the project will proceed.
This is the initial engineering design of the project.
PFPR will provide the opportunity receive review comments and to revise the plans before they are finalized.
All of the statements are true.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D

## Slide 65: Learning Objective
Which of the follow is not critical path for the PFPR request to be on schedule?
  A. Environmental technical studies approved
  B. Utilities 1st submission or verification complete
  C. Phase II ESA report approved.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: C

## Slide 66
Information to Fill Out Templates:
PSR & P6 Schedule
Notes: Next, we are going to practice using a preconstruction status report and the Primavera P6 schedule to find information that is needed to fill out templates for the concept phase.
[Directions: Be sure that all participants have copies of slides 67 & 69 without the answers. This will be active engagement with the participants to learn how to use these resources.]

## Slide 67
What is the date of the PFPR request?
Notes: (click 1) What is the date of the PFPR request?
(direction: go to the next slide which shows the enlarged view of P6 from the PSR) (use the PSR from the previous PDP training – PI 0017959)

## Slide 68
What is the date of the PFPR request?
This is the PFPR meeting date NOT the request date
Must look at the full P6 schedule to find the date
Where do you find the PFPR Request date?
Notes: (click 1) What is the date of the PFPR request? This is an excerpt from the PSR which GDOT management looks at.
(click 2) This is scaled down version of the P6 schedule only shows the PFPR inspection BL date which is the meeting not the request.
(click 3) Where do you find the PFPR request date?
(click 4) PM must look at the full P6 schedule to find the date. (direction: move to next slide for the P6 schedule)

## Slide 69
What is the date of the PFPR request?
04/10/24 = BL date (milestone)
Notes: What date is the PFPR request due? (direction: give participants time to find the date)
(click 1) The BL date is 4/10/24. Always look at the baseline date not the other columns that say just “start” & “finish.”

## Slide 70
When should the PM have the PFPR Request letter prepared for review/signature?
BEGIN with the END in MIND
PFPR Request = 04/10/24
2 weeks before = 03/27/24
Factor time for QAQC process & signature (min. approx. 2 weeks before PFPR due date)
Notes: (click 1) When should the PM have the PFPR request letter prepared for review and signature?
(click 2) Hint: Begin with the end in mind. Use the PFPR request BL date.
(click 3) Best practice is approximately 2 weeks or 10 business days before the BL due date. For this example, that would be 3/27/24.
(click 4) PM should allow time for the QAQC process and signature. The PM should start working on the letter prior to this date.

## Slide 71
Title on PSR
Use the date that the letter will be submitted to OPD doc tracker
Yellow highlights are
directions for the preparer and should be removed along with the text.
Fill out anything that is highlighted in gray. Remove the highlight when done.
Use BL date from P6
PID is not usually required on our projects. If unsure, refer to Policy 6863-13.
PODI (Projects of Division Interest) – our projects are not PODI unless you are told otherwise
Put all PFPR packages on PW per the PW workflow
Notes: This is the PFPR request letter.
(click 1) Yellow highlights are directions for the preparer and should be removed along with the text.
(click 2) Fill out anything that is highlighted in gray. Remove the highlight when done.
(click 3) Project description needs to match the title on the PSR
(click 4) The date should be the date the letter is uploaded to the OPD document tracker.
(click 5) The date will come from the P6 schedule. Be sure to use the baseline date.
(click 6) PODI stands for Projects of Division Interest – When a project is transitioned to you to manage, if it is a PoDI project, you should be told that.
(click 7) The PFPR package should be place on ProjectWise per the ProjectWise workflow for PFPR.
(click 8) PID stands for Public Interest Determination and is not usually required on GDOT projects. If unsure, refer to Policy 6863-13 or coordinate with the project’s DUO. It is for projects where GDOT is paying or participating in the costs associated with the removal, relocation or adjustment of utility facilities. Normally the Utility Owner is responsible for these costs.

## Slide 72
Don’t forget to fill out the header
Do not remove – part of template
Initials are always
Office Head:Asst. Office Head:District Program Manager:Project Manager
Just the PI # - do not include “-PE”
Delete the link
Only applies if GDOT is acquiring ROW and there are activities prior to ROW auth.
Notes: [PFPR template letter continued]
(click 1) Fill in the PI # that GDOT can charge their time to. Do not include “-PE” with the number.
(click 2) If you have project that will not be preparing ROW appraisals in advance of the ROW funds being authorized, then remove this paragraph. (click 3) This is the link to the PW workflow. Delete the link.
(click 4) This date is part of the template. Do not remove.
(click 5) Don’t forget to fill out the header.
(click 6) Be sure to fill out the initials for reviewers and preparers of the letter. Office Head; Asst. Office Head; Program Manager or District Program Manager; Project Manager; Project Manager Assistant (if applicable and in lower case letters)

## Slide 73: Templates Used Between CR Approval and PFPR Request
The following is a list of potential templates that may be needed for a project:
Traffic and Projections Diagram letter
Traffic Projections Request Form
Environmental Technical Studies (AOEs) Request letter (in-house only)
Request to Complete Technical Studies form (in-house only)
UST Phase I Request Letter
UST Phase I Approval Request
Design Exception or Variance letter
Pavement Design Package Submittal Checklist
Soil Survey Request (In-House)
Utilities Request 1st Submission letter
PFPR Request Letter
PFPR Checklist
Notes: These are just a list of potential templates that may be required between CR approval and PFPR request. There may be other submissions needed that are not listed. These are just the most common templates that this program uses.

## Slide 74: Where to Find Templates
ROADS
  www.dot.ga.gov/GDOT/pages/DesignResources.aspx
Reference Tool: OPD Index Library (located on CD_Common/Administration/OPD Library
Notes: The templates are located on ROADS. Reference the OPD Index Library if you are having dificulting finding the template.