## Slide 1
Notes: This training is part 4 of a 5-part series related to the PDP process. The purpose of this training series is to provide a foundation level of understanding of the PDP process. It will cover every process or study that a project may require per the PDP process. For additional information, the PDP manual should be referenced. In PDP Overview #4, the training will cover the PDP process between PFPR inspection to ROW authorization.
Materials: Provide participants with paddles to engage with quizzes. Each participant should have a copy of the P6 schedule for PI 0019039.
Training Time: 1.5 hours

## Slide 2: Learning Objectives
PFPR Report Approval Process
ENV Process to ROW Authorization
ROW Plan Development Process
How to Reference a PSR and/or P6 Activities
Common Templates
Notes: The learning objectives of this training are to
(click 1) be able to explain PFPR report approval process
(click 2) Understand the environmental process for ROW Authorization & why it is critical path
(click 3) Understand the ROW plan development process
(click 4) Be able to reference a PSR and/or P6 activities for information for the templates
(click 5) Be able to locate the templates that a PM will need during the preliminary design phase

## Slide 3: Preliminary Design Phase Recap
What is the purpose of PFPR?
  A. Ensure the design meets the need & purpose of the project.
  B. Ensure that the project can be built and maintained.
  C. Identify the preliminary needs for ROW and easements.
  D. All of the above.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D

## Slide 4: Preliminary Design Phase Recap
Which of the follow must be completed prior to requesting PFPR?
  A. Environmental technical studies approved
  B. Utilities 1st submission or verification complete
  C. Preliminary design complete
  D. All of the above
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D

## Slide 5: Preliminary Design Phase Recap
Preliminary design must avoid or minimize impacts to all of the following except?
  A. Utilities
  B. Historic Resources
  C. Pavement
  D. Protected Species
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: C

## Slide 6
Plan Development Process
(Design to Construction)
Concept Phase
Construction
Final Design
ROW Authorization
Note: This is only a graphical representation of when ROW Auth occurs.
Preliminary Design
PFPR
Notes: (click 1) This training is going to cover the PDP steps between the PFPR inspection and right-of-way authorization. It will cover finishing the preliminary design phase and starting the final design phase.

## Slide 7: Preliminary Design Phase
Federal $ Must
Follow
PDP
P
D
P
PDP Chapter 6
Final Design Starts After PFPR Report Acceptance
All Projects have Preliminary Design
Notes: (click 1) If any federal money will be used on the project, GDOT must follow the Plan Development Process (PDP) per the oversight agreement with Federal Highway Administration (FHWA).
(click 2) All projects must go through a preliminary design phase before entering into the final design phase. However, there are some types of projects with expedited schedules that will not require a true preliminary design phase. Regardless, the project will start with preliminary design before moving into final design.
(click 3) Most but not all projects start final design phase after PFPR report responses are accepted and distributed. The exception is that some expedited projects may not have a PFPR meeting.

## Slide 8
Final PFPR Report
PFPR Request
PFPR Inspection
Draft PFPR Report
Preliminary/Final Design (PFPR Process)
Accepted PFPR Report
  Final PFPR report ≠ Accepted PFPR report
Office of Engineering Services
Notes: (click 1) After the PM requests PFPR, a draft PFPR report is provided with comments that will be discussed at the PFPR inspection (aka meeting). The final report contains the final set of comments based on the review of the preliminary plans. The accepted PFPR report is the final PFPR with the designer’s responses to the comments. The PFPR responses must be accepted by the Office of Engineering Services. The final PFPR report is not the same as the accepted PFPR report.

## Slide 9: PFPR Responsibilities: Office of Engineering Services
PDP Section 6.6.4
Conducts Review of Preliminary Plans
Schedules PFPR Meeting
Reviews & Accepts PFPR Report
Prepares Final PFPR Report
FINAL
Prepares Draft PFPR Report
DRAFT
Notes: (click 1) The Office of Engineering Services will schedule the PFPR meeting after they have reviewed the PFPR package for completeness.
(click 2) The Office of Engineering Services will conduct the review of the plans and solicit comments from other SMEs.
(click 3) Then Engineering Services will prepare the draft set of comments which will be used as discussion points at the PFPR inspections.
(click 4) After the PFPR meeting, the draft PFPR report is updated and finalized before returning the PFPR report to the PM.
(click 5) The PM submits the PFPR report back to Engineering Services with the designer’s responses to the comments. These are the written commitments that must be addressed before the plans are ready for final field plan review. Accepted means that the responses to the comments have been approved by the Office of Engineering Services.

## Slide 10
Final PFPR Report
PFPR Request
PFPR Inspection
Draft PFPR Report
Preliminary/Final Design (PFPR Process)
Accepted PFPR Report
Preliminary Design Phase
Final Design Phase
PFPR responses due
4 weeks after
Notes: (click 1) The PM has to submit the responses to the comments within 4 weeks. The 4-week clock starts when the final PFPR report is received.
(click 2) When the responses are accepted, the PFPR is finalized and distributed to GDOT management and other offices. The preliminary design phase concludes when the PFPR comments are addressed on the plans. Once the plans are revised, then the final design phase begins.

## Slide 11: PFPR Report Responsibility: PM
PDP Section 6.6.4
Coordinate with Designer
Review PFPR Report for Missing Responses or PM Commitments
Submit
Responses to Engineering Services
Distribute Accepted PFPR Report
Report with Responses due in
4 weeks
Notes: (click 1) When the PM receives the final PFPR report, the PM must coordinate with the designer for the responses.
(click 2) The designer will submit the PFPR report with the responses back to the PM. The PM must review the responses to ensure that no comments were missed or if there are commitments for the PM, the PM is aware of these.
(click 3) The PM submits the PFPR report with responses back to Engineering Services. Don’t forget that this must be done within 4 weeks of receiving the final PFPR report.
(click 4) Once the PFPR report is accepted, the PM is responsible to distribute the report via email.

## Slide 12: Preliminary Design Phase – PFPR Inspection
After the report is considered ACCEPTED:
  The preliminary plans and other appropriate documents will be modified, where necessary, to address the issues discussed at the PFPR.
  Modifications to the plans that affect ROW and easements, construction limits, and environmental resources should be completed immediately.
Timely resolution of all field plan review issues is critical for continued coordination and smooth plan development.
PDP Section 6.6.4
Notes: No changes to the report can be made after it is accepted by the Office of Engineering Services. After it is accepted:
(click 1) The preliminary plans and other appropriate documents will be modified, where necessary, to address the issues discussed at the PFPR.
(click 2) Modifications to the plans that affect ROW and easements, construction limits, and environmental resources should be completed immediately.
(click 3) Timely resolution of all field plan review issues is critical for continued coordination and smooth plan development.

## Slide 13: PFPR Review
How many versions of the PFPR report are there?
1
2
3
4
Draft PFPR Report
Final PFPR Report
Accepted PFPR Report
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: C - The 3 versions are draft, final, and accepted.

## Slide 14: PFPR Review
Why is the Final PFPR report different from the other versions?
It is prepared prior to the PFPR inspection.
It is approved by Office of Engineering Services.
It is prepared by OES.
It is prepared after the PFPR inspection.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D - Remember that OES is not an acronym for the Office of Engineering Services. It is the acronym for Office of Environmental Services.

## Slide 15: PFPR Review
How many weeks does the PM have to submit the final PFPR report with responses?
2
4
8
As long as it takes.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: B - It is important for the PM to know this timeframe. Engineering Services does not always include a due date in the email with the final PFPR report.

## Slide 16: PFPR Review
Who is responsible for distributing the Accepted PFPR report?
GDOT PM
Consultant PM
Engineering Services
Design Policy & Support
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: A

## Slide 17
Distribute PFPR Report
Approved ROW Plans
Prepare NEPA document*
Detailed ROW Cost Estimate
Complete Draft ROW Plans
Implement PFPR comments
L&D Report
NEPA document approval*
ROW Authorization
Note: not in sequential order – many are done concurrently
*may not be required for a project
ROW-UTL Mtg *
Final Design (PFPR to ROW Authorization)
Environmental Certification for ROW Authorization
Request Soil Survey* (if not requested prior to PFPR)
Request BFI/WFI and/or Phase II ESA*
Final Design
Prelim.
Notes: This slide is a simplified version of the Final Design PDP flowchart from after PFPR to ROW Authorization. Final design phase starts after the accepted PFPR report and responses are distributed to GDOT management and various offices. The plans are updated per the PFPR comments. Based on the updated plans, ROW plans are refined and the NEPA document is prepared. Concurrent to the plan design is the ROW plan process and the NEPA document approval. After ROW plans are approved, environmental certification is issued, and a detailed cost estimate is approved, ROW funds can be authorized to begin acquisition of property. Next, we will focus on the environmental process.

## Slide 18
Distribute PFPR Report
Prepare NEPA document*
NEPA document approval*
ROW Authorization
Note: not in sequential order – many are done concurrently
Final Design (PFPR to ROW Authorization)
Environmental Certification for ROW Authorization
Final Design
Prelim.
Notes: While final design is in progress, the NEPA process is underway. Reminder that having any federal money allocated to the project will trigger NEPA and the need for a NEPA document.

## Slide 19
Distribute PFPR Report
Prepare NEPA document*
NEPA doc approval*
FFPR Request
Note: This graphic applies if there is not a ROW phase.
* Does not apply if GEPA and under $100 million
Final Design (No ROW Phase): Environmental Process
Final Design
Prelim.
Notes: While final design is in progress, the NEPA process is underway. Reminder that having any federal money allocated to the project will trigger NEPA and the need for a NEPA document. If there isn’t a ROW phase, then NEPA approval is needed prior to the FFPR request. The preparation of the NEPA documentation is the same for both scenarios. It begins after the PFPR report has been distributed and the plans are updated based on the PFPR comments.

## Slide 20
Prepare NEPA document*
NEPA document approval*
Environmental Process (PFPR to ROW Auth):
NEPA Document
Environmental Certification for ROW Authorization
NEPA document prepared after:
Technical studies are approved
Plans are updated
Notes: The NEPA document is prepared after both of the following are done.
(click 1) Environmental technical studies are approved. These are the reports that discuss impacts to ecology, air, noise, and cultural resources (history and archaeology). Normally, the technical studies are approved prior to the PFPR request. However, there are some exception.
(click 2) The preliminary design plans have been updated per the comments and responses in the accepted PFPR report.

## Slide 21
Environmental Process (PFPR to ROW Auth): NEPA Document
NEPA document requires FHWA approval.
Prepare NEPA document*
NEPA document approval*
Environmental Certification for ROW Authorization
Notes: (click 1) NEPA document requires approval by the Federal Highway Administration. The exception is if a PCE (programmatic categorical exclusion) is prepared. Then GDOT can approve it.

## Slide 22
Environmental Process (PFPR to ROW Auth): Environmental Certification
Certification is issued after the NEPA document is approved.
Required for ROW Authorization.
  Only certification required to authorize the funds.
Prepare NEPA document*
Environmental Certification for ROW Authorization
NEPA document approval*
Note: GEPA projects can certify after technical studies are approved.
If under $100 million
Notes: (click 1) The Environmental Certification is issued by OES after the NEPA document is approved.
(click 2) Environmental certification is required for ROW authorization. It is the only certification required to authorize the funds to start acquiring ROW.
(click 3) For state funded projects, environmental certification can occur after the technical studies are approved if the project is less than $100million.

## Slide 23: Environmental Studies
The NEPA document should be submitted from the consultant to the OES reviewer directly.
  No letters or emails are needed from the PM.
OES
Submission
ENV Consultant
Notes: (click 1): The NEPA document should be submitted directly from the environmental consultant to the OES reviewer. No letters or emails are needed from the PM. This is the one office where submissions do not need to go through the PM.

## Slide 24: Environmental Studies
In-House NEPA Document
OES
Environmental Certification
NO PM Action Needed
Notes: (click 1) If the NEPA document will be completed in-house, no letters or emails are needed from the PM.
(click 2) Approval of the NEPA document will trigger OES to certify for ROW. No action is needed by the PM.
(click 3) These activities do not require a PM action. However, it is still the PM’s responsibility to coordinate with the Environmental SME to ensure that the project is on schedule for these items.

## Slide 25: Environmental Review
What is required before the environmental certification can be issued?
  A. An approved NEPA document
  B. Approved technical studies if it is a GEPA project (under $100mil)
  C. Approved Permits
  D. A & B
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D

## Slide 26: Environmental Review
Which of the following is NOT true about the environmental certification?
  It is the only certification required for ROW Authorization.
  ROW funds cannot be authorized without it.
  PFPR Report cannot be approved without it.
  Not every project will require the certification for ROW Authorization.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: C - Answer D is true because not all projects have the need to acquire ROW or easements.

## Slide 27
Distribute PFPR Report
Approved ROW Plans
Prepare NEPA document*
Detailed ROW Cost Estimate
Complete Draft ROW Plans
Implement PFPR comments
L&D Report
NEPA document approval*
ROW Authorization
Note: not in sequential order – many are done concurrently
*may not be required for a project
ROW-UTL Mtg *
Final Design (PFPR to ROW Authorization)
Environmental Certification for ROW Authorization
Request Soil Survey* (if not requested prior to PFPR)
Request BFI/WFI and/or Phase II ESA*
Final Design
Prelim.
Notes: Next, we will focus on the ROW plan development process.

## Slide 28
Distribute PFPR Report
Approve ROW Plans
Complete Draft ROW Plans
L&D Report
ROW Authorization
Note: not in sequential order – many are done concurrently
*may not be required for a project
ROW-UTL Mtg *
Final Design (PFPR to ROW Authorization)
Final Design
Prelim.
Notes: The ROW plan development starts during preliminary design. However, the plans are finalized after PFPR.

## Slide 29
Updated ROW Plans
ROW-UTL Mtg
(if needed)
ROW Plans (PFPR to ROW Authorization)
After PFPR, the ROW plans are updated.
PM coordinates with the DUO to determine if a ROW-UTL meeting is required.
The purpose of the meeting is to ensure that there is enough ROW and easement for proposed utility relocations.
PFPR
Draft ROW Plans
Notes: (click 1) The PFPR package included a set of draft ROW plans. After the preliminary plans are updated based on the PFPR comments, the draft ROW plans are then updated to the final version of the plans.
(click 2) The PM must then coordinate with the District Utility Office to determine if a ROW- Utilities meeting is required.
(click 3) The purpose of the meeting is to ensure that there is enough ROW and easement for proposed utility relocations.

## Slide 30
Approved ROW Plans
ROW Plans
L&D Report
ROW-UTL Mtg
ROW Plans (PFPR to ROW Authorization)
After the ROW-UTL mtg, the plans are updated and finalized.
  The meeting minutes must be attached with the submission of the ROW plans to the Office of ROW.
Submit ROW Plans
(if needed)
Include mtg minutes
Notes: (click 1) Based on the ROW-UTL mtg, the plans are updated and finalized.
(click 2) The meeting minutes (or a waiver to not hold the meeting) must be attached with the submission of the ROW plans to the Office of ROW.

## Slide 31
Approved ROW Plans
ROW Plans
L&D Report
ROW-UTL Mtg
ROW Plans (PFPR to ROW Authorization)
Before GDOT can purchase ROW, the project must be advertised that ROW will be acquired.
This advertisement is done as part of the Location & Design (L&D) report.
Final ROW Plans
(if needed)
Notes: (click 1) Before GDOT can purchase ROW, the project must be advertised that ROW will be acquired.
(click 2) This advertisement is done as part of the Location & Design (L&D) report.

## Slide 32
Approved ROW Plans
ROW Plans
L&D Report
ROW-UTL Mtg
ROW Plans (PFPR to ROW Authorization)
ROW plans are approved after the L&D report is signed.
Final ROW Plans
(if needed)
Notes: (click 1) ROW plans are approved after the L&D report is signed.

## Slide 33
Approved ROW Plans
NEPA Approval
L&D Report
ROW Plans (PFPR to ROW Authorization)
NEPA Date
L&D Date
Notes: (click 1) NEPA approval date is included with L&D Report.
(click 2) L&D Report approval date is included with ROW plan coversheet.
(click 3) ROW plans are approved after signed ROW coversheet with L&D date is provided

## Slide 34: ROW Plans Process
The ROW/UTL team meeting is held approximately 2 weeks before the ROW plans are submitted.
The draft ROW plans are submitted about 1 week before L&D Report is submitted.
  The UTL-ROW team meeting minutes are to be attached to the submission of the plans.
  PM submit ROW plans – follow P6 BL
Notes: (click 1) The ROW/UTL team meeting is held approximately 2 weeks before the ROW plans are submitted.
(click 2) The draft ROW plans are submitted about 1 week before L&D Report is submitted.
(click 3)The UTL-ROW team meeting minutes are to be attached to the submission of the plans. If the meeting is waived, attach the email from the District Utility Office stating that the meeting was not required.
(click 4) PM should follow the P6 baseline date for submitting the ROW plans.

## Slide 35: ROW Plans Process (continued)
To submit the ROW plans to the Office of Right-of-Way:
  Follow the ProjectWise workflow for “Right of Way Plans Approval and Revision Process”
  Prepare the “ROW Plan Submittal Letter”
    Email the letter and plans to PlansOffice@dot.ga.gov
Notes: (click 1) To submit the ROW plans to the Office of Right-of-Way:
(click 2) Follow the ProjectWise workflow for “Right of Way Plans Approval and Revision Process”
(click 3) The PM will prepare the ROW plans submittal letter and email the plans link to PlansOffice@dot.ga.gov.

## Slide 36: ROW Plans Process (continued)
The L&D report is submitted to the Office of Design Policy & Support (DPS).
  Fill out the L&D Submittal Letter
  Fill out L&D report & notice template
    Location and Design Report Template – Appendix B
  Submit via email to ConceptReports@dot.ga.gov
Notes: (click 1) The L&D report is submitted to the Office of Design Policy & Support (DPS).
(click 2) “L&D Submittal Letter” is located online under OPD templates.
(click 3) L&D report & notice template is located on ROADS/Manuals & Guides/Plan Development Process/Category: Report Templates and Examples/Location and Design Report Template – Appendix B. This is filled out by the PM.
(click 4) PM will submit both the letter and the L&D report via email to ConceptReports@dot.ga.gov to the Office of Design Policy & Support.

## Slide 37: ROW Plans Process (continued)
  Do not hold up the L&D submission for the environmental date.
  The L&D cannot be approved without the environmental approval date included.
Notes: (click 1) The L&D report includes the environmental document approval date.
(click 2) The environmental document may be pending approval when the “draft” L&D is submitted. Do not hold up the L&D submission for the environmental date. For submitting the draft L&D report to DPS, be sure to follow the P6 baseline date, if possible.
(click 3) The L&D cannot be approved without the environmental approval date included. Therefore, DPS can complete their review and have it pending approval until the environmental approval date is available.

## Slide 38: ROW Plan Development Review
When are the ROW plans developed?
After the technical studies are approved.
Before PFPR is held.
After PFPR is held.
After the L&D is approved.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: B -The draft plans are included with the PFPR package. The plans are updated and finalized after PFPR.

## Slide 39: ROW Plan Development Review
The ROW-UTL meeting is a coordination meeting to ensure there is enough right-of-way or easement for utility relocations and associated work.
True
or
False
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: True

## Slide 40: ROW Plan Development Review
What report is prepared to provide information for the advertisement of ROW acquisition starting?
  Location & Design Report (L&D)
  NEPA Document
  ROW Report
  Concept Report
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: A

## Slide 41: ROW Plan Development Review
What documents have to be approved before the ROW plans can be approved?
Concept Report & L&D Report
NEPA Document & GEPA Document
NEPA Document & L&D Report
Utility Plans & ROW-UTL Meeting
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: C - Remember that the date of the NEPA document is needed before the L&D Report can be approved. The L&D Report must be approved before the ROW plans can be approved because the L&D date is on the ROW plans coversheet.

## Slide 42
Approve ROW Plans
ROW Plans
L&D Report
ROW-UTL Mtg
Utilities (PFPR to ROW Authorization)
Notes: The ROW-UTL meeting is a coordination meeting to ensure that the design involving the utilities being relocated has included the land necessary to move the utilities, if applicable. Remember that the coordination with the utility companies took place prior to the PFPR request as part of 1st Utilities submission. This is a coordination meeting with the designer, district utility coordinator, the district ROW coordinator, and the PM.

## Slide 43: Utilities
If Utilities will be relocated, a ROW/UTL team meeting may be required.
PM should refer to ROW-UTL team meeting procedures to determine if it is required.
  Confirm with the District UTL coordinator the meeting is required.
  Fill out the “ROW-UTL Meeting Request Letter”.
Notes: (click 1) If Utilities will be relocated, a ROW/UTL team meeting may be required.
(click 2) PM should refer to ROW-UTL team meeting procedures to determine if it is required.
(click 3) If unsure, PM should confirm with the District UTL coordinator that it is required.
(click 4) If it is required, PM is to fill out the “ROW-UTL Meeting Request Letter”. Letter is located online in the Program Delivery folder.

## Slide 44: Utility Review
When is the ROW-UTL meeting held?
After PFPR is held and the plans are updated.
Prior to PFPR being held.
After the L&D Report is submitted.
After the environmental report is approved.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: A - The purpose of the ROW-UTL meeting is to ensure that there is enough ROW in the plans for relocation of utilities. Therefore, this meeting is needed after the preliminary design is updated and before the ROW plans are submitted for approval. Don’t forget that the meeting minutes from this meeting must be attached with the ROW plans are submitted for review.

## Slide 45
Distribute PFPR Report
Approved ROW Plans
Prepare NEPA document*
Detailed ROW Cost Estimate
Complete Draft ROW Plans
Implement PFPR comments
L&D Report
NEPA document approval*
ROW Authorization
Note: not in sequential order – many are done concurrently
*may not be required for a project
ROW-UTL Mtg *
Final Design (PFPR to ROW Authorization)
Environmental Certification for ROW Authorization
Request Soil Survey* (if not requested prior to PFPR)
Request BFI/WFI and/or Phase II ESA*
Final Design
Prelim.
PDP Section 6.3.2
Notes: If a soil survey is required and was not done before PFPR, then it would be needed after PFPR. Always check section 6.3.2 of the PDP manual to determine if and when a soil survey is required for each project. A soil survey will determine the geotechnical features of the soil. These features must be understood by the designer for engineering the project correctly.

## Slide 46: Soil Survey
It is required for major projects such as:
  widening projects,
  new alignments, and
  projects that have a significant change in grade (5ft raising or lowering of the existing profile grade line).
PDP Section 6.3.2
Notes: (click 1) It is required for major projects such as widening projects, new alignments, and projects that have a significant change in grade (5ft raising or lowering of the existing profile grade line).
Bullet 4: If a Soil Survey Report is required, check PDP to see if the project is located within a county that requires and approved report prior to PFPR. If is needed but requested prior to PFPR, it will need to be requested after PFPR inspection is held.

## Slide 47: Soil Survey
If a Soil Survey Report is required, check PDP manual.
  If it is required but not previously requested, the request would be due during this portion of the PDP process.
PDP Section 6.3.2
Notes: If a Soil Survey Report is required, check PDP to see if the project is located within a county that requires and approved report prior to PFPR.
(click 1) If is needed but requested prior to PFPR, it will need to be requested after PFPR inspection is held.

## Slide 48: Soil Survey
If it is required:
  Fill out “Soil Survey Request (In-House)”
    If it is a consultant prepared report, use same letter but modify it.
  Include the OMAT checklist.
  Follow the PW workflow OMAT Geotechnical & Environmental Submittals
Add note in OPD tracker of any change to templates.
Notes: If it is required:
(click 1) PM to fill out “Soil Survey Request (In-House)” letter. The letter is a request for the Office of Materials & Testing to complete the soil testing and write the report.
(click 2) If a consultant has been scoped to prepare the soil survey report, fill out the same template. However, updated the language to request a review of the report instead of a request to do the work.
(click 3) Be sure to include the OMAT checklist [Next slide will discuss the checklist]
(Click 4) Follow the ProjectWise workflow entitled OMAT Geotechnical & Environmental Submittals.

## Slide 49: Soil Survey: OMAT Checklist
Notes: (click 1) The OMAT checklist is located online at ROADS/Design Related Resources/Additional Resources.
(click 2) The PM will need to choose the consultant or in-house version of the checklist. The correct checklist is based on who is preparing the soil survey report.

## Slide 50
Distribute PFPR Report
Approved ROW Plans
Prepare NEPA document*
Detailed ROW Cost Estimate
Complete Draft ROW Plans
Implement PFPR comments
L&D Report
NEPA document approval*
ROW Authorization
Note: not in sequential order – many are done concurrently
*may not be required for a project
ROW-UTL Mtg *
Final Design (PFPR to ROW Authorization)
Environmental Certification for ROW Authorization
Request Soil Survey* (if not requested prior to PFPR)
Request BFI/WFI and/or Phase II ESA*
Final Design
Prelim.
Notes: Reminder: The graphic does not represent the PDP process in sequential order. However, if a BFI or WFI is needed, it should be done after PFPR.

## Slide 51: WFI/BFI
WFI = Wall Foundation Investigation
BFI = Bridge Foundation Investigation
WFI/BFI reports are prepared and/or approved by the Office of Materials & Testing (OMAT).
PDP Section 6.3.5
Notes: Bullet 1: WFI = Wall Foundation Investigation
Bullet 2: BFI = Bridge Foundation Investigation
Bullet 3: WFI/BFI reports are prepared and/or approved by the Office of Materials & Testing (OMAT).

## Slide 52: WFI/BFI
Required on projects that have non-standard GDOT walls (WFI).
Required if a bridge structure (not just the bridge deck) is being replaced or newly constructed (BFI).
Before any type of foundation investigation can be requested, the Office of Bridge Design must review and approve the plans.
Notes: (click 1) Required on projects that have non-standard GDOT walls (WFI).
(click 2) Required if a bridge structure is being replaced or newly constructed (BFI).
(click 3) Before any type of foundation investigation can be requested, the Office of Bridge Design must review and approve the plans.

## Slide 53: WFI/BFI
A template letter does not exist. One will need to be created to submit a request or to request approval of a report.
  The District Program Manager needs to approve the letter before it is sent.
Notes: (click 1): A template letter does not exist. One will need to be created to submit a request or to request approval of a report. The Program Manager needs to approve the letter before it is sent.

## Slide 54: WFI/BFI
The designer needs to complete the submittal checklist.
  ROADS/Design Related Resources/Additional Resources/GEOTECH XXX Submittal Checklist
Follow the directions per the ProjectWise workflow for “OMAT Geotechnical & Environmental Submittals”.
  Submit through OPD Document Tracker
  Sent automatically to OMAT after OPD’s review
Notes: (click 1) Be sure to include the OMAT checklist which is located online at ROADS/Design Related Resources/Additional Resources. Just like the soil survey report, the PM will need to choose the consultant or in-house version of the checklist depending on who is doing the foundation investigation.
(click 2) Follow the directions per the ProjectWise workflow for “OMAT Geotechnical & Environmental Submittals”. The PM will upload the letter and checklist to the OPD Document Tracker. Once it has been reviewed internally, it will be automatically submitted to OMAT for review from the OPD document tracker.

## Slide 55
Distribute PFPR Report
Approved ROW Plans
Prepare NEPA document*
Detailed ROW Cost Estimate
Complete Draft ROW Plans
Implement PFPR comments
L&D Report
NEPA document approval*
ROW Authorization
Note: not in sequential order – many are done concurrently
*may not be required for a project
ROW-UTL Mtg *
Final Design (PFPR to ROW Authorization)
Environmental Certification for ROW Authorization
Request Soil Survey* (if not requested prior to PFPR)
Request BFI/WFI and/or Phase II ESA*
Final Design
Prelim.
Notes: Next, we will focus on Detailed ROW Cost Estimates. The detailed cost estimate is not the same as the cost estimates that the PM has to submit either annually or at milestones. This is estimate is what is authorized as the true amount of the ROW funds that the project will need to acquire parcels of land.

## Slide 56: Detailed ROW Cost Estimate
Prepared by the District ROW Office.
Submission of the draft ROW plans to the ROW office will trigger the preparation of the detailed ROW cost estimate.
  No additional action is required by the PM.
  Last ROW cost estimate prepared for
  the project.
Notes: (click 1) This is prepared by the District ROW Office. All of the previous cost estimates were prepared by either a consultant vendor or the GDOT ROW office.
(click 2) Submission of the draft ROW plans to the ROW office will trigger the preparation of the detailed ROW cost estimate.
(click 3) No additional action is required by the PM.
(click 4) This is the last ROW cost estimate prepared for the project.

## Slide 57
Distribute PFPR Report
Approved ROW Plans
Detailed ROW Cost Estimate
ROW Auth
Final Design (PFPR to ROW Authorization)
Environmental Certification for ROW Authorization
Final Design
Prelim.
Notes: Next, we will focus on the required components to authorize the ROW funds.

## Slide 58: ROW Authorization
ROW Authorization is the approval of funds used to purchase right-of-way and easements for the construction of the project.
Notes: ROW Authorization is the approval of funds that will be used to purchase right-of-way and easements for the construction of the project.

## Slide 59: ROW Authorization (for Federally Funded Projects)
Environmental approval is critical path to ROW authorization.
NEPA document approval is needed for both:
  Environmental Certification; and
  L&D Report approval
L&D approval
ROW plan approval
NEPA Doc
approval
ENV Cert
Notes: (click 1) The environmental approval is critical path for ROW Authorization.
(click 2) The NEPA document approval is needed for both environmental certification and the location and design report approval. Remember the L&D report cannot be approved until the environmental approval date is included. The ROW plans cannot be approved until the date from the L&D report is added to the coversheet.

## Slide 60: ROW Authorization
The following are required in order to authorize the use of the ROW funds:
  Environmental Certification
  ROW Plan Approval
  Approved Detailed ROW Cost Estimate
L&D approval
ROW plan approval
ROW Auth
NEPA Doc
approval
ENV Cert
Detailed ROW Est.
Notes: The following are required in order to authorize the use of the ROW funds:
(click 1)Environmental Certification. Remember this is critical path.
(click 2) ROW Plan Approval.
(click 3) Approved Detailed ROW Cost Estimate

## Slide 61: ROW Authorization Review
What is the critical path activity to ensure that ROW Authorization is on schedule?
ROW plan approval
PFPR report approval
Soil Survey report approval
Environmental approval
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D

## Slide 62: ROW Authorization Review
Without the environmental document approval, three items for ROW authorization cannot be approved or issued. Which is item not impacted by the environmental approval?
  A. Environmental certification
  B. L&D approval
  C. Detailed ROW cost estimate
  D. ROW plan approval
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: C - The detailed ROW cost estimate is based on the final version of the ROW plans. Note that I did not say based on the approved ROW plans.

## Slide 63
Information to Fill Out Templates:
PSR & P6 Schedule
Notes: Next, we are going to practice using a preconstruction status report and the Primavera P6 schedule to find information that is needed to fill out templates for the concept phase.
[Directions: Be sure that all participants have a copy of the P6 schedule for PI 0019039.]

## Slide 64
P6 Activities for ROW Plans and Environmental Approval
Use the Schedule for PI 0019039
Find the P6 dates for the following activities:
When are the ROW plans to be submitted by the PM?
What is the L&D Approval date?
What is the CE approval date?
What is the environmental certification date?
When are the ROW plans to be approved?
Notes: [Direction: Each participant should have a pdf copy of the schedule for PI 0019039. Give participant time to find the answer.]

## Slide 65
P6 Activities for ROW Plans and Environmental Approval
When are the ROW plans to be submitted by the PM?
Note: Submissions are 0-day duration (same start & finish date)
06/24/25 = BL date
Notes: (click 1) For the P6 schedule, notice that there are a variety of steps shown but they are not all are shown in chronological order. Instead, knowing the PDP process and looking at the baseline (BL) date to determine which step comes first. For this project, the PM submits ROW plans is June 24, 2025. Remember to look at the baseline dates. Do not follow the start and finish dates. These are the projected dates based on the information that has been entered as actual dates and % complete.
(click 2) Any task that is a submission will have zero-day duration. This means that the start and finish date are the same.

## Slide 66
P6 Activities for ROW Plans and Environmental Approval
What is the L&D approval date?
Hint: It is a date after the PM submits the L&D.
03/18/26: BL finish date of 60100
60500 is the advertisement period which is after the approval
Notes: (click 1) Hint: The L&D approval date is after the PM submits the L&D Report. Think about the order of the process.
(click 2) The approval date should try to match the baseline finish date, which is 3/18/26. An approval task is not the same a submission task. It takes time to review and approve. Consequently, the PM should look at the baseline finish date for the approval date that the project is targeting.
(click 3) Task 60500 is the L&D Approval Advertisement. Once the L&D report is approved, then the project is advertised. This advertisement period notifies the public that ROW acquisition is about to start on a project.

## Slide 67
P6 Activities for ROW Plans and Environmental Approval
What is the CE approval date?
Hint: FHWA is the agency that approves NEPA documents
03/02/26: the finish date of 14573
Notes: (click 1) Hint: Federal Highway Administration is the agency that approves the NEPA documents.
(click 2) This schedule is a little tricky to follow using the hint. Sometimes as a PM, you will have to play detective to understand the schedule because there may be activities needed that another project did not require. For this project, you can see that the environmental document has several sublevels of the work breakdown structure. Environmental Documents is WBS 16.10. Categorical Exclusion or CE is WBS 16.10.3. 4f is WBS 16.10.3.2.
(click 3) If you look at task 14311 NEPA Document Summary, it is a summary task. That means that it starts when the 1st activity related to the task begins and finishes when the last task ends. Using this knowledge, as a PM the NEPA document is finished on 3/2/26. Since the PM knows how the summary task works and that the NEPA document approval is the end of these tasks, the PM can review P6 and realize that Task 14573 is the last task to be completed.
(click 4) The finish date of Task 14573 has a finish date of 3/2/26 which matches the summary task finish date. This is when the CE will be approved. The title of the task does not directly state that it is FHWA review and approval, but it does say Agency Review.

## Slide 68
P6 Activities for ROW Plans and Environmental Approval
What is the environmental certification date?
Hint: ENV Certification is after agency approval of the NEPA doc
03/16/26: the finish date of 70300
Notes: (click 1) Hint: Environmental certification is after agency approval of the NEPA document.
(click 2) Task 70300 is the Environmental Certification for ROW Authorization Complete task. Remember that approval or certification would be the finish date. For this project, the schedule has baseline environmental certification date of 3/16/26. Note that this is a task under the WBS for ROW plan Activities. That is why it is not under the Environmental Documents WBS.

## Slide 69
P6 Activities for ROW Plans and Environmental Approval
When are the ROW plans to be approved by?
03/18/26: the finish date of 50400
50000 is a summary task for ROW plan steps. It is complete when ROW plans are approved.
Notes: (click 1) Task 50400 is the ROW plans final approval. For this project, it has a baseline finish or approval date of 3/18/26.
(click 2) Task 50000 is ROW Plans Summary. Since the word summary is in the title, the PM knows that this is the start and finish of all activities associated with this WBS. The baseline finish date matches the ROW plans approval date.

## Slide 70
P6 Activities for ROW Plans and Environmental Approval
L&D approval
ROW plan approval
NEPA Doc
approval
ENV Cert
3/18/26
3/2/26
3/16/26
3/18/26
ENV is CRITICAL PATH
Notes: (click 1) Now putting the dates that we have just found from the P6 schedule and using the knowledge of how the approved NEPA document is linked to other documents for ROW authorization, you can see that Environmental is critical path. If the environmental process is delayed, then these other items will be delayed. Consequently, the authorization of the ROW funds will be delayed because ROW funds cannot be authorized without having ROW plans approved, Environmental certification, and the detailed cost estimate.

## Slide 71
Fill out anything that is highlighted in gray. Remove the highlight when done.
Yellow highlights are
directions for the preparer. For this template, keep items 1 & 2 after removing the highlight.
Title on PSR
Use the date that you anticipate the letter will be signed
Delete steps 3 & 4 after the directions are completed. Step 4 is the directions for the email submission.
Initials are always
Office Head: Asst. Office Head: District Program Manager: Project Manager
Notes: This is the L&D submission letter located online in OPD templates.
Click 1-6 (read info)

## Slide 72
The blue text is the directions. Delete all blue text.
Only applies if scope has changed
Kimberly W. Nesbitt (Office of Program Delivery)
Notes: This is the L&D notice and is located online in ROADS/Manuals & Guides/Plan Development Process/Category: Report Templates and Examples/Location and Design Report Template – Appendix B.
Click 1-3 (read items)

## Slide 73
Update header
If not approved yet, write “TBD”; update when approved – for GEPA write date that tech studies were approved.
If GEPA, add a statement that it is under $100 million and technical studies are complete.
Choose the one(s) that apply
Fill in Document Type (NEPA or GEPA)
Notes: This is more of the L&D report.
Click 1-5 (read items)

## Slide 74
Note: Submit a pdf and Word version
Check the location map for this info
Notes: This is the rest of the L&D notice.
Click 1-2 (read items)

## Slide 75
Leave blank line
Fill out the top
The blue text is the directions. Delete all blue text.
Fill out info
Fill out info – office head is Kim Nesbitt; include PM’s email and telephone number
Notes: This is the L&D notice which is part of the L&D report template. The notice is used to advertise to the public the upcoming ROW acquisition for a project.
Click 1-5 (read items)

## Slide 76: Templates Used Between PFPR Inspection and ROW Authorization
The following is a list of potential templates that may be needed for a project:
ROW-UTL Team Meeting Request Letter
L&D Submission Letter
L&D Report & Notification
Soil Survey Request
WFI or BFI Request
Notes: These are just a list of potential templates that may be required between PFPR inspection and ROW authorization. There may be other submissions needed that are not listed. These are just the most common templates that this program uses.