## Slide 1
Notes: This training is part 5 of a 5-part series related to the PDP process. The purpose of this training series is to provide a foundation level of understanding of the PDP process. It will cover every process or study that a project may require per the PDP process. For additional information, the PDP manual should be referenced. In PDP Overview #5, the training will cover the PDP process between ROW authorization to Let.
Materials:
Training Time: 2 hours

## Slide 2: Learning Objectives
Identify 3 Versions of the Final Plans
List 3 Certifications for Let
List 5 Items to Authorize CST Funds
3 Types of Plan Changes
FFPR Report Approval Process
FFPR
Notes: The learning objectives of this training are to
(click 1) Be able to explain FFPR report approval process
(click 2) Be able to identify the 3 versions of the final plans
(click 3) Be able to list the 3 certifications required for Let
(click 4) Be able to list the 5 items needed to authorize construction funds
(click 5) Be able to list the 3 types of plan changes after final plans are submitted

## Slide 3: PFPR Review
Which is NOT a version of the PFPR report?
Draft
Final
Accepted
Approved
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D - GDOT accepts the responses to the comments. However, this is not an “approval” of the changes. The designer will still need to evaluate whether the design changes will work.

## Slide 4: PFPR Review
What is the timeframe for a PM to submit the PFPR report with responses?
2 weeks
4 weeks
8 weeks
30 days
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: B - It is important for the PM to know this timeframe. Engineering Services does not always include a due date in the email with the final PFPR report. Although 30 days is 4 weeks, the timeframe is measured in weeks.

## Slide 5: ROW Authorization Review
Which certification(s) is needed to Authorize ROW funds?
Environmental & Utilities
Right-of-Way
Utilities
Environmental
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D - For ROW authorization, only one certification is required which is the environmental certification.

## Slide 6
Plan Development Process
(Design to Construction)
Concept Phase
Preliminary Design
Final Design
Construction (Let)
Notes: This training is only focusing on PDP steps that occur during the final design phase.

## Slide 7: Final Design Phase
PDP Section 7
Federal $ Must
Follow
PDP
P
D
P
Begins after PFPR Report is Accepted
Avoid changes to ROW plans (if possible)
Notes: (click 1) If any federal money will be used on the project, GDOT must follow the Plan Development Process (PDP) per the oversight agreement with Federal Highway Administration (FHWA).
(click 2) The final design phase usually begins after PFPR inspection has been held and the PFPR report with responses has been accepted.
(click 3) During the final design phase, once the ROW plans are approved, any changes to the construction plans that increase or decrease the required ROW or easement should be avoided, if possible.

## Slide 8
ROW Auth
Prepare NEPA reeval
Finalize plans
Corrected FFPR
NEPA
re-eval approval
Let1
1 These steps do not apply to a Local Let project.
FFPR
Final Design Phase (ROW Authorization to Let)
ROW Acquisition
ENV Cert
CST Auth1
Utility Cert
ROW Cert
Detailed CST Cost Est1
2nd Utility Submission
Final Plans
Notes: This slide is a simplified version of the Final Design PDP flowchart from after ROW Authorization to Let.
(click 1) ROW acquisition begins after the funds have been authorized.
(click 2) While ROW acquisition is in progress, the design plans are being finalized.
(click 3) The 2nd Utility submission process is occurring during the final design process.
(click 4) Based on these plans, the NEPA document and special studies (ecology, archaeology, history, air, & noise) are re-evaluated to ensure that what was previously approved is still valid and that impacts have not changed, or the change(s) have been documented.
(click 5) After the project has been certified for environmental, ROW, and utilities, the construction funds can be authorized.
(click 6) A final detailed CST cost estimate is prepared based on the final plans.
(click 7) The funds for construction are authorized after the final plans are prepared, the 3 certifications are received, and the detailed CST cost estimate is prepared.
(click 8) After CST Authorization, the project is advertised and then it can be awarded (aka let) to the lowest qualified bidder.

## Slide 9
Final Plans
CFFPR
FFPR
Final Field Plan Review
FFPR inspection is an opportunity to review the proposed final plans.
Notes: (click 1) FFPR inspection is held to provide an opportunity for all subject matter experts (SMEs) to review the proposed final plans and provide written comments. This is a first review of the plans that will be provided to the contractor for construction. It is held before corrected FFPR plans and final plans are submitted.

## Slide 10
Plan Development Process: Final Design
Final Design
FFPR inspection
FFPR Request
ROW Authorization (if applicable)
PM Milestone
Notes: (click 1) FFPR Request is a milestone that must be submitted per the baseline date.

## Slide 11: Final Field Plan Review (FFPR)
The focus of the review is to ensure that the design has continued in a direction that:
Meets the Need & Purpose
Check that PFPR responses were done
Request 28 weeks before Let
Notes: The focus of the final field plan review is to ensure that the design has continued in a direction that:
(click 1) Satisfies the purpose and need of the project. Remember that the scope of the design is still based on what was approved in the concept report.
(click 2) This is a 2nd review for the SMEs to ensure that specifications and commitments are being incorporated into the plans.
(click 3) The FFPR meeting (aka inspection) is to be held no later than 24 weeks before Let. The PM should request FFPR no later than 28 weeks before Let.

## Slide 12: FFPR Request
PM needs to prepare the “FFPR Request Letter”
  Letter is online under the Program Delivery folder.
PM and Designer need to fill out the “Final Field Plan Review (FFPR) Checklist”
  Checklist is online on Design Related Resources page in the Additional Resources box.
Notes: (click 1) PM needs to prepare the “FFPR Request Letter”. The letter is located online under the Program Delivery folder.
(click 2) PM and Designer need to fill out the “FFPR Checklist”. The checklist is located online on Design Related Resources page in the Additional Resources box.

## Slide 13: FFPR Responsibilities: Office of Engineering Services
PDP Section 6.6.4
Conducts Review of Final Plans
Schedules FFPR Meeting
Reviews & Accepts FFPR Report
Prepares Final FFPR Report
FINAL
Prepares Draft FFPR Report
DRAFT
Notes: (click 1) The Office of Engineering Services will schedule the FFPR meeting after they have reviewed the FFPR package for completeness.
(click 2) The Office of Engineering Services will conduct the review of the plans and solicit comments from other SMEs.
(click 3) Then Engineering Services will prepare the draft set of comments which will be used as discussion points at the FFPR inspections.
(click 4) After the FFPR meeting, the draft FFPR report is updated and finalized before returning the FFPR report to the PM.
(click 5) The PM submits the FFPR report back to Engineering Services with the designer’s responses to the comments. These are the written commitments that must be addressed before the plans are ready for final field plan review. Accepted means that the responses to the comments have been approved by the Office of Engineering Services.

## Slide 14: Final Design Phase – FFPR Reports
PDP Section 7.7
Draft FFPR report
Final FFPR report
Accepted FFPR report
Notes: There are 3 different versions of the FFPR report. It is important for the PM to understand each version and when it occurs in the design process. (next slide will explain each version)

## Slide 15
Final FFPR Report
FFPR Request
FFPR Inspection
Draft FFPR Report
Final Design (FFPR Process)
Accepted FFPR Report
  Final FFPR report ≠ Accepted FFPR report
Office of Engineering Services
PDP Section 7.7
FFPR responses due
2 weeks after
Notes: (click 1) After the PM requests FFPR, a draft FFPR report is provided with comments that will be discussed at the FFPR inspection (aka meeting). The draft FFPR report is provided to the PM and SMEs prior to the FFPR inspection.
The final FFPR report is provided to the PM within a few days after the FFPR inspection. The final report contains the final set of comments based on the review of the final plans.
The PM will submit the FFPR report back to Engineering Services with the designer’s responses. The accepted FFPR report is the final FFPR with the designer’s responses to the comments. The FFPR responses must be accepted by the Office of Engineering Services. The final FFPR report is not the same as the accepted FFPR report.
(click 2) The FFPR report with responses is due back to Engineering Services within 2 weeks of receiving the final FFPR report.

## Slide 16: FFPR Report Responsibility: PM
Coordinate with Designer
Review FFPR Report for Missing Responses or PM Commitments
Submit
Responses to Engineering Services
Distribute Accepted FFPR Report
Responses due in
2 weeks
PDP Section 7.7.4
Notes: (click 1) When the PM receives the final FFPR report, the PM must coordinate with the designer for the responses.
(click 2) The designer will submit the FFPR report with the responses back to the PM. The PM must review the responses to ensure that no comments were missed or if there are commitments for the PM, the PM is aware of these.
(click 3) The PM submits the FFPR report with responses back to Engineering Services. Don’t forget that this must be done within 2 weeks of receiving the final FFPR report.
(click 4) Once the FFPR report is accepted, the PM is responsible to distribute the report via email.

## Slide 17: FFPR Report Steps
Once accepted, the PM will distribute the accepted FFPR report with responses via email.
  No submission letters are required.
PDP Section 7.7.4
Office of Engineering Services
PM
Designer
Eng Srvc
PM
2 weeks
Notes: Bullet 1: After the FFPR meeting (aka inspection) is held, Office of Engineering (OEngS) will provide the report to the PM. The PM will forward the report to the designer. After the designer provides responses to the comments, the report will be submitted back to the PM. The PM will then submit the report back to Engineering Services for review and acceptance.
PM will submit the report with responses to OEngS for review via email back to the reviewer. The report with responses is due within 2 weeks of receiving the report from OEngS.
(click 2) Once accepted, the PM will distribute the accepted FFPR report with responses via email. No submission letters are required.

## Slide 18: FFPR Report and Final Plan Updates
After the report is considered ACCEPTED:
The plans and other appropriate documents will be modified, where necessary, to address the issues discussed at the FFPR.
A project will not be considered ready to let until all FFPR comments are addressed to the satisfaction of the State Project Review Engineer.
PDP Section 7.7.4
Notes: (click 1) After the Office of Engineering Services accepts the FFPR responses, the report is considered accepted and the GDOT PM will distribute it. No changes to the report can be made after it is accepted by the Office of Engineering Services. The final plans and other appropriate documents will be modified, where necessary, to address the issues discussed at the FFPR.
(click 2) A project will not be considered ready to let until all FFPR comments are addressed to the satisfaction of the State Project Review Engineer.

## Slide 19: FFPR Review
How many versions of the FFPR report are there?
2
3
4
5
  Draft FFPR report –prior to FFPR
  Final FFPR report –updated based on FFPR discussion
  Accepted FFPR report – includes responses to the comments.
Notes: (direction: Read question 1 and give participants time to respond. )
(click 1) Answer: B - There are 3 versions of the report. This is the same process that the PFPR report follows.

## Slide 20: FFPR Review
How long does the PM have to submit the responses to the FFPR comments?
  2 weeks
  4 weeks
  8 weeks
  30 days
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: A - The PM must remember that they have 2 weeks to return the FFPR report with the responses back to Engineering Services. This is half of the time that the PM has for the PFPR responses.

## Slide 21: FFPR Review
What office issues/approves the Accepted FFPR report?
  Office of Environmental Services (OES)
  Office of Engineering Services (EngSrvc)
  Office of Design Policy & Support (DPS)
  Office of Program Delivery (OPD)
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: B

## Slide 22: FFPR Review
Who is responsible to distribute the Accepted FFPR report?
  GDOT PM
  Designer
  Office of Engineering Services
  It is automated
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: A - As a PM, you need to know this. If Engineering Services sends the PM an email stating that the FFPR report is accepted, this should trigger the PM to distribute the report even if Engineering Services does not tell the PM to do this.

## Slide 23
Final Plans
CFFPR
FFPR
Corrected FFPR
Implement all FFPR comments
Reviewed to ensure that all changes agreed to in the FFPR report have been implemented
Due no later than 18 weeks before Let.
Follow the Letting Schedule Calendar not P6 BL dates
Due 18 weeks before let
Notes: (click 1) The designer will implement all FFPR comments. These updated plans are known as the corrected FFPR (CFFPR) plans.
(click 2) The Office of Engineering Services will review the CFFPR plans to ensure that all changes per the FFPR report have been implemented.
(click 3) The CFFPR plans are due 18 weeks before let. After FFPR, follow the letting schedule calendar and not the P6 baseline dates.

## Slide 24
Final Plans
When all comments have been addressed and resolved, the final plans for construction are submitted.
Final Plans is due no later than 10 weeks before Let.
Follow the Letting Schedule Calendar not P6 BL dates
Final Plans
CFFPR
FFPR
Due 10 weeks before let
Notes: (click 1) When all comments have been addressed and resolved, the final plans for construction are submitted.
(click 2) The final plans are due 10 weeks before let. For the final plans be sure to follow the due dates as stated on the Letting Schedule calendar. Do not follow P6 for these dates.

## Slide 25: 3 Steps of Final Plans
FFPR
Corrected FFPR
Final Plans
First opportunity for review comments.
Final plans updated based on FFPR comments.
Final version that will be provided to the contractor for construction.
Notes: (click 1) The final plans are submitted with the FFPR package. These plans are reviewed by the Office of Engineering Services as well as other GDOT SMEs. It is the first opportunity to review and provide input on the final plans.
(click 2) The final plans are updated to address the comments and commitments made at FFPR. The Office of Engineering Services will review the plans against the accepted FFPR report to ensure that all issues and comments have been addressed.
(click 3) Once all of the FFPR comments have been addressed or resolved, the plans are ready for construction. This is the final plan set and will be included with the bid advertisement for construction.

## Slide 26: After PM Requests FFPR, follow Letting Schedule NOT P6
PM responsible tasks
Example dates for a January 2024 Let
Notes: (click 1) After PM requests FFPR, PM must follow the Letting Schedule NOT the P6 schedule.
(click 2)The green highlights are submissions that the PM is responsible for on the letting schedule.
(click 3) The pink boxes are corresponding dates if the project was letting in January 2024. These are the dates that must be met to keep the project letting on time.
[Note: Letting Schedule is available on the Bidding Administration’s office webpage. It is located under the Resources box. A new schedule does not come out until approximately September each year.]

## Slide 27: CFFPR Review
  CFFPR plans are preliminary design plans that incorporate some of the revisions as identified during the FFPR inspection.
  CFFPR plans are final design plans that incorporate ALL revisions as identified during the FFPR inspection.
True
or
False
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: False

## Slide 28: CFFPR Review
Where does the PM find the CFFPR due date?
  CFFPR letter
  Letting Schedule Calendar
  P6 BL date
  18 weeks before let
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: B - Although, the CFFPR plans should be submitted no later than 18 weeks before let, the PM should follow the date on the letting schedule calendar.

## Slide 29: Corrected FFPR
PDP Section 7.7.4
  Submission due date is based on the Letting Schedule Calendar not P6.
  NOTE: Be sure to print out the AASHTOWare 411 cost estimate before turning over the control.
Prepare the “Corrected FFPR Plans Submission Letter”
CFFPR checklist
Notes: (Click 1) Next, we will look at the template letter for the CFFPR submission. PM will prepare the “Corrected FFPR Plans Submission Letter”. The template is located online under Program Delivery.
(click 2) The submission due date is based on the Letting Schedule Calendar not P6.
(click 3) The letter outlines the items that are needed to be submitted with the letter. This is the checklist for CFFPR. Unlike the PFPR and FFPR requests, there is not a separate checklist.
(click 4) PM must coordinate with designer to have AASHTOWare control turned over to the Office of Engineering Services. AASHTOWare is the cost estimating software that the designer uses to determine the estimated construction cost.
(Click 5) NOTE: The GDOT PM should print out the AASHTOWare 411 cost estimate before turning over the control. This copy will be part of the CFFPR submission package. 411 is printed prior to giving Engineering Services control because Engineering Services will zero out all costs. This will prevent a potential contractor from seeing what cost they should use to bid on the project.

## Slide 30: Final Plans: Detailed Cost Estimate
The CFFPR plans will trigger the preparation of the engineer’s detailed cost estimate for CST fund authorization.
  This cost estimate is prepared by the Office of Engineering Services.
  PM does not need to take any action for this.
PDP Section 7.8.2
Notes: (click 1) The CFFPR plans will trigger the OEngS to prepare the Engineers Estimate. The estimate is utilized by the Office of Financial Management for requesting authorization of construction funds to let the project.

## Slide 31: Final Plans
Final plans for letting are submitted after CFFPR plans have been reviewed.
  Due 10 week before let.
  Follow the Letting Schedule Calendar.
Note: After CFFPR, the PDP steps does not apply to local let projects.
PDP Section 7.8.2
Notes: (click 1) After the CFFPR plans have been submitted, the final plans for letting can be submitted. Per the letting schedule, the final plans are due to the Construction Bidding Administration 10 weeks before let.
(click 2) Note: These steps does not apply to local let projects after CFFPR is submitted.

## Slide 32: Final Plans
  Checklist: Under Design Related Resources in the Bidding Administration Folder.
PM to fill out
PM & Designer to complete the “Designer’s Checklist for Plan Submittal”
Notes: (click 1) PM & Designer to complete the “Designer’s Checklist for Plan Submittal”. The checklist is located online under Design Related Resources in the Bidding Administration Folder.
(click 2) The PM, not the designer, will fill out Section Q. The District Utility coordinator for the project will provide the files to the PM. The PM will then add the information to this table.

## Slide 33: Final Plans
  Submission due date is based on the Letting Schedule Calendar not P6.
Final plans package checklist
Prepare the “Final Plan Submission Letter”
Notes: (click 1) PM to prepare the “Final Plan Submission Letter”. The template is located online in the Program Delivery folder.
(click 2) Submission due date is based on the Letting Schedule Calendar not P6.
(click 3) The letter contains a list of items that the final plans package must contain, including the designer’s checklist. However, depending on the project some of the items listed may not be applicable and should be removed from the list.

## Slide 34: Final Design Plans Review
What are the 3 important sets of plans developed during the final design phase? (in chronological order)
  PFPR plans, ROW plans, FFPR plans
  Draft plans, CFFPR plans, Final plans
  FFPR plans, CFFPR plans, Final plans
  Draft FFPR report, Final FFPR report, Accepted FFPR report
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: C - The question is asking about the final design plans.

## Slide 35
ROW Auth
Prepare NEPA reevaluation
NEPA
re-evaluation approval
Let1
Purchase ROW
Environmental Process
(ROW Authorization to Let)
Final Design
ENV Certification
Graphic representation only - Not to exact calendar timeline
Notes: Now we will focus on the environmental process. This graphic assumes that there was ROW authorization which implies that the NEPA or GEPA document was already approved.

## Slide 36
Prepare NEPA re-eval
NEPA
Re-eval approval
Let1
Environmental Process (PFPR to Let – No ROW)
Final Design
Preliminary Design
PFPR
Technical Studies Complete
FFPR
NEPA doc approved
Graphic representation only - Not to exact calendar timeline
Environmental Certification
Notes: If the project does not have required ROW or easements needed, then the NEPA document would need to be approved prior to FFPR being requested.

## Slide 37
Environmental Process
(ROW Authorization to Let)
Required for any projects with environmental resources.
Within the boundaries of the resource, the design is LOCKED and cannot be changed.
Permit applications (if needed) are based on these plans.
ENV Lockdown Plans
Occurs 31 or 38 weeks before Let
FFPR
Final Design
Notes: (click 1) Lockdown plans are required for any projects with environmental resources.
(click 2) Within the boundaries of the resource, the design is LOCKED and cannot be changed.
(click 3) Permit applications (if needed) are based on these plans.

## Slide 38
Update Special Studies
Environmental Process
(ROW Authorization to Let)
All of the special studies reports are updated (re-evaluated) based on the accepted FFPR report and lockdown plans.
ENV Lockdown Plans
FFPR
Final Design
Graphic is not an accurate time reference – follow P6
Notes: (click 1) The lockdown plans are needed for the preparation of the updated special studies. The reports are re-evaluations of the previously approved special studies. The updated special studies are started when the lockdown plans are received but not submitted until after FFPR has been held. This helps to ensure no changes were made to the lockdown plans which would then change the updated special studies reports.

## Slide 39
Update Special Studies
NEPA
re-evaluation
approval
Environmental Process (ROW Authorization to Let)
ENV Lockdown Plans
FFPR
After the updated special studies are approved, the NEPA re-evaluation document is prepared and approved by FHWA.
Final Design
Notes: (click 1) After the updated special studies are approved, the NEPA re-evaluation document is prepared and approved by FHWA.
(click 2) Note: GEPA projects (under $100 mil) can certify after technical studies are complete.

## Slide 40
Update Special Studies
NEPA
re-eval
approval
Environmental Process (ROW Authorization to Let)
ENV Cert for Let
ENV Lockdown Plans
FFPR
After the NEPA document is approved, the project can be environmentally certified for let.
Due 11 weeks before let
31 or 38 weeks before let
Notes: (Bullet 1) After the NEPA document is approved, the project can be environmentally certified for let.
(click 3) Environmental certification is due 11 weeks before Let.

## Slide 41: (Environmental) Lockdown Plans
Lockdown plans are prepared before FFPR request.
Lockdown plans are required to either:
  Show that the impacts to resources have not changed; or
  Provide the finalized impact information.
Lockdown Plans for Permits
FFPR
Final Design
Notes: (click 1) Lockdown plans are prepared before the FFPR request. This is because lockdown plans are needed no later than 31 weeks before let. The FFPR request is due no later than 28 weeks before let. However, the PM should follow the P6 schedule.
(click 2) Lockdown plans are required to:
Show that the impacts to resources have not changes; or
Provide the finalized impact information. The plans are used to prepare the permit. No design changes that would impact a resource can be made to the plans after this submission. There can be plan edits after this submission if the changes do not alter the known impact(s) to a any of the environmental resources.

## Slide 42: (Environmental) Lockdown Plans
Lockdown plans are due to OES either 31 or 38 weeks before let.
  31 weeks:
    Section 404 permit [Regional Permit (RP) or Nationwide Permit (NWP)]
    Georgia Buffer Variance (BV).
  38 weeks:
    Section 404 permit [Individual Permit (IP)]
  Submit “Environmental Lockdown Plans Submission” letter to OES.
Notes: (click 1) Lockdown plans are due to OES either 31 or 38 weeks before let.
(click 2) 31 weeks prior if the Section 404 permit is a Regional Permit (RP), Nationwide Permit (NWP) or if it is a Georgia Buffer Variance (BV). Section 404 permit is for impacts to waters of the US (streams, wetlands, marsh, ponds/lakes). The BV is for impacts to the protective zone (aka buffer) around streams and lakes.
(click 3) 38 weeks prior if the Section 404 permit is an Individual Permit. This is for projects with significant impacts to waters of the US. This is not usually needed for the safety and ops program.
(click 4) PM to submit “Lockdown Plans for 404 Permit” letter to the Office of Environmental Services. The template is located online under Design Related Resources in the Program Delivery folder. The letter is used for both the Section 404 permit and the buffer variance permit.

## Slide 43: NEPA Re-evaluations
NEPA re-evaluations are needed to certify for Let.
  All special studies will have an updated report or memo to identify any changes (or no changes).
  Then the NEPA Re-evaluation is prepared and approved by FHWA.
Note: The re-evaluations are based on the lockdown plans.
Notes: (click 1) If the project has an approved NEPA document, then NEPA re-evaluations are needed to certify construction funds for let.
(click 2) All special studies (ecology, archaeology, history, air, and noise) will have an updated report or memo to identify any changes (or no changes) since the approved technical studies report was completed.
(click 3) After the updated special studies are approved, an updated NEPA document (aka NEPA Re-evaluation) is prepared and approved by FHWA.
(click 4) Note: The re-evaluations are based on the lockdown plans.

## Slide 44: NEPA Re-evaluations
(Consultant) NEPA re-evaluation document:
  Submitted from consultant to OES.
  No letters or emails are needed.
(In-house) NEPA re-evaluation document:
  Submit “Project Changes & Revised Request to Assess Project Impacts” form (on OES website)
Notes: (click 1) The consultant submits the re-evaluations to the OES reviewer directly. No letters or emails are needed from the PM.
(click 2) If the NEPA document will be completed in-house, no letters or emails are needed from the PM. However, the PM will need to fill out and submit a project changes &revised request to assess project impacts form which is located on the OES office website under the resources box.

## Slide 45: NEPA Re-evaluations
Approval of the NEPA re-evaluation document will trigger OES to certify for Let.
  No action is needed by the PM.
Notes: (click 1) Approval of the NEPA document will trigger OES to certify for Let. No action is needed by the PM.

## Slide 46: NEPA Re-evaluations
For accelerated schedule projects or projects without ROW, the same process would apply to the NEPA document approval.
  NEPA would need to be first approved prior to FFPR.
  NEPA re-evaluation would be approved after FFPR.
Notes: (click 1) Note: For accelerated schedule projects or projects without ROW, the same process would apply to the NEPA document approval. NEPA would need to be approved prior to FFPR being requested. A NEPA re-evaluation would be required after FFPR was held.

## Slide 47: Environmental Review
If a project has an approved NEPA document, when does the NEPA document re-evaluation take place?
  After FFPR
  Before FFPR
  After Lockdown Plans
  A & C
Notes: (direction: Read question 1 and give participants time to respond. )
(click 1) Answer: D

## Slide 48: Environmental Review
What triggers the environmental certification for Let?
  PM contacting OES
  Lockdown Plan submission
  Approval of the NEPA re-evaluation
  CST fund authorization
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: C

## Slide 49: Environmental Review
Before environmental permits can be prepared, what is needed? (HINT: Permits are based on this.)
  Lockdown plans
  Updated technical studies
  NEPA re-evaluation
  FFPR plans
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: A

## Slide 50: Environmental Review
How many weeks before Let are lockdown plans required?
  Either 10-weeks or 18-weeks prior to Let
  After FFPR but before CFFPR.
  Either 24-weeks or 28-weeks prior to Let.
  Either 31-weeks or 38-weeks prior to Let.
  The level of permit will determine the timeframe.
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D

## Slide 51
ROW Auth
Let1
Final Design
1 These steps do not apply to a Local Let project.
Final Design Phase
(ROW Authorization to Let)
ROW Acquisition
ROW Cert
Notes: Now we will focus on the ROW acquisition.

## Slide 52
ROW Cert
ROW Process (ROW Authorization to Let)
Once all parcels have been acquired, the project will receive a ROW certification.
  No action is required by the PM.
Per the Letting Schedule Calendar, ROW certification is due 11 weeks before Let.
ROW Acquisition
Due 11 weeks before let
Notes: (click 1) This is a high-level overview of the ROW process. Once all parcels have been acquired, the project will receive a ROW certification. No action is required by the PM to certify for ROW.
(click 2) Follow the Letting Schedule not P6. The certification is always due 11 weeks before let.

## Slide 53
ROW Cert
If there isn’t any ROW on the project, the project must still get a No Required ROW certification.
  The PM will be contacted by the ROW office to fill out and sign the N/R ROW certification.
Per the Letting Schedule Calendar, ROW certification is due 11 weeks before Let.
No ROW Acquisition
Due 11 weeks before let
ROW Certification (No ROW)
Notes: (click 1) If there isn’t any ROW on the project, the project must still get a No Required ROW certification. The PM will be contacted by the ROW office to fill out and sign the no required ROW certification.
(click 2) Follow the Letting Schedule not P6. The certification is always due 11 weeks before let.

## Slide 54: Right of Way Review
All parcels need to be acquired prior to ROW certification.
True
or
False
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: True

## Slide 55: Right of Way Review
All projects require ROW certification.
True
or
False
All projects either have a ROW certification or a N/R ROW certification.
Notes: (direction: Read question 1 and give participants time to respond. )
(click 1) Answer: True

## Slide 56
ROW Auth
Final Plans
Finalize plans
Corrected FFPR
Let1
1 These steps do not apply to a Local Let project.
FFPR
Utility Process (ROW Authorization to Let)
2nd Utility Submission
Utility Certification
Notes: Next, we will focus on the utility process during final design.

## Slide 57
2nd UTL Submission
FFPR
Utility Coordination: 2nd UTL Submission
Purpose: Coordinate with the Utility Owners and receive input regarding the proposed relocation of utilities.
Required for FFPR plans
Notes: (click 1) The purpose of the 2nd Utility (UTL) submission is to coordinate with the Utility Owners and receive input regarding the proposed relocation of utilities.
(click 2) The plans for FFPR cannot be finalized until the information from 2nd UTL submission is incorporated.

## Slide 58
UTL Process (ROW Authorization to Let)
2nd UTL submission triggers the utility companies to prepare and submit utility permits and utility adjustment schedules.
2nd UTL Submission
UTL Permits & UASs
Notes: (click1) 2nd UTL submission triggers the utility companies to prepare and submit utility permits and utility adjustment schedules.

## Slide 59
UTL Process (ROW Authorization to Let)
After all permits and UASs are received and approved, the project can be utilities certified for Let.
Note: If the project involves a railroad, the project cannot be certified until railroad coordination is complete.
2nd UTL Submission
UTL Permits & UASs
UTL Cert
Due 11 weeks before let
Notes: (click 1) After all permits and UASs are received and approved, the project can be certified for utilities.
(click 2) Follow the Letting Schedule not P6. The certification is always due 11 weeks before let.
(click 3) Note: If the project involves a railroad, the project cannot be certified until railroad coordination is complete with the railroad company.

## Slide 60: 2nd Submission Utility
1st submission (verification)
2nd submission
PFPR
FFPR
Notes: (click 1) If a project has 1st Submission or 1st Verification for Utilities, it will have 2nd Submission Utilities.

## Slide 61: 2nd Submission Utility
2nd Submission Utilities is when the utility companies review the plans for proposed utility relocations.
  Provide back mark ups on the plans; or
  No conflict letter is sent.
Notes: (click 1) 2nd Submission Utilities is when the utility companies review the plans for the proposed utility relocations.
(click 2) The utility companies either provide back mark ups because something designed is now in conflict with their utility; or
(click 3) The utility company agrees with the design and sends a no conflict letter to GDOT.

## Slide 62: Utility Certification
Utility Certification occurs after 2nd Submission is complete.
  No action is required by the PM to certify the utilities for let.
Notes: (click 1) UTL certification occurs after 2nd submission is complete. This means that all UTL companies have responded. No action is required by the PM to certify the utilities for let.

## Slide 63: Final Plans: Utility Permits
District UTL office will provide:
  No Conflict letters
  Approved UTL permits
  Utility adjustment Schedules (UASs)
  Failure to Submit (FTS) letters (if needed).
  PM will need these for the final plans submission.
Notes: (click 1) District UTL office will provide the PM with copies of the no conflict letters, approved UTL permits and UASs and/or the Failure to Submit (FTS) letters.
(click 2) The PM will need these for the final plans submission. If the District UTL coordinator does not provide the UTL permits, UASs, and/or FTS letters, then the PM should ask for them.

## Slide 64: Utility Review
2nd UTL submission occurs after FFPR.
  Before FFPR – the information regarding utility relocation is incorporated into the final design plans
True
or
False
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: False

## Slide 65
ROW Auth
Detailed CST Cost Estimate1
Let1
1 These steps do not apply to a Local Let project.
Final Design Phase:
CST Authorization
ENV Cert
ROW Cert
Utility Cert
CST Auth1
Final Plans
Notes: Now we will focus on CST Authorization.

## Slide 66: Construction Authorization
The following are required to authorize the CST funds:
  Environmental Certification
  Utility Certification
  ROW Certification
CST
Auth
ENV Cert
UTL Cert
ROW Cert
Notes: The following are required in order to authorize the use of the construction funds:
(Click 1-3): Environmental Certification; Utility Certification; ROW Certification;

## Slide 67: Construction Authorization (cont.)
The following are required to authorize the CST funds:
  Final Plans
  Engineer’s Cost Estimate
CST
Auth
7 weeks before let
ROW Cert
Detailed CST Cost Est.
UTL Cert
ENV Cert
Final Plans
Notes: [continued from previous slide]
(Click 1-2): final plans, and Engineer’s Cost Estimate. The cost estimate is prepared by the Office of Engineering Services. Only that office has access to see the final cost estimate.
(click 3): Per the letting schedule, CST funds are to be authorized 7 weeks before let.

## Slide 68: Construction Authorization Review
What certification(s) is/are required for CST Authorization?
  2nd Submission, ENV, ROW
  UTL, Lockdown Plans, ROW
  ENV only
  ENV, UTL, ROW
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D

## Slide 69: Construction Authorization Review
Which item is NOT needed to authorize the CST funds?
  Certifications
  Detailed ROW Cost Estimate
  Final Plans
  Detailed Engineer’s Cost Estimate
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: B - To authorize construction funds, all GDOT let projects require 3 certifications, final plans, and a detailed engineering cost estimate.

## Slide 70: What Is Needed If Plans Change After Final Plan Submission?
Notes: Sometimes, there may changes to the plans that are not ready until after the final plans have been submitted. This should try to be avoided, but if it cannot, then a plan revision is required. The next few slides will discuss the various types of plan revisions.

## Slide 71: Plan Revisions: Revision, Amendment, and UOC
PM is responsible for submitting plan revisions after final plans have been submitted.
There are 3 categories for revisions:
  Revision prior to Advertisement
  Revision by Amendment
  Use on Construction (UOC) Revision
Notes: (click 1) PM is responsible for submitting plan revisions after final plans have been submitted.
(click 2) There are 3 categories for revisions: 1) revision prior to advertisement. 2) revision by amendment, 3) use on construction revision.

## Slide 72: Plan Revisions: Revision, Amendment, and UOC
Revision prior to Advertisement (to CBA)
  Changes to plans that are submitted no later than 6.5 weeks prior to letting
  No later than 7.5 weeks prior to letting for PODI projects
PDP Sections 7.10.1, 7.10.2, & 8.2.5
Final Plans
Let
Advertise project
Revision
6.5 weeks
Notes: (click 1) Revision prior to Advertisement are submitted to the office of construction bidding administration.
This revision is for changes that are submitted no later than 6.5 weeks prior to letting.
If it is a PODI (projects of division interest) project, the revision is submitted no later than 7.5 weeks prior to let.

## Slide 73: Plan Revisions: Revision, Amendment, and UOC
Revision by Amendment (to CBA)
  Changes to plans that occur from 6.5 week to 10 calendar days before letting
PDP Sections 7.10.1, 7.10.2, & 8.2.5
Final Plans
Let
Advertise project
Revision
Amendment
6.5 weeks
10 days
Notes: (click 1): Revision by Amendment are submitted to the office of construction bidding administration. These changes will be an amendment to what is being posted as the bid package.
Revisions by Amendment are changes to plans that occur from 6.5 week to 10 calendar days before letting.

## Slide 74: Plan Revisions: Revision, Amendment, and UOC
Use on Construction (UOC) Revision (to contractor)
  Changes to plans that occur 9 days before letting or anytime during construction
PDP Sections 7.10.1, 7.10.2, & 8.2.5
Final Plans
Let
Advertise project
Revision
Amendment
UOC
6.5 weeks
10 days
Notes: (click 1): Use on Construction or UOC revisions are submitted directly to the contractor. Note: If NTP has not been issued to the contractor, the PM must “hold” onto the UOC until NTP has been issued.
These are plan changes that occur 9 days before letting or anytime during the construction phase.

## Slide 75: Plan Revisions: Revision, Amendment, and UOC
Revision prior to Advertisement
  PM to complete “Revised Final Plans (Bidding)” letter
Revision by Amendment
  PM to complete “Amendment” letter
UOC
  PM to complete “Use on Construction Letter”
Prior to any plan changes, PM must coordinate with OES and District UTL office.
Let
Advertise project
Revision
Amendment
UOC
6.5 weeks
10 days
Final Plans
Notes: (click 1) The Revised Final Plans letter is required for Revision prior to Advertisement submission.
(click 2) The Amendment letter is required for the Revision by Amendment submission.
(click 3) The Use on Construction letter is required for the UOC submission.
(click 4) Prior to any plan changes, PM must coordinate with OES and District UTL office to ensure that changes do not trigger additional coordination or report updates.

## Slide 76: Construction Phase
After the contractor has been awarded the project and the NTP has been issued, the PM must notify the property owners that construction is starting.
  Prepare and mail “Property Owner CST Notification Letter”
Notes: (click 1) After the contractor has been awarded the project and the NTP has been issued, the PM must notify the property owners that construction is starting.
(click 2) PM must prepare and mail “Property Owner CST Notification Letter”. Do not mail the letter until the contractor has NTP.

## Slide 77: Revised Final Plans Review
Plans can be revised after the Final Plans are submitted.
  This should be avoided if possible.
True
or
False
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: True

## Slide 78: Revised Final Plans Review
Which is not a type of final plan revisions?
  Revision prior to Advertisement
  Revision by Amendment
  Use on Construction (UOC)
  L&D Advertisement
Notes: (direction: Read question 1 and give participants time to respond.)
(click 1) Answer: D

## Slide 79: Templates Used Between ROW Authorization and Let
The following is a list of potential templates that may be needed for a project:
FFPR Request
Corrected FFPR Plans Submission Letter
Final Plans Submission Letter
Environmental Lockdown Plan Submission
Revised Final Plans Letter
Amendment Letter
Use on Construction Letter
Property Owner CST Notification Letter
Notes: These are just a list of potential templates that may be required between ROW authorization and Let. There may be other submissions needed that are not listed. These are just the most common templates that this program uses.