## Slide 1: Preconstruction Status Report
09.18.2025
Office of Program Delivery
Notes: This training is going to cover the various informational components of the Preconstruction Status Report (PSR). we will focus on the purpose of the PSR, what information a PM is responsible to maintain, and how to interpret the information on the PSR.
Training Materials: PSR example PI 0013724 & PSR A for the exercises during this presentation.
Training Time: 1.5 hours

## Slide 2: What is the purpose of a PSR?
A communication tool for GDOT
executive management to get a
quick snapshot of the project
when they are coordinating with
stakeholders and politicians.
Notes: What is the Purpose of a PSR? (ask for audience responses)
(bullet 1) A communication tool for GDOT executive management to get a quick snapshot of the project when they are coordinating with stakeholders and politicians.

## Slide 3: The purpose of the PSR is NOT…
To be a project management tool.
Notes: The purpose of the PSR is NOT…
(click 1) to be a project management tool. When preparing the PM notes, keep in mind that this is for GDOT mgmt. to read and have a quick understanding of the project status.

## Slide 4: Who is the Audience for the PSR?
GDOT Executive Management
Notes: Who is the audience for the PSR? (ask for participant responses)
(bullet 1) GDOT Execute Management

## Slide 5: PSRs are very Important!
PM Compliance Metric
Funding decisions
Balance lettings
Commitments to politicians, government officials, and citizens
Communicates to SMEs
Notes: (bullet 1) Keeping PSRs current and accurate is a metric for a project manager.
(bullet 2) GDOT uses the information on the PSR to make funding decisions.
(bullet 3) GDOT management makes decisions to move let dates to keep fiscally balanced. For example, if a project is ahead of schedule, it may be given an early let date to offset a project that cannot make it’s let date.
(bullet 4) GDOT uses the information to make commitments to politicians, government officials, and citizens.
(bullet 5) PSRs communicate with SMEs about the status of the project. It helps them to prioritize their workload.

## Slide 6: What is the most important thing for the PM to remember about the PSR?
It must always represent an accurate picture of the status of the project, up to date, and is written for GDOT management who may not be familiar with the project.
Notes: What is the most important thing for the PM to remember about the PSR?
(bullet 1) It must always represent an accurate picture of the status of the project, up to date, and is written for GDOT management who may not be familiar with the project.

## Slide 7: Individually take 2 minutes to look at a PSR and identify the areas (use PSR example 0013724)
Which sections of the PSR must be completed by the PM?
Notes: Which sections of the PSR must be completed by the PM? (Ask each participant to review PSR Example 0013724 and take 2 minutes to identify all of the areas. We will discuss them after the 2 minutes is up and using the next slide.)

## Slide 8
OFM
OES – ENV Program Mgr
OES
OFM
OEngS
(if applicable)
Notes: (start with the top of the PSR and review each column one at a time to identify items that the PM can and should update)
(click 1) Project Manager – This should show the name of the current GDOT PM
(click 2) AOHD Initials – for GDOT PMs working under Gresham Smith for the safety and operations program, FORD program, etc. the initials should be GSP. For the GDOT embedded PMs, this should be the Assistant Office Head initials for either the south team or the north team.
(click 3) Office – For our PSRs, this will always be Program Delivery.
(click 4) Consultant – This does not imply that GDOT has hired a consultant. The information is to list who is responsible for designing the project. This could be “No Consultant, In-house Design”, “consultant design (contract with GDOT)”, “Local Design, local PE funds”, etc. In TPro, PM selects from a dropdown menu if it is not already filled in or filled in incorrectly.
(click 5) Concept - This should match the project. What is the basic design going to do? For example, “roundabout”, “signals”, “cable barrier” to name a few. Select from the dropdown menu in TPro.
(click 6) Measure – This should always be “E” for the English measurement system.
(click 7) Design Firm – This lists who is doing the design. It could be the name of a consulting firm, GDOT District X (if in-house), or GDOT Roadway (if in-house).
(click 8) Lighting Type – Fill this out based on the type of lighting that will part of the project. If no lighting, it should say none.
(click 9) Project Manager – These are the PM notes. They must be updated a minimum of every 30 days and follow the TPro guidance for notes. It is not shown on the PSR but there is an OPD PSR version which also shows the ROW/Let PM notes. Those notes cannot be older than 30 days.
(click 10) Design – This is used if the designer is not in-house GDOT. The PM will fill this out to include information about who to contact for project design questions and for the procurement information.
(click 11) P6 – This is a portion of the P6 schedule. The PM is responsible to update the actual start, actual finish and the % complete.
(click 12) Pre Parcel Count – If the project does not have ROW authorized, the PM must ensure that this number matches the plans.
(click 13) Sponsor – It tells management who is responsible for designing the project. It could be GDOT or Local Sponsor. The Office of Financial Mgmt updates this field.
(click 14) ENV Doc Type – This is the environmental document type which is based on the funds for the project. The choices are NEPA or GEPA. Remember that even a penny of federal money on a project will require a NEPA document. The office of environmental services is the only one who can update this. PM should contact the ENV Program Manager.
(click 15) ENV Consultant – Who is performing the environmental work? It will list the name of a consulting firm or in-house, if OES will do the work. Only OES can update this information.
(click 16) Cost estimate date – These dates inform management when the cost estimate for a phase of money was last updated and approved. Unless the funding phase is authorized, the date can never be more than 1 year old. The office of engineering services approves the cost estimates and will update the dates.
(click 17) Acquired by- This is referring to who is responsible to acquire ROW parcels. This can only be updated by OFM.

## Slide 9: When Writing PM Notes, think about the Reader
The PM notes & the ROW/Let PM notes should not:
Use acronyms unfamiliar to GDOT
Include redundant information
Notes: When writing PM notes, think about the reader which is GDOT management.
(click 1) The PM notes and the ROW/Let PM notes should not do the following:
(click 2) use acronyms unfamiliar to GDOT. In other words, not invent your own acronyms.
(click 3) include redundant information. If P6 shows the task activity as complete, do not put it in the PM notes.

## Slide 10: Individually take 2 minutes to look at a PSR and identify the areas (use PSR Example 0013724)
Which AREas on the PSR are cross referenced to determine if the project is on schedule?
Notes: Which areas on the PSR are cross reference to determine if the project is on schedule? (The participants should use PSR 0013724 to identify these areas. Give the participants 2 minutes to identify the information. Then continue to next slide.)

## Slide 11
Notes: (click 1) The schedule let date should be compared to the management let date. The mgmt. let date represents when the project is scheduled to let per P6 or management’s direction. The schedule let date is a projected date based on the actual start date, actual finish date, and/or % complete that has been entered into P6. Based on the inputted information, the schedule let date is determined. If the schedule date is later than the mgmt. let date, then the project may miss the let date. If schedule date is close or earlier than the mgmt. let date, the project is typically on schedule.
(click 2) The PM notes must state if the project is on schedule or not on baseline. The information under this statement should support the statement.
(click 3) The P6 schedule’s actual start and finish dates and/or % complete when compared to the base (aka baseline) dates, will determine if the project is on schedule or not.
(click 4) Under the P6 schedule, summary notes from other offices are provided. These notes should also support the schedule information and the PM notes when determining if the project is on schedule or not.
(click 5) When reviewing the mgmt. let date against the mgmt. ROW date, note how many months difference there are. Then look at the ROW notes under the P6 table. Are there enough months to accommodate acquisition per the ROW notes?

## Slide 12: Individually Take 2 minutes to look at a PSR and identify the areas (use PSR Example 0013724)
What information is provided by the funding box?
Notes: What information is provided by the funding box? (The participants should review PSR 0013724 and list the information that they get from the funding box. Give the participants 2 minutes to review and then go to next slide.)

## Slide 13
Fund Codes indicate if the project is federal, state, or locally funded
  HB170 = state funds
  LOC = local funds
  All Others = federal funds
Notes: (click 1) Look at the codes under the “fund” column.
(click 2) The fund codes indicate if the project is federal, state or locally funded.
(click 3) HB170 stands for House Bill 170. This the bill that provides state funds.
(click 4) LOC stands for local funds.
(click 5) All other fund codes represent federal funds which come from various federal transportation bills.

## Slide 14
Why do some phases have an approved and proposed year, but others do not?
  Lump sum funding does not have approved and proposed years
  Other federal funds are listed in the STIP for a specific FY & funding phase
Notes: (Click 1) Why do some phases have an approved and proposed year, but others do not? (wait for answers)
(click 2) Lump sum funding does not a have a separate approved and proposed years. Think of lump sum as drawing from one large pot of money and not individual accounts. If it is not lump sum, there should be approved and proposed years listed. This is how GDOT balances the budget.
(click 3) Funds that are not Lump Sum are listed in the STIP for a specific phase and project. The funds in the STIP must be approved to be used in a specific Fiscal Year. If the schedule changes and the fiscal year is changing, then the STIP must be modified. Until the modification is approved, it will appear on the PSR as proposed to communicate to GDOT management when the funds are proposed to be used.

## Slide 15
Approved = The project is included in the STIP
Proposed = Schedule has changed but it has not been updated in the STIP yet
Note: State funds are not included in the STIP.
Notes: (Click 1) If there is a date under the approved column, the funds are included in the STIP.
(click 2) The proposed column is to list the anticipated year the funds will be needed due to a schedule change. If the proposed year does not match the approved year, then the STIP has not been updated yet.
(click 3) Note: State funds are not included in the STIP but there will be a proposed year to help GDOT plan the budget by year.

## Slide 16
What does the lump year tell management?
  This is the fiscal year that this money has been allocated to be used.
Notes: (click 1) What does the lump year tell management? (wait for answers)
(click 2) This is the fiscal year that this money has been allocated to be used for that phase of funding. Again, this is how GDOT budgets money.

## Slide 17
How do you know if the lump year is accurate?
Compare it to the Mgmt Let or Mgmt ROW year
If it does not match, notify OTO or Planning.
Including the office that programmed the project on PCRF will trigger this to be updated
Notes: (click 1) How do you know if the lump year is accurate?
(click 2) Compare it to the mgmt. let year or mgmt. ROW year. CST & UTL funds should match year with the Mgmt Let date. ROW funds should match years with Mgmt ROW date.
(click 3) if it does not match, notify office the programmed the funds. This could be the Office of Traffic Operations (OTO) or the Office of Planning. Coordinate with the office that programmed the project.
(click 4) Include the originating office (i.e. OTO, planning or bridge) on the PCRF (project change request form) triggers this to be updates.

## Slide 18
What does STIP stand for?
  State Transportation Improvement Program
What is the STIP?
  Fundng plan for the next four years (current + 3 years)
  Includes MPO TIPs & projects not included in a TIP
Notes: (click 1) What does STIP stand for? (ask for answer)
(click 2) State Transportation Improvement Plan
(click 3) What is the STIP? (ask for answers)
(click 4) It is the statewide plan for the next four years (current year + 3 years).
(click 5) (don’t explain MPO or TIP- will be done on next slide) It includes all MPO TIPs and projects not included in a TIP. In other words, any project planned within the next 4 years and is located anywhere in the state of Georgia.

## Slide 19
Why is the STIP amount for all phases of this project $0.00?
  If authorized = $0.00 (no longer part of the TIP or STIP)
  Lump sum funds are not listed by individual PI #s. Therefore, they are not listed .
    Remember: Lump sum = bucket of money.
Notes: Why is the STIP amount for all phases of this project $0.00? (ask for answers)
(click 1) When a phase is authorized, it changes to $0.00 and is no longer part of the TIP or STIP.
(click 2) Lump sum funds are not listed by individual PI#s. Therefore, they are not listed in the TIP or STIP.
(click 3) Remember that lump sum funds pull from one bucket of money.

## Slide 20
What does TIP stand for and what organization has a TIP?
  Transportation Improvement Program
  MPO
What does MPO stand for and how many people minimum?
  Metropolitan Planning Organization
  Population of at least 50,000
Notes: What does TIP stand for and what organization has a TIP? (ask for answer)
(click 1) (answers to question) Transportation Improvement Plan; MPO
(click 2) What does MPO stand for and how many people minimum are needed to make a MPO? (ask for answers)
(click 3) (answers to question) Metropolitan Planning Organization; Population of at least 50,000

## Slide 21: TPro PM Notes
Notes: Next, we will discuss the TPro PM notes that are displayed on the PSR.

## Slide 22: TPro PM Notes: FORMATS
Within 7 months of Let
LET STATUS
More than 7 months from Let
NOT IN LET STATUS
Notes: There are two formats that PM must follow when writing the PM Notes in TPro.
(click 1) The first format is Not in Let Status. This used for any project that is more than 7 months from the management let date.
(click 2) the 2nd format is Let Status. This is used for any project that is within 7 months of the management let date. For the purpose of this training, we are only going to focus on the Not in Let Status format.
[presenter direction: next slides talk more about Not in Let Status format]

## Slide 23: TPro PM Notes: Projects Not in Let Status
Follow the OPD Template
General Format:
  Scope
  Schedule
  Next Milestone
  Risk/Issue
  Budget
  PM’s initials & date of update
Notes: (click 1) For projects that are not in let status, follow the OPD template.
(click 2) The PM’s notes have the same general format which always includes scope, schedule, next milestone, risk/issue, budget, and the PM’s initials and date the notes were updates. We will discuss the components of this outline in the following slides.

## Slide 24
CR Approved?
Brief Description of Scope
Revised CR needed?
Scope
Status of Schedule? (if not active)
On Schedule or Not on Schedule for BL
If not, why & how many months?
Recovery Plan?
Next Milestone
Schedule
TPro PM Notes: Projects Not in Let Status
Notes: (click 1) When reporting on the scope of the project, it should be relevant to the status of the concept report or state that a concept is not required. These are some of the questions that the information provided by the PM should answer for GDOT management.
(click 2) The next section is about the status of the schedule. GDOT management needs to understand if the project is on schedule or note on schedule and why. This information can impact the Department’s ability to balance the budget by knowing when various funding phases will require money. The schedule and funding are correlated. Plus, this information helps GDOT management to be able to communicate to others outside of GDOT about the timeframe for when the project will be delivered to construction.

## Slide 25
State the risk &
Affected milestone
Risk
PE in-house & contract (remaining funds)
Charge # for personnel
Cost Estimate status/info (only if not updated in TPro yet or no date in TPro)
Budget
TPro PM Notes: Projects Not in Let Status
Notes: (click 1) The risk section is to communicate if there is an issue or activity that was not previously planned for in the schedule. This activity or issue is jeopardizing or potentially jeopardizing the ability of the project to be delivered on schedule. Therefore, it needs to be communicated to GDOT management.
(click 2) The budge section is to notify GDOT management of the status of the Preliminary Engineering (PE) funds as they are being used on the project. It is also to alert management if additional funds will be required for the PE phase. Since GDOT SMEs must charge their work time to a specific project, the notes must include the PI charge number that they will use on their timesheet. Finally, if cost estimates are in the process of being updated/revised and the funds are different from what has previously been approved and planned for, then GDOT management needs to have the new amounts communicated. This will assist GDOT management in the ability to balance the funding and keep projects moving forward.

## Slide 26: TPro Design Field Notes
Notes: Next, we will discuss the PM’s responsibility for maintaining information in the TPro design field.

## Slide 27
Use if NOT being designed by in-house staff
Include:
  designer contact
  local sponsor contact (if applicable)
  contract information (including procurement status)
TPro PM Notes: Design Field Notes
Notes: (click 1) The PM can only use the Design Field if project is NOT being designed in-house. In other words, neither the district design team nor the Office of Roadway Design are responsible for the plan development of the project.
(click 2) In the design field, the PM will provide information for the designer contact, local sponsor contact (if applicable), and contract information, including status of needed or in progress contracts. If in-house is designing the project, then the contract information will be place in the PM Notes.

## Slide 28
General Format:
  Local Sponsor Contact’s name, email, phone #
  Consultant Firm, PM’s Name, email, phone #
  Master Contract info
  Task Order info
  PM’s initials & date notes updated
TPro PM Notes: Design Field Notes
Notes: (click 1) There is a specific format for the information that is to be included in the design field. It should include the name, email address, & phone number of the person that can answer questions about the design of the project. This is usually the consultant project manager. If there is a local sponsor, then the contact for this project should be provided. Information related to the procurement of the consultant services is to be included in this field. Finally, just like the PM note section, the PM is to initial and date the notes. This communicates how old the information is.

## Slide 29
Contract #
NTP Date
Expiration Date
Master Contract
TO #
NTP Date
Expiration Date
Status of procurement (if NTP has not been issued)
Task Order
TPro PM Notes: Design Field Notes
Notes: (click 1) For the master contract, the notes should include the contract number, NTP date, and expiration date of the contract.
(click 2) If there is a task order, the task order number, NTP date, & expiration date should be listed. If other task orders or contracts are needed, in development, or in procurement, each task order or contract should be listed with its procurement status.

## Slide 30: Work Independently
Review PSR A
HAS the PM filled out all Required sections of the PSR?
Check for completeness (not accuracy)
Take 1 minute to Look at the PSR
Notes: (each participant should have a copy of PSR A)
We just reviewed all of the areas of information on the PSR that the PM is either directly responsible for or needs to make sure it is not left blank. Review PSR A to check that the PM has filled out all required sections of the PSR? Use your highlighter or pen to identify any missing information. You will have one minute to review the PSR. Reminder: Don’t just look for the PM metric information. Also, you are checking for completeness not accuracy.

## Slide 31
COMPLETE
Still in Concept Phase; therefore, no approved estimates yet
Notes: (click 1 – 8 to highlight the TPro info that a PM is responsible for) As you can see this PM did fill out all of the areas.
(click 9-11) (to highlight areas that the PM should check but another office would update.)
(click 12) The PSR is not missing information. Therefore, it passes the completeness check. It is complete but is it accurate? (rhetorical question: go to next slide)

## Slide 32
Review PSR A
ARE the PM NOTES and DESIGNER Notes Following the Required TEMPLATE?
Check Format (not accuracy)
HINT: Compare to TPRO Format
Work Independently
Take 2 minute to Look at the PSR
Notes: Are the PM notes and the designer notes following the required template? In other words, is the required information and the correct order of providing the information used per the TPro Guidance? You are focusing on the PM Notes and the Designer Notes which are PM compliance metrics. You have 2 minutes to review the PSR notes.

## Slide 33
Outline of information follows TPro Format (not in Let Status):
Scope
Schedule
Next Milestone
Risk
Budget
PM initials and date
This matches consultant contact. This is accurate.
This note is not easily understood. What does “expected” mean? Is this when it will be submitted into RTS? This does not tell the reader the status of the task order. Also, what is “DES”? Not a standard GDOT acronym.
Follows TPro Format:
-consultant contact info
-contract info
-master contract info
-next TO status or
-current TO
- PM initials and date
FORMAT
Notes: (click 1) (read red box)
(click 2) (read purple box)
(click 3) (read green box)
(click 4) (read yellow box)
(click 5) With the exception of using non-GDOT standard acronyms, the format of information has been correctly done.

## Slide 34: (HINT: Cross Reference the information on the PSR)
Review PSR A
Is IT Accurately Reflecting The pROJEct Status?
Work Independently
Take 4 Minutes to Check for:
  Scope Accuracy
  Schedule Accuracy
  Budget Accuracy
Notes: The 3 pillars of project management are scope, schedule, and budget. When GDOT executive management is reviewing a PSR, they are looking at all 3 of these elements. The information for each of the pillars is stated in several different ways on a PSR. GDOT management will cross reference the information to determine if the PM’s reporting is accurate or not. No need to look up various files and documents on ProjectWise because GDOT management is going to look at the PSR to find out what they need to know and share about a project. Therefore, accuracy is vital to not on the PM’s reputation but for management to be able to have a snapshot of the project which will then provide information for decisions or commitments related to a project.
Take a look at PSR A. Is the PSR accurately reflecting the project status? It is recommended that you evaluate one pillar at a time. You have 4 minutes to review the PSR and all information, not just the PM notes. Please write down your review comments for this PSR.

## Slide 35
Scope
This is not accurate reporting.
Scope type = matches top of PSR
This states that survey is in next task order. If that is true why is survey database in P6 as 99% complete?
Finish date = submission date. P6 has 4/28/21 but PM notes have 4/29/21
Notes match TPro guidance and tell the status of the CR & but it is not consistent with P6 information
Information about the schedule does not belong in this section. Also, preliminary plans generally start after concept approval.
Notes: Let’s talk about the scope information.
(click 1) (read blue box)
(click 2) (read red box)
(click 3) (red yellow box)
(click 4) (read green box)
(click 5) (read purple box)
(click 6) (read orange box)

## Slide 36
Schedule
This is not accurate reporting.
Project is 3 months off BL
These do not match. 5 vs 44 requires different acquisition time. This could affect schedule. Which is correct?
Current schedule allows for 18 months for
ROW acquisition.
5 parcels = 12 months
44 parcels = 18 months or more
Inaccurate note for months behind BL
Since the CR was submitted, the next milestone is correctly written.
Access what? Proofread to avoid typos
Notes: Let’s talk about the schedule information.
(click 1) (read blue box)
(click 2) (read blue box)
(click 3) (read red box)
(click 4) (read green box)
(click 5) (read dark blue box)
(click 6) (read orange box)

## Slide 37
Budget
This is not accurate reporting due to the note about Utilities not being correct.
This is accurate since CR is not approved yet.
Until the first cost estimates are submitted after CR approved, no approval dates will be listed.
CR are not submitted without all cost estimates included. This note has not been updated.
In-house has negative funds. Therefore, a 1625 is needed. This is accurate reporting.
Notes: Let’s talk about the schedule information.
(click 1) (read green box)
(click 2) (read blue box)
(click 3) (read blue box)
(click 4) (read red box)
(click 5) (read orange box)

## Slide 38: Questions?