## Slide 1: Primavera P6: Project Scheduling Basics
09.17.2025
Office of Program Delivery
Notes: The purpose of this class is to understand the terminology and structure of a Primavera P6 schedule.
Course Material: Provide participants copy of the P6 schedule print out for PI 0017962 and paddles for answers. It is needed for the practicum activity.
Training Time: 30 minutes

## Slide 2: Learning Objectives
Schedule Terminology
What is Project Scheduling?
Purpose of Project Scheduling
Benefits of a Schedule
Importance of Accurate P6 Information
This Photo by Unknown Author is licensed under CC BY
Notes: (click 1) In this training, you will learn some of the basic schedule terminology. You will learn what is project scheduling and the purpose of project scheduling. We will also discuss the benefits of having a schedule for the project.

## Slide 3: Schedule Terminology
Work Breakdown Structure
Baseline & Planned Duration
Milestones
Predecessors/Successors
Critical Path
Notes: GDOT uses a scheduling software program called Primavera P6. It is important to understand some of the basic terminology associated with schedules. These terms will be explained in the next few slides.

## Slide 4: Schedule Terminology
Work Breakdown Structure (WBS)
HOUSE
Foundation
Interior
Exterior
Pour Concrete
Excavate
Frame
Sub Task
Sub Task
Sub Task
Electrical
Plumbing
Notes: The Work Breakdown Structure or WBS breaks work into smaller tasks to make the work more manageable and approachable. This is an example of how a WBS might be used for the construction of a home. The complete construction of the home would be the end result. The 3 main construction tasks would be the foundation, the interior, and the exterior. Each of those tasks would be further broken into smaller tasks.

## Slide 5
Work Breakdown Structure (WBS)
WBS 1
WBS 2
WBS 3
WBS 4
Notes: (click 1) Primavera P6 does color code the WBS. The color coding and the symbols work together to let the user or read of the software understand how the tasks are interrelated to a larger task. In this example the project is building the Wellmont Station. Wellmont Station is WBS 1. One of the main subtasks or activities is construction. Construction is broken into 3 WBS 3 levels: Below Grade, Above Grade, & Fence. Each WBS 3 has subtasks or activities known as WBS 4 level.

## Slide 6
Work Breakdown Structure (WBS)
WBS 1
WBS 2
WBS 3
WBS 4
Notes: (click 1) A WBS 4 example is Task W1050 for Grade Site.

## Slide 7: Schedule Terminology
Baseline Date & Planned Duration
BL Start & BL Finish = P6 Dates based on an Approved Schedule
BL Start
BL Finish
Planned Duration
Example: 20.0d = 4 weeks (or 1 month)
Notes: Baseline dates are the start and finish dates for each activity in the schedule. Every activity in P6 has a BL start and BL finish date. The baseline dates are assigned to the approved schedule for each project.
(click 2) The time between the baseline start and baseline finish date is the planned duration. In other words, how many business days will the activity take. If the P6 activity has a planned duration of 20 days, the activity is allotted 4 weeks or 1 month to complete. The duration is not based on calendar days.
The starting point of a schedule used as a point of comparison for actual performance progress

## Slide 8: Schedule Terminology
Actual Date
Actual Start & Actual Finish =
Dates that are entered into P6
BL Start
BL Finish
Actual Start
Actual Finish
Notes: (click 1) Actual Start and Actual Finish dates are information that is entered into P6. The owner of the task or activity is the person responsible to enter the actual dates. Ideally, the actual dates should be the same as the baseline dates.
(click 2) The baseline dates of a schedule are used as a point of comparison for actual performance progress. Remember that starting an activity late is a delay that could result in the actual finish date being late. However, this is not a forgone conclusion. It is the responsibility of the PM to manage the schedule and evaluate opportunities to recover time and finish on or close to the BL finish date, when possible.

## Slide 9: Schedule Terminology
Remaining Duration
Remaining Duration = days required to complete an activity that has started
Actual Start
Actual Finish
Work Completed
Remaining Duration
Notes: (click 1) The planned duration provided the number of workdays that it would take to complete an activity. Once the work has actually started, the number of days that it will take to finish the task is called the remaining duration.
(click 2) This is a visual representation of the work is left to do which is known as the remaining duration.

## Slide 10: Schedule Terminology
Remaining Duration
Planned Duration
Remaining Duration
Example: Planned 20d & completed is 30%
Need to Know:
Planned Duration (days total)
% of work completed
Remaining duration = 70% x 20d = 14d
Notes: (click 1) To figure out the remaining duration, the PM must know two things: first what was the planned duration & second what is the estimated %complete for the work associated with that activity?
(click 2) For example, if there is a design activity with the planned duration of 20 days and the designer tells the PM that the work is 30% complete, the PM would know that means that there is still 70% of the work to complete. The planned duration is a guide for how long that activity normally takes to complete. Therefore, in this example, the PM would multiple the planned duration by the % of work that is left. The answer would be the remaining duration for the activity and this information would be entered into P6.

## Slide 11: Schedule Terminology
Milestones
Important Task !!!
P6 Milestone only PM Milestones
Notes: (click 1) A milestone is symbolized in P6 as a diamond. A project milestone is a task of zero duration that shows an important achievement in a project. The milestones should represent a clear sequence of events that incrementally build up until your project is complete.
(click 2) OPD has assigned 3 milestones that a PM must make as part of being compliant with the OPD metrics. Although the PM milestones are milestones in the P6 schedule, they are not the only milestones for the project.
(click 3) For example, receiving the notice to proceed for the consultant contract on baseline schedule is a milestone but it is not a metric for the PM. However, it is important for the schedule to remain on baseline. If the NTP is not received per the BL date, the project is potentially at risk of being delayed and not recovering the schedule.

## Slide 12: Schedule Terminology
Predecessor/Successor
Predecessor
Successor
Starts before next activity; or
Must be completed before next activity
Begins after predecessor has started; or
After predecessor is complete
Notes: (click 1) Predecessor - a task that must start or be completed before the next task can begin.
(click 2) Successor - a task that begins after the predecessor has begun or is completed.

## Slide 13
Predecessor/Successor
Activity | BL Start | BL Finish | Predecessor to Activity | Successor to Activity
02800 | 5/22/23 | 6/5/23 | 02900 | 
02900 | 6/5/23 | 12/4/23 |  | 02800
Notes: This is an excerpt from a P6 schedule for activities involved with the concept report. The predecessor and successor are easily identified among tasks that are part of the same work breakdown structure for a particular task. For this example, the 3 sub tasks are for the Concept Report Approval.
(click 1) By reviewing the BL start and finish dates of each of the 3 activities, it is easy to identify which activity must start before another activity. For task 02800, the task must be completed before task 02900 can begin. Therefore, task 02800 is the predecessor for task 002900. Conversely, task 02900 is the successor of task 02800.

## Slide 14: Schedule Terminology
Critical Path
Excerpt of a Gantt Chart
Critical Path
Notes: Critical Path – The sequence of scheduled activities that determines the duration of the project. Critical path items are denoted in red. If critical path items are not completed on schedule, then milestones will be missed. For example, environmental technical studies are critical path to requesting PFPR. If the technical studies are not approved or close to approval prior to the date the PM must request PFPR, then the milestone will be missed. That is because OES will not grant permission to proceed with the PFPR request.
(click 1) This representation of the schedule is called a gnat chart. The P6 schedule can be represented as an excel table or a gantt chart or both.

## Slide 15: What is a Project Schedule?
Project Start Date
Project Finish Date
Baseline Schedule
Critical Path
Recovery Schedule
Notes: In short, it’s a timetable that outlines start and end dates and milestones that must be met for the project to be completed on time.
The project schedule is often used in conjunction with a Work Breakdown Structure (WBS) as a way to evenly distribute work among team members. The project schedule should be updated on a regular basis in order to gain a better understanding of the project’s current status.
A schedule is a listing of project milestone activities and deliverables usually with intended start and finish dates.

## Slide 16: What is the purpose of Project Scheduling?
Demonstrates realistic time and cost estimates for each activity
Communication Tool
Illustrates the relationship of activities with each other and to the whole project
Notes: (click 1) The project schedule is the tool that communicates what work needs to be performed, which resources of the organization will perform the work and the timeframes in which that work needs to be performed. The project schedule should reflect all of the work associated with delivering the project on time. Without a full and complete schedule, the project manager will be unable to communicate the complete effort, in terms of cost and resources, necessary to deliver the project.
(click 2) In order to sequence time and allocate resources to a project, project managers use project scheduling which serves several purposes. It illustrates the relationship of activities with each other and to the whole project. It identifies the precedence relationship between activities.
(click 3) It demonstrate the realistic time and cost estimates for each activity, and it optimize labor and material resources by identifying project’s critical barriers.

## Slide 17: Schedule Benefits
Reduce risk of delay
Assists in understanding numerous project details
Understanding of the project current status
Notes: Just to wrap up some of the benefits to project scheduling are that
(click 1) It Lowers the chance of delay and assists in recovering from delay
(click 2) Assists in understanding numerous project details (what activities need to be done and when)
(click 3) Gives a better understanding of the project current status. The wording “better understanding” was intentional. If P6 is not current or accurate, it is difficult for the PM to truly know the status of the project.

## Slide 18
Practicum Activity: P6 Schedule
Notes: [Directions: Participants should have a copy of printout from PI 0017962 and paddles for answers]

## Slide 19
Learning Objective
What P6 Activity number is
“Request/Receive Utilities First Submission”?
20927
B. 89500
C. 20900
D. 95300
Notes: [Directions: Give participants time to look at the P6 schedule. Answer: C – see page 3 lower 1/3 of the page under SUE and 1st Submission Utilities]

## Slide 20
What is the Baseline Finish date for activity #13411 “Technical Studies Summary”?
5/17/24
B. 10/31/24
C. 1/31/25
D. It’s not completed.
This is the BL start date.
This is the projected finish date based on information entered into P6.
Learning Objective
Notes: [Directions: Give participants time to look at the P6 schedule. Answer: B – see page 2 of pdf lower 1/3 of page]
(click 2) This date is based on the baseline start date.
(click 3) This date is the projected finish date. The date was not filled in by anyone in Primavera. It is generated based on the information that has been entered into P6.
(click 4) The question asked about the baseline finish date. The actual finish date would be based upon what really happened and when.

## Slide 21
How many days are planned for the Concept Activity #19344 “Develop and Evaluate Alternatives”?
0.0d
B. 20.0d
C. 4.0d
D. 10.0d
Learning Objective
Notes: [Directions: Give participants time to look at the P6 schedule. Answer: B. Look at page 1 of the pdf, approximately halfway down under Develop Draft Concept Report. ]

## Slide 22
What is the equivalent for a planned duration of 60.0d?
60 calendar days
B. 2 months
C. 3 months
D. I have no idea.
Remember: Planned duration is based on workdays. There are approx. 20 workdays in a month.
Learning Objective
Notes: [Directions: Give participants time to respond. Answer: C]
(click 1) Remember that planned duration is based on workdays not calendar days. There are approx. 20 workdays in a month.

## Slide 23: Importance of Accurate P6 Information: PM
Truth in Reporting
Evaluate Risk
Develop a Recovery Plan
Notes: It is the PM’s responsibility and metric to maintain up-to-date & accurate information in the schedule.
(click 1) Missing information, incomplete information, or inaccurate schedule information does not allow the PM to accurately report to GDOT management on the status of the project. For example, if a project is not showing as not on schedule due to missing information, the credibility of the PM may be challenged if they report that it is on schedule. Having the Primavera P6 current and accurate will provide evidence of how the project is doing in relationship to its schedule.
(click 2) If the schedule information is up-to-date, the PM will be able to assess if there is a risk or delay and how that might impact the project’s schedule.
(click 3) The accurate P6 information will also aid the PM in being able to develop a recovery plan. For example, a project that is 3 months behind has a different recovery plan than one that is 8 months behind.

## Slide 24: Importance of Accurate P6 Information: GDOT Management
Determine When Funds for ROW Authorize
Plan the Lettings
Provide Information
Notes: GDOT management needs the P6 information to be up-to-date and accurate to
(click 1) Determine if the funds are on schedule to be authorized. Remember that management has to balance the budget for all projects. The budget is based on a plan to have a specific amount of money authorized each month. If a project is off schedule and cannot recover, then the planned ROW budget must be adjusted.
(click 2) The construction funds are budgeted by both fiscal years and for each month within the fiscal year. The P6 schedule is reviewed by GDOT management to determine if GDOT will have balanced lettings.
(click 3) Board members, government officials, stakeholders, or concerned citizens may contact GDOT management and ask about the status of a project. Management may review the schedule and provide an update about the project. Therefore, the schedule must be up-to-date and accurate for GDOT management to provide information to those outside of GDOT.

## Slide 25
*Excerpt of GDOT Mgmt. PSR
Only shows PFPR inspection task
Notes: (click 1) There are various types of PSRs. However, one of the comment elements of every PSR is a table that includes some of the P6 activities and dates. Depending on the focus of the PSR, the activities displayed in the P6 table may change.
(click 2) This PSR is the GDOT executive management PSR. Management is concerned about when the PFPR inspection (aka meeting ) will be held. They are not focused on the PM milestone of PM request PFPR.
[transition to next slide to see the OPD PSR for the same project]

## Slide 26
*Excerpt of GDOT OPD PSR
Displays additional PFPR tasks that are important to the PM/OPD
Notes: (click 1) This PSR is the Program Delivery PSR. OPD is concerned about when the PM requests PFPR and the PFPR inspection will be held. OPD includes the PM requests PFPR because it is a metric for this office. This OPD version of the PSR includes more P6 tasks that the previous version.

## Slide 27: Questions?