## Slide 1: Project Status Update (PSU)
09.24.2025
Office of Program Delivery
Sheet Guidance
Notes: The purpose of this class is for OPD Project Managers to understand and properly fill out the Project Status Update form.
Training Time: 1 hour

## Slide 2: Learning Objectives
Purpose & Audience
Whose Responsibility
When It is Needed
PSU Location
Fill Out the Information
Notes: (click 1) The learner will understand the purpose of the Project Status Update form, and who the intended audience of this document is.
(click 2) You will know who is responsible for maintaining the information in this document.
(click 3) You will learn when the PSU is required and how often it must be updated.
(click 4) Management must be able to location the document at any time. Therefore, you will learn the location that all PMs should be storing the latest document.
(click 5) Finally, you will learn how to properly fill out the PSU.

## Slide 3
Purpose & Audience
Project Status Update (PSU) Current and Accurate Information
Purpose:
(Brief) Project Reference Document
Audience:
GDOT management
Notes: (click 1) The Project Status Update (PSU) is a document that contains current and accurate information related to a project.
(click 2) The purpose of the PSU is to provide a brief project reference document for GDOT management to understand and explain the project to stakeholders, government officials, politicians, and GDOT Board members.
(click 3) The audience for this document is GDOT management. It is not intended to be a project manager tool.

## Slide 4: Who is Responsible for the PSU?
Project Manager:
Create the PSU
Update the PSU
Notes: (click 1) The Project Manager is responsible to create and continually update the PSU.

## Slide 5
When is a PSU Required?
Every OPD Project
Updated Monthly (PM Metric)
Notes: (click 1) A PSU is required on every project that the Office of Program Delivery manages. The PSU must be updated monthly (at a minimum). This is one of the PM’s metrics for monthly compliance.

## Slide 6
Where is the PSU Located?
TEMPLATE – Project Status Update Form
It is found Online
ROADS/Design Related Resources/Category: Program Delivery
Notes: (click 1) The template is found online the Design Related Resources page. Look for the template entitled Project Status Update Form.

## Slide 7
Filling Out the PSU
Notes: Next, we will discuss the proper way to fill out the information on the Project Status Update form.

## Slide 8
Information from the PSR.
Don’t forget to update monthly
Notes: (click 1) The information for these items can be found on the PSR.
(click 2) Don’t forget to update the date when the PSU is revised. The PSU must be updated every 30 days and a new version of the PSU should be saved monthly on ProjectWise.

## Slide 9
2. PSU are to be saved on PW in the AOH folder under PE\Program Delivery
Hyperlink is for the AOH folder
Notes: (click 1) The PSU is to be saved on ProjectWise under AOH folder.
(click 2) The hyperlink is for the AOH folder, not the individual file.

## Slide 10
3. Check monthly that this information is still correct.
Notes: (click 1) These items need to be reviewed monthly to ensure that the information is still correct.

## Slide 11
4. Information is on the PSR.
Reminder: If the schedule changes via PCRF or BL Shift, then update the MGT date(s).
Choose one of these options
Notes: (click 1) This information can be found on the PSR. Don’t forget to update the management let date and/or management ROW date if the schedule shifts.
(click 2) For the environmental document type, you should select the correct document and delete the other options.

## Slide 12
6. This is the approved cost estimates for each funding phase. If the funding phase does not apply, write “$0.00.”
Additional funding needed: state which funding phase needs more money
List the new estimate and the funding phase
5. This is asking if on schedule for Mgmt. LET date
Notes: (click 1) This is asking if on schedule for Mgmt. LET date (not BL or the P6 let date).
If PM Notes are in Let Status Format, make sure that this information matches the PSR. Must answer this regardless of the PM note format.
(click 2) This is the approved cost estimates for each funding phase. If the funding phase does not apply, write “$0.00.”
f the answer is “Yes”, state which funding phase needs more money.

## Slide 13
7. Match the TPro expanded description
8. Follow the directions
Delete and replace with GeoPi image
Notes: (click 1) This should match the TPro expanded description. The language should be easy for non-technical people to understand.
Remember: This will need to be updated if the scope changes.
(click 2) follow the directions

## Slide 14
9. List out the milestones
Concept Report submission (if applicable)
PFPR request
FFPR request
Let date (list even though it is not a milestone)
10. List in brief sentences and include dates (if applicable) about what is happening on the project.
11
11. This information should match the information on the PSR.
Update the date each month
Notes: (click 1) For the project schedule, list out the milestones and the Let date.
(click 2) For the status update, list brief sentences about what is happening on the project.
(click 3) This information should match the information on the PSR. If there is more than one active contract/task order, it should be included. Do not include contracts that have been completed and closed.
(click 4) Don’t forget to fill out the header and updated the date each month

## Slide 15
12
If the project is controversial or potentially controversial, maintain a timeline of various public or government official coordination and outreach meetings.
12. If project is not controversial, delete this section.
Notes: (click 1) This section is only needed if the project is controversial. If it is not, then delete this section.
(click 2) If the project is controversial or potentially controversial, maintain a timeline of various public or government official coordination and outreach meetings.

## Slide 16
13
13. Next steps are critical path items to reach the next milestones or funding authorization (ROW Authorization or CST Authorization).
This is not a repeat of all of information from the “status update” section.
Notes: (click 1) Next steps are critical path items to reach the next milestones or funding authorization (ROW Authorization or CST Authorization).
(click 2) This is not a repeat of all of information from the “status update” section. Instead, list the high-level steps to reach the next milestone or funding authorization.

## Slide 17
14
14. If there is a project risk to the schedule, then list the risk.
If no risk to the schedule, list “N/A.”
Example:
Section 4(f) coordination due to a historic property within the project area.
(Assumption: Section 4(f) was not included in the schedule)
If Section 4(f) was included in the schedule, then it would not be listed as a risk.
Notes: (click 1) If there is a project risk to the schedule, then list the risk. Ensure that the reader can understand the risk with a brief explanation.
If no risk to the schedule, list “N/A.”
(click 2) For example, a PM might list Section 4(f) coordination due to a historic property within the project area as a risk. The assumption in this scenario is that Section 4(f) was not included in the schedule.
(click 3) If Section 4(f) was included in the schedule, then it would not be listed as a risk.

## Slide 18
Notes: Next, we will review an example PSU for filling it out properly.

## Slide 19
This is a hyperlink to the AOH folder
List the District Program Manager
If not on schedule, state how the schedule will recover.
Do not leave blank
or you will have to update the link every month
Notes: (click 1) Remember to use a hyperlink for the folder instead of the individual file.
(click 2) List the District Program Manager.
(click 3) The management ROW date should not be blank. If there isn’t a ROW phase, then write N/A.
(click 4) If the project is not on schedule for let, include a statement on how the schedule will recover.

## Slide 20
Match expanded TPro description
Match the approved cost estimates or the PM Notes if it is being updated
Notes: (click 1) The listed budget cost should be either what is approved or matches what the PM has put in their TPro notes as the updated cost estimate.
(click 2) The scope description should match and be consistent with the information from the TPro expanded description field.

## Slide 21
Copy image from GeoPi
Notes: (click 1) Each PSU should have a snipped copy of the GeoPi map showing the project location.

## Slide 22
List ALL completed and upcoming milestones
List “Concept Report Submission – N/A” if there isn’t concept report (also applies to PFPR if applicable)
Notes: (click 1) List all of the completed and upcoming milestones.
(click 2) If a project does not have a concept report submission milestone, it should still be listed but with N/A beside it.

## Slide 23
Explain the current status of the project
Notes: (click 1) When writing notes, include dates to give context to the information. Be mindful that dates should be written as a 6-digit number. Otherwise, there may be confusion as to whether the date represents a month and day or a month and year. If it is representing a month and year, write it as 2-digit month and 4-digit year.

## Slide 24
List ALL current contracts and task orders
Notes: (click 1) Include all current contracts and task orders. If a contract is no longer in use, it should be removed from the PSU.

## Slide 25
Not a repeat of all of the “status update” – high-level summary
Notes: (click 1) This is to show the comparison between what was written as the “status update” notes and the “next steps” notes. Notice that the “next steps” is not a copy of the information. Instead, it is listing the critical steps to get to the next milestone or funding authorization.

## Slide 26
This is the risk to the schedule only.
Notes: (click 1) Remember that a risk is related to the schedule. If the schedule included the activity or time needed for a task, this would not be considered a risk. It should be something that the schedule did not consider.

## Slide 27
Each project must have a PSU.
All PSUs are to be saved in the AOH folder under Program Delivery on PW.
PSUs must be updated each month as part of OPD PM compliance.
Project Status Update Sheet Reminders
Notes: (read slide)

## Slide 28
Each month a new PSU file must be created.
    Save the name of the PSU sheet using the naming convention:
    Year.month.day_PIXXXXXXX_County_Project_Status_Update
  Example: 2023.11.08_PI0015670_Banks_Project_Status_Update
  Note: The date in the file name should match the PSU sheet’s page 1 and the header on the additional sheets.
Project Status Update Sheet Reminders
Notes: (read slide)

## Slide 29: Questions?