## Slide 1: Schedule Development Process & Changes
09.25.2025
Office of Program Delivery
Notes: This training teaches the OPD PM the basic steps of developing a schedule. It also provides a foundational understanding of the processes to change an approved schedule.
Training Time: 30 minutes

## Slide 2
Learning Objectives
Schedule Responsibilities
Schedule Development Process
4 Types of Schedule Changes
Accessing OPC Documents
Notes: (click 1) The PM will learn what their responsibilities are related to the schedule.
(click 2) The PM will understand the basic steps of the schedule development process.
(click 3) The PM will understand the 4 types of schedule changes.
(click 4) The PM will understand how to access the OPC documents related to the schedule development or modification process.

## Slide 3: Schedule Responsibilities: Office of Program Control
Primavera P6 Owner
Work with PMs
Notes: (click 1) The office of program control (aka OPC) is the owner of GDOT’s scheduling software. GDOT is currently using Primavera P6 for the software. OPD PMs have a license to use the software but do not own it.
(click 2) OPC has many other responsibilities but related to schedules, this office works with PMs to ensure that scheduling is followed and understood.

## Slide 4: Schedule Responsibilities: Project Manager
Develop Schedule
Ensure Active Schedule
Monitor & Update P6
Request Schedule Changes
PM Metric
Notes: (click 1) The PM is responsible to develop a schedule if one does not exist.
(click 2) The PM is to ensure that every project has an active Schedule. This is a PM metric.
(click 3) The PM must monitor and continually update the information in the schedule.
(click 4) The PM is responsible to request schedule changes if they are needed.

## Slide 5
Schedule Review
The OPD PM is the owner of Primavera P6.
True
or
False
Notes: (directions give participants time to respond. Answer: False – OPC is the owner. OPD is a user with a license from OPC)

## Slide 6
Which PM responsibility is a metric?
Updating P6 each project
Developing a schedule for each project
Having an active schedule for each project
Monitoring the schedule for each project.
Schedule Review
Notes: (directions give participants time to respond. Answer: C) Although the others are also PM responsibilities, only active schedule for each project is a metric.

## Slide 7: New Schedule Process: Overview
Initial Schedule
Schedule Review Committee
Active Schedule
Notes: (click 1) This graphic is an overview of the process for a schedule on a new project. The initial or draft schedule is created. It is presented to the schedule review committee. After it is approved, the schedule is activated. On the next slide, we will look at this process in greater detail.

## Slide 8: New Schedule Process
Fill out Initial Schedule Form
Request Initial Schedule
Create Initial Schedule
Fill Out SRC Package
Request SRC
Present at SRC
Schedule
Approved
Activate Schedule
Share Schedule
Notes: (click 1) This graphic represents the basic steps for creating and activating a new schedule on a project. The PM fills out the OPC template called Initial Schedule. This form is then submitted to OPC to create the initial schedule. OPC provides the initial schedule to the PM for review.
(click 2) Once the schedule appears to cover the needed tasks of the project and timeline, the PM fills out the package for the schedule review committee. Then the request to present the schedule at SRC is submitted to OPC. OPC will review the package and let the PM know when month the schedule will be presented to SRC.
(click 3) After the schedule is presented, the schedule review committee will decide if the schedule can be approved, denied, or modified. When the schedule is approved, OPC will active the schedule. This means that the schedule is now “live” on the project and the PM must start to follow the baseline dates. After the schedule is active, the PM should share a copy of the P6 schedule with other team members who do not have access to P6.
In this graphic, the blue represents the PM steps. The pink represents the steps by OPC and the green step is SRC.

## Slide 9
Schedule Development: Needed Forms
Initial Schedule Form
Fill Out
Initial Schedule Revision Comment Form
Fill Out
Ready for Schedule Review Checklist
Fill Out
SRC Meeting Report Format
Review
Notes: (click 1) There are 4 forms that PM will use when creating a new schedule. First is the initial schedule form. Once the initial schedule is created by OPC, the PM will review the schedule and determine if there should be any revisions. The changes are documented in the initial schedule revision comment form. When the initial schedule is ready to be submitted to the schedule review committee, the PM will fill out the Ready for Schedule Review checklist. Prior to presenting at SRC, the PM will need to review the SRC meeting report format. All of these documents are located on the OPC site.

## Slide 10
The initial schedule is the active schedule.
True
or
False
Schedule Review
Notes: (directions give participants time to respond. Answer: False – This is the unapproved schedule. )

## Slide 11
The PM develops the initial schedule.
True
or
False
requests
Schedule Review
Notes: (directions give participants time to respond. Answer: False – This is the unapproved schedule. )

## Slide 12
Which is the correct order of the schedule development process?
Initial schedule, SRC, Active Schedule
SRC, Initial Schedule, Active Schedule
Initial Schedule, Active Schedule, SRC
None of these
Schedule Review
Notes: (directions give participants time to respond. Answer: A)

## Slide 13
4 Types of Changes:
Baseline Shift
PCRF
Schedule Modification
Shelf Form
Types of Schedule Changes
Notes: (click 1) Sometimes after a schedule is approved, it must be changed. There are 4 different types of schedule changes: baseline shift, project change request form, schedule modification, and shelf form.

## Slide 14
Types of Schedule Changes:
Baseline Shift
Criteria for a BL Shift:
Schedule is active
Schedule was issued with an anticipated NTP date
Can only be used once at the start of the project
Request as soon as NTP is known
Notes: (click 1) The criteria for requesting a baseline shift are:
The schedule is active
The schedule was issued with an anticipated notice to proceed date
This type of schedule changes is only used for the very start of the project and must be related to a late NTP.
A baseline shift is needed if a schedule has been approved with an anticipated NTP date. This means that it was anticipated that the consultant would be under contract and issued notice to proceed by a certain. However, the actual NTP is beyond what was anticipated. If the schedule was followed without the baseline shift, the project would never be able to recover and would always be off the baseline schedule. This type of schedule change keeps the P6 activities and durations for each activity the same but moves the baseline dates to line up with the actual NTP date.
(click 2) The BL shift should be requested as soon as the NTP is known.

## Slide 15
Example:
Active Schedule’s NTP Date: 3/4/24
Mgmt. Let Date: 12/19/28
Consultant receives NTP: 9/6/24
9/6/24-3/4/24 = 6 months behind
(Shifted) Active Schedule’s NTP Date: 9/4/24
(Shifted) Mgmt. Let Date: 6/19/29
*All P6 activities are given a new BL dates that are 6 months later
Types of Schedule Changes:
Baseline Shift
Notes: For example, the active schedule has a NTP date of March 4, 2024 and a management let date of December 19 2028.
(click 1) The consultant receives NTP on September 6, 2024.
(click 2) the anticipated date was 6 months before the actual NTP
(click 3) The schedule is shifted to align with the actual NTP date
(click 4) This triggers the rest of the schedule to be shifted and the management let date moves to June 19, 2029.
(click 5) all P6 activities are given new BL dates that are 6 months later. The old schedule is no longer followed.

## Slide 16
Project Change Request Form Criteria:
Schedule cannot recover for Let date
Schedule will change fiscal year
Schedule is at least 1 year behind baseline
Submit PCRF as soon as possible
Types of Schedule Changes:
PCRF
Notes: (click 1) A Project Change Request Form must be completed by the PM when the schedule cannot recover for the let date, the ROW Authorization or Mgmt Let Date will change fiscal years, or the schedule is at least 12 months behind baseline. This should be a last resort for the PM to correct the schedule. If properly monitoring the schedule and coordinating with the SMEs, often a schedule can be recovered.
(click 2) Once it is determined that a PCRF is required, the PM should submit it as soon as possible. Remember that GDOT must balance the lettings. This means that there is a maximum number of projects allocated to each month for let. The change in the schedule also affects GDOT’s budget for the fiscal year.

## Slide 17
Schedule Modification Criteria:
P6 activity needs to be removed
P6 activity needs to be added
Types of Schedule Changes:
Schedule Modification
Notes: (click 1) The schedule modification is related to specific P6 activity or activities. Sometimes a schedule was activated with an activity that no longer applies to the project. In this case, the activity may need to be removed from the schedule. Otherwise, it will push out the schedule because it has not been completed. Other projects may not have included a specific P6 task that was later determined to be needed. In this scenario, the P6 activity must be added to the schedule.

## Slide 18
Shelf Form Criteria:
ROW Authorization funds are not available
Construction Authorization funds are not available
Project on hold right before funding authorization occurred
Types of Schedule Changes:
Shelf Form
Notes: (click 1) There are times when a project develops to a certain point, but GDOT does not have the funds available for either ROW authorization or Construction Authorization. In this scenario, the PM would have been notified by GDOT management and the project would need to be placed on the shelf. The idea is that the project is ready for next funding phase to be authorized but be placed on hold until the money is available.
(click 2) The project is developed up to the point of the next funding authorization. It has nothing to do with what a consultant may have been scoped to do for the project.

## Slide 19
Which is NOT a type of schedule change?
PCRF
Schedule Modification
PFA
Shelf Form
Schedule Review
Notes: (directions give participants time to respond. Answer: A)

## Slide 20
Which type of schedule change is used if the actual NTP is different than the anticipated NTP of the 1st Task Order or Contract?
Shelf Form
Schedule Modification
PCRF
Baseline Shift
Schedule Review
Notes: (directions give participants time to respond. Answer: D)

## Slide 21
The PM should submit a PCRF as soon as possible if the schedule cannot recover and the Fiscal Year will be missed.
True
or
False
Schedule Review
Notes: (directions give participants time to respond. Answer: True)

## Slide 22: How to Access OPC Documents

## Slide 23
Scroll Down
Notes: Once you are on the Office of Program Control’s page, you will need to scroll down to the Resources box.

## Slide 24
Notes: Click on OPC Team Site.

## Slide 25
Notes: This is the OPC team site.
(click 1) Select the form that you need from the right side of the page.

## Slide 26
Notes: (click 1) For specific types of projects, there may be a template available. Check here before requesting a full schedule.
(click 2) For all other projects, you will use the initial schedule request form.

## Slide 27
Notes: The initial schedule request form is a one page document that the PM must fill out.

## Slide 28
Must be familiar with the proposed project
Notes: (click 1) The PM will have to know or research a little about the proposed project to be able to fill out the form.

## Slide 29: Questions?