Accelerated Bridge Construction  Decision Questionnaire

| Project Information |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Name/Location: |  |  |  |  |  |  |
| PI No.: |  |  |  | Preliminary Submittal: |  |  |
| GDOT Project Manager: |  |  |  | Final Submittal: |  |  |
| Bridge EOR: |  |  |  | Let Date: |  |  |
| Addition Information: |  |  |  |  |  |  |
| Bridge Information |  |  |  |  |  |  |
| Bridge No.: |  |  |  |  |  |  |
| ADT On: |  |  | ADT Under: |  |  |  |
| Existing Bridge Length: |  |  | Proposed Bridge Length: |  |  |  |
| Existing Bridge Width: |  |  | Proposed Bridge Width: |  |  |  |
| Project Description: |  |  |  |  |  |  |
| Anticipated Construction Duration: |  |  |  |  |  |  |
| Scope of Work: |  |  |  |  |  |  |
| Addition Information: |  |  |  |  |  |  |

General Site Considerations

|  | Question/Issue: |  | Yes | Poss. | No | N/A | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Is bridge construction on the critical path of this project? |  |  |  |  |  |  |
| 2 | Could construction impact businesses? |  |  |  |  |  |  |
| 3 | Do locals have an opinion on the project? |  |  |  |  |  |  |
| 4 | Are there any issues regarding construction timeframes (e.g. fish spawning, bird nesting, high water, permits, major events)? |  |  |  |  |  |  |
| 5 | Are there critical features or services on the route that need to be considered (e.g. hospital, emergency services, transit, school buses)? |  |  |  |  |  |  |
| 6 | Will there be impacts to any Railroads? If Yes: |  |  |  |  |  |  |
|  | a. | Does railroad traffic need to be maintained during construction? |  |  |  |  |  |
|  | b. | Frequency of trains |  |  |  |  |  |
| 7 | Are there Utilities on the bridge? |  |  |  |  |  |  |
| 8 | Are there utilities in the area that will need to be relocated? |  |  |  |  |  |  |
| 9 | Are there any known geotechnical issues that may affect construction? |  |  |  |  |  |  |
| 10 | Score from Go/No-Go Tool |  |  |  |  |  |  |
| Additional Considerations: |  |  |  |  |  |  |  |

Traditional Construction Methods

|  | Question/Issue: |  | Yes | Poss. | No | N/A | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 11 | Is it likely that this project will include complex traffic control schemes, long detours, or significant user impacts due to bridge construction? |  |  |  |  |  |  |
| 12 | Is staged construction feasible? If Yes: |  |  |  |  |  |  |
|  | a. | Average Delay Time |  |  |  |  |  |
|  | b. | Is additional bridge width required to accommodate staged construction? |  |  |  |  |  |
|  | c. | Will additional R/W or easements be required to accommodate staged construction |  |  |  |  |  |
| 13 | Does the existing bridge have features that make it difficult to accommodate staging (truss bridge, slab span, beam spacing issues, etc.)? |  |  |  |  |  |  |
| 14 | Could additional width be needed on culverts, bridges, or shoulders to maintain traffic on the existing route or the detour route? |  |  |  |  |  |  |
| 15 | Is it likely that temporary bridge structures will be needed? |  |  |  |  |  |  |
| 16 | Will temporary traffic signals be required? |  |  |  |  |  |  |
| 17 | Does it appear that maintenance of traffic will require additional right-of-way? |  |  |  |  |  |  |
| Additional Considerations: |  |  |  |  |  |  |  |

Detour

|  | Question/Issue: |  | Yes | Poss. | No | N/A | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 18 | Will/Can traffic be detoured? If Yes: |  |  |  |  |  |  |
|  | a. | Detour Delay Time |  |  |  |  |  |
|  | b. | Local Alternative Detour Delay Time |  |  |  |  |  |
|  | c. | Will the detour route have a detrimental impact on emergency vehicles, school buses, or other sensitive traffic? |  |  |  |  |  |
|  | d. | Is the local alternate detour route in need of repairs? |  |  |  |  |  |
|  | e. | Are there load limit restrictions on the detour? |  |  |  |  |  |
|  | f. | Are there bridge width or height restrictions on the detour? |  |  |  |  |  |
|  | g. | Are there issues regarding suitability of detour route (length, speed limit, travel time, etc.)? |  |  |  |  |  |
|  | h. | Will intersection improvements be required on detour/alternate routes? |  |  |  |  |  |
| Additional Considerations: |  |  |  |  |  |  |  |

Accelerated  Bridge Construction

|  |  | Question/Issue: | Yes | Poss. | No | N/A | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 19 |  | Are there significant risks or other factors (site complexity) that could be mitigated by accelerating bridge construction? |  |  |  |  |  |
| 20 |  | Are there suitable staging locations? |  |  |  |  |  |
| 21 |  | Will the use of ABC mitigate the need for utility relocation? |  |  |  |  |  |
| Additional Considerations: |  |  |  |  |  |  |  |

Conclusion:

Engineer of Record

Based on the findings & conclusions above, further consideration of accelerated bridge construction is warranted: YES NO Name: ___________________________________ Date: __________ Comments:

Office of Construction

Based on the findings & conclusions above, further consideration of accelerated bridge construction is warranted: YES NO Name: ___________________________________ Date: __________ Comments:

District Construction

Based on the findings & conclusions above, further consideration of accelerated bridge construction is warranted: YES NO Name: ___________________________________ Date: __________ Comments:

Office of Bridge Design and Maintenance

Based on the findings & conclusions above, further consideration of accelerated bridge construction is warranted: YES NO Name: ___________________________________ Date: __________ Comments:

Accelerated Bridge Construction

Decision Questionaire

General Information/Background:

The ABC decision questionnaire  should be completed after go/no-go tool indicated favorable conditions for ABC.  The process has been developed to help determine project sites that are best suited to use accelerated bridge construction techniques. The questionnaire  investigates impacts to the local community and provides a consistent method to define the parameters of the project location.

Instructions

Line By Line Instructions:

Project Information

It is intended that this tool be filled out and recorded by the ABC Liaison, with assistance from the Project Manager, Construction Engineer and the Bridge Office.

Bridge Information:

Record the basic bridge data, including the ADT on and under the bridge, which may help in determining appropriate staging, traffic control, and ABC alternatives. This data is on the Bridge Inventory Sheet, available from the GDOT GeoPI.  https://www.dot.ga.gov/applications/geopi/Pages/Search.aspx

Project Description:

List the major work type such as “bridge replacement”, “bridge re-deck with widening”, “superstructure replacement”, etc.  If known, include the approximate construction duration using traditional construction methods.  If the project includes major roadway work indicate the anticipated duration of bridge construction only.  The complete focus of the project should be captured in the Scope of Work.  Include any additional information that is unique to this project.

General Site Considerations

Question/Issue No. 1:

Is bridge construction on the critical path of this project?

In assessing the need for accelerated bridge construction it’s important to understand what role bridge construction plays in the overall scope and duration of the project.  If the bridge work is not on the critical path it may not be cost effective to accelerate the bridge portion of the work.

Question/Issue No. 2:

Could construction impact businesses?

The cost of mitigating impacts to local businesses can be substantial. Staging alternatives ranging from full closure to ½ at-a-time, or even night time construction may help moderate these concerns.  List the potential business impacts.

Question/Issue No.3:

Do locals have an opinion on the project?

Locals may have insight on the bridge site that may not be obvious.  They may also have a preference to a short road closure over extended stage construction or know of events that may interfere with construction.

Question/Issue No. 4:

Are there any issues regarding construction timeframes (e.g. fish spawning, bird nesting, high water, permits, major events)?

Work with environmental, hydraulics, and DNR representatives to determine if the aforementioned issues may restrict the ability to use conventional construction methods or timeframes, which may lead to compressed construction schedules or reduced access to adjacent right-of-way.

Question/Issue No. 5:

Are there critical features or services on the route that need to be considered (e.g. hospital, emergency services, transit, school buses)?

The need to maintain access for emergency services, school buses, transit, etc., can impact project scheduling, duration and staging alternatives. List the known critical services or features that must be considered and whether or not they can be accommodated using conventional construction methods and staging.

Question/Issue No.6:

Will there be impacts to any Railroads?

Impacts to railroads will require additional coordination with the facilities owners to ensure that their concerns are considered.

Question/Issue No. 6a:

Does railroad traffic need to be maintained during construction?

The cost of flagging operations and temporary structures can be significant, so it may make sense to investigate ABC alternatives, which may reduce roadway user and railroad impacts as well as construction duration.

Question/Issue No. 6b:

Frequency of trains

On a heavily traveled railroad, it may be beneficial to limit construction time to increase safety to workers and lessen impacts to train traffic.

Question/Issue No. 7:

Are there Utilities on the bridge?

Utilities located on the bridge may impact possible ABC methods.  If ABC is determined to be beneficial to the project, an attempt should be made to locate utilities off of the bridge.

Question/Issue No. 8:

Are there utilities in the area that will need to be relocated?

Adjacent utilities should be examined to determine if they will need to be moved to accommodate the proposed facilities or construction access.  If ABC methods appear applicable, there may be additional access requirements to accommodate multiple cranes at the same site.

Question/Issue No. 9:

Are there any known geotechnical issues that may affect construction?

Geotechnical issues may not be apparent until after the BFI is completed, but the limits and any existing plans should be reviewed for geotechnical issues that may affect the timing or cost of the project  The cost of poor soil mitigation can be significant and may be avoided through the use of construction staging or ABC techniques that don’t disturb the affected areas.

Question/Issue No. 10:

Record Score from Go/No-Go Tool

Question/Issue No. 11:

Is it likely that this project will include complex traffic control schemes, long detours, or significant user impacts due to bridge construction?

Long detours and complex traffic control schemes may lead to higher construction and roadway user costs, which may make spending additional funds on ABC techniques a cost effective solution.  The more complex the traffic control scheme or the longer the detour route, the more likely ABC can be a viable alternative. Review the possible traffic staging options and detour routes for use in determining the user impacts.

Question/Issue No. 12:

Is staged construction feasible?

If there are staged construction option available it may not be cost effective to utilize ABC methods.  If staged construction is an option provide a brief comment on the intended method.

Question/Issue No. 12a:

Average Delay Time

Input the Average Vehicle Delay determined using the appropriate vehicle delay worksheet.

Question/Issue No. 12b:

Is additional bridge width required to accommodate staged construction?

Overbuilding the proposed structure to accommodate staged construction will increase project costs.  If yes, comment on the approximate overbuild width.

Question/Issue No. 12c:

Will additional R/W or easements be required to accommodate staged construction?

The purchase of additional R/W or easements can be a significant project cost and lead to delays in the project schedule.

Question/Issue No. 13:

Does the existing bridge have features that make it difficult to accommodate staging (truss bridge, slab span, beam spacing issues, etc.)?

Features such as existing beam spacing (i.e. not having a beam along the centerline of the roadway) may limit the ability to use ½ at-a-time construction or other staging alternatives.  Some bridge types, such as trusses are not suitable to widening.

Question/Issue No.14:

Could additional width be needed on culverts, bridges, or shoulders to maintain traffic?

If it becomes necessary to spend funds to temporarily widen existing roadways or structures, it may make sense to spend those funds on ABC alternatives, which may also reduce roadway user impacts and construction duration.

Question/Issue No. 15:

Could temporary bridge structures be required?

If early analysis indicates that ½ at-a-time construction staging, detours, or other fairly simple staging alternatives are not suitable, it may be necessary to construct a temporary bridge. Since temporary structures may cost as much as 60% of the cost of a new bridge, it may make sense to spend some additional funds on ABC alternatives, which may also reduce roadway user impacts and construction duration.

Question/Issue No. 16:

Will temporary traffic signals be required?

The cost and impact of using temporary traffic signals or traffic control systems need to be considered when determine if the extra costs associated with ABC is warranted.

Question/Issue No. 17:

Does it appear that maintenance of traffic will require additional right-of-way?

Same considerations as question No. 3c, but related to possible right-of-way acquisition.

Question/Issue No. 18:

Will/Can traffic be detoured?

If it’s already been determined that traffic cannot or will not be detoured, it is not necessary to complete the remainder of question 18, otherwise proceed to the following sub-questions:

Question/Issue No. 18a:

Detour Delay Time

Input the Detour Delay determined using the appropriate vehicle delay worksheet.

Question/Issue No. 18b:

Local Alternative Detour Delay Time

Input the Local Alternative Detour Delay determined using the appropriate vehicle delay worksheet.

Question/Issue No. 18c:

Will the detour route have a detrimental impact on emergency vehicles, school buses, or other sensitive traffic?

Similar to question No. 5, but in regards to the proposed detour route.

Question/Issue No. 18d:

Is the local alternate detour route in questionable condition?

Work with the District Engineer to determine if the available detour routes are in suitable condition or if significant funds would be required to repair or restore the route.

Question/Issue No. 18e:

Are there load limit restrictions on the detour?

Work with the Bridge Office and District Engineer to determine if the proposed work will require temporary load postings or strengthening of bridges, culverts, or roadways within the project limits.  If it becomes necessary to spend funds to strengthen bridges and roadways, it may make sense to spend those funds on ABC alternatives.

Question/Issue No. 18f:

Are there bridge width or height restrictions on the detour?

Similar to question 18e, existing bridge height and width restrictions may limit the available detour routes. Work with  the District Engineer to obtain any needed restrictions.

Question/Issue No. 18g:

Are there other issues regarding the suitability of the detour route (length, speed limit, travel time, etc.)?

List the additional characteristics of the available detour routes that they may make them undesirable. Long detours, routes with reduced speed and increased travel time may result in further consideration of other construction or contract administration alternatives that eliminate or limit the need for a detour.

Question/Issue No. 18h:

Are modifications needed at intersections on detour/alternate routes?

Consider the need for temporary signals, signing, or modifications that may be needed to existing intersections to accommodate traffic on the detour route.

Question/Issue No. 19:

Are there significant risks or other factors (site complexity) that could be mitigated by accelerating bridge construction?

List any other known risks or concerns that are not included in any of the previous questions.  Examples might include lack of available concrete production facilities in the region, rapid changes in water elevation or velocity, limited construction window due to local ordinances, adjacent to vibration sensitive structures, etc.  The District  Engineer may also be able to provide insight regarding this issue.

Question/Issue No. 20:

Are there suitable staging locations?

Without suitable staging location the ABC option may be infeasible.

Question/Issue No. 21:

Will ABC mitigate utility relocation?

If ABC can mitigate utility relocation, it may be beneficial to use extra funds on ABC methods.

Additional Considerations:

Before making a final decision as to whether or not accelerated bridge construction is a viable alternative, consideration should also be given to “packaging” additional bridges in the vicinity, and acknowledgment of other planned construction work in the area.

Conclusion:

After thoroughly reviewing the responses to the questions, the Engineer of Record should give their recommendation based off the defined parameters.  The ABC Decision Questionnaire may be reviewed by representatives of the Bridge Office, Construction Office, and District Construction.  The State Bridge Engineer will review the analysis for a final decision on if the project warrants ABC.

Example responses may include:

NO

“A suitable detour is available and the traffic demands at this site do not warrant the use of ABC.”

“Staging can be facilitated using ½ at-a-time construction (or other staging method) without the use of ABC.”

“Bridge construction is not on the critical path and the overall construction schedule will not benefit by using ABC.”

“Conventional bridge construction methods will adequately address the schedule and user impacts on this project.”

YES

“Roadway user impacts and safety make ABC a viable alternative.”

“Use of a lateral slide (or other ABC alternative) will be further investigated.”