## Slide 1: Post Let Right-of-Way 1
Start
Submit
1
Specialty Reports
Yes
2 GDOT Accept Specialty Report
Revise
Complete
Release to Negotiate
Submit
Submit
Yes Relocation
3 Design-Builder Revise Specialty Report
4
Design-Builder Submit Appraisals
5 GDOT Accept Appraisals
7
Design-Builder Submit Relocation Package
8 GDOT Accept Relocation Package
9
Design-Builder Revise Relocation Package
Resubmit
6
Design-Builder Revise Appraisals
Resubmit
No
Resubmit
Revise
Revise
No Relocation
10
Design-Builder Negotiations

## Slide 2: Post Let Right-of-Way 2
12 GDOT Review Respond to Counter Offer
Yes
Accept
Close
13
Design-Builder Respond to Interest Holder
21
Design-Builder Prepares Closing Documents
10
Design-Builder Negotiations
22 SAAG Conducts Closing
Close
11 GDOT Signs Executed FMV Option
Property Management?
Request Condemnations
14 GDOT Review & Accept Early Condemnation
Reject
Approve
Release to Negotiate
No Relocation
Counter
Offer
Successful
FMV
Accept
20 GDOT Conducts Admin Review
15 GDOT Verify Final Negotiations
17 Administrative Review Request Received
19
GDOT Review Admin Review Package
16
Design-Builder Send 10 Day Letter
23 Design-Builder Submit Condemnation Package
24 SAAG Files Condamnation Pétition
Submit
Package
Sent
Revise
18
Design-Builder Send Admin Review Package
Not Successful
No
Accept
Rejection
No
Revise
Reject
Accept
Yes
Petition Filed
Submit
Friendly Condemn
No
Yes
31
Design-Builder Submit Final Parcel File
Relocation
8
GDOT Accept Relocation Package
5 GDOT Accept Appraisals
Reject

## Slide 3: Post Let Right-of-Way 3
Relocation
No
26a GDOT Release to Clear
Submit
25a Design-Builder Submits Notices
27a Design-Builder Submit Final Prop Mgmt Doc
GDOT PM Needed?
Release
Submit
26
GDOT Release to Clear
Submit
25
Design-Builder Submits Notices
27
Design-Builder Submit Final Prop Mgmt Docs
Release
Submit
Yes
Yes
No
Yes
28A
PMC Review/ Coordinate GDOT PM
28
PMC Review/ Coordinate GDOT PM
30a
PMC Verify Prop Mgmt Forms Complete
Property Management?

## Slide 4: Post Let Right-of-Way 4
30a
GDOT Verify Prop Mgmt Forms Complete
Submit
29A
Design-Builder Performs Property Management and Submit PM7
28A
GDOT Releases to Design-Builder to Perform Property Management
Yes
Reviewed
31
Design-Builder Submit Final Parcel File
Yes
30
GDOT Verify Prop Mgmt Forms Complete
Submit
29
Design-Builder Performs Property Management and Submit PM7
28
GDOT Releases to Design-Builder to Perform Property Management
Submit
Reviewed
33
Design-Builder Revises Parcel File
32 GDOT Verify Complete
Archive
Update Subject
Finish
Submit
Yes
No
No
Incomplete
Incomplete
Incomplete
Complete
Code
Complete
True
False
Resubmit
Property Management Needed?
27
Design-Builder Submit Final Prop Mgmt Doc
Property Management?