# MASTER UTILITY ADJUSTMENT AGREEMENT

# (Owner Managed)

# Agreement No.: -U-

THIS AGREEMENT, by and between ________________________, hereinafter identified as the “Developer”, and      , hereinafter identified as the “Owner”, is as follows:

# WITNESSETH

WHEREAS, the STATE OF GEORGIA, acting by and through the Georgia Department of Transportation, hereinafter identified as “GDOT”, is authorized to plan, designate, improve, manage, control, construct, and maintain a state highway system and shall have control of and responsibility for all construction, maintenance, or any other work upon the state highway system and all other work which may be designated to be done by the department by this title or any other law, all sin conformance with the provisions of O.C.G.A. § 32-2-2 et seq. as amended; and

WHEREAS, GDOT proposes to construct a project identified as the _______________ (the “Facility”); and

WHEREAS, pursuant to that certain Design Build Finance Agreement (DBFA) by and between GDOT and the Developer with respect to the Facility (the “DBFA”), the Developer has undertaken the obligation to design, build and, participate in the finance of the Facility; and

WHEREAS, the Developer’s duties pursuant to the DBFA include causing the removal, relocation, or other necessary adjustment of existing utilities impacted by the Facility (collectively, “Adjustment”), subject to the provisions herein; and

WHEREAS, the Facility may receive Federal funding, financing and/or credit assistance; and

WHEREAS, the Developer has notified the Owner that certain of its facilities and appurtenances (the “Owner’s Utilities”) are in locational conflict with the Facility, and the Owner has requested that the Owner undertake the Adjustment of the Owner’s Utilities pursuant to O.C.G.A. § 32-6-170, et seq.  as necessary to accommodate the Facility; and

WHEREAS, the Owner’s Utilities and the proposed Adjustment of the Owner’s Utilities are described as follows [insert below a description of the affected facilities (by type, size and location) as well as a brief description of the nature of the Adjustment work to be performed (e.g., “adjust 12” waterline from approximately Highway Station 100+00 to approximately Highway Station 200+00”)]:

; and

WHEREAS, the Owner recognizes that time is of the essence in completing the work contemplated herein; and

WHEREAS, the Developer and the Owner desire to implement the Adjustment of the Owner’s Utilities by entering into this Agreement.

# AGREEMENT

NOW, THEREFORE, in consideration of these premises and of the mutual covenants and agreements of the parties hereto and other good and valuable consideration, the receipt and sufficiency of which being hereby acknowledged, the Developer and the Owner agree as follows:

# 1.	Preparation of Plans.  [Check one box that applies:]

The Developer has hired engineering firm(s) acceptable to the Owner to perform all engineering services needed for the preparation of plans, required specifications, and cost estimates, attached hereto as Exhibit A (collectively, the “Plans”), for the proposed Adjustment of the Owner’s Utilities.  The  Developer represents and warrants that the Plans conform to the most recent Utility Accommodation Policy and Standards Manual (UAM) issued by the Georgia Department of Transportation (“GDOT”) pursuant to O.C.G.A. §32-6-174, which can be found at:

http://www.dot.state.ga.us/doingbusiness/utilities/pages/manual.aspx.

By the execution of this Agreement or by the signing of the Plans, the Owner hereby approves and confirms that the Plans are in compliance with the “standards” described in Paragraph 3(d)

The Owner has provided plans, required specifications and cost estimates, attached hereto as Exhibit A (collectively, the “Plans”), for the proposed Adjustment of the Owner’s Utilities.  The Owner represents and warrants that the Plans conform to the UAM.  By the execution of this Agreement, the Developer hereby approves the Plans.  The Owner also has provided to the Developer a utility plan view map illustrating the location of existing and proposed utility facilities on the Contractor’s right of way map of the Facility.  With regard to its preparation of the Plans, Owner represents as follows [check one box that applies]:

The Owner’s employees were utilized to prepare the Plans, and the charges therefore do not exceed the Owner’s typical costs for such work.

The Owner utilized consulting engineers to prepare the Plans, and the fees for such work are not based upon a percentage of construction costs.  Further, such fees encompass only the work necessary to prepare the Plans for Adjustment of the Owner’s Utilities described herein, and do not include fees for work done on any other project.  The fees of the consulting engineers are reasonable and are comparable to the fees typically charged by consulting engineers in the locale of the Facility for comparable work for the Owner.

2.	Review by GDOT.  The parties hereto acknowledge and agree as follows:

(a)	Upon execution of this Agreement by both the Developer and the Owner, the Developer will submit this Agreement, together with the attached Plans, to GDOT for its review and approval as part of a package referred to as a “Utility Work Plan”.  The parties agree to cooperate in good faith to modify this Agreement and/or the Plans, as necessary and mutually acceptable to all parties, to respond to any comments made by GDOT thereon.  Without limiting the generality of the foregoing, (i) the Owner agrees to respond (with comment and/or acceptance) to any modified Plans and/or Agreement prepared by the  Developer in response to GDOT comments within thirty (30) days after receipt of such modifications; and (ii) if the Owner originally prepared the Plans, the Owner agrees to modify the Plans in response to GDOT comments and to submit such modified Plans to the  Developer for its comment and/or approval (and re-submittal to GDOT for its comment and/or approval) within thirty (30) days after receipt of GDOT’s comments.  The Owner’s failure to timely respond to any modified Plans submitted by the Developer pursuant to this paragraph shall be deemed the Owner’s approval of same.  If the Owner fails to timely prepare modified Plans which are its responsibility hereunder, then the Developer shall have the right to modify the Plans for the Owner’s approval as if the Developer had originally prepared the Plans.    The process set forth in this paragraph will be repeated until the Owner, the Developer and GDOT have all approved this Agreement and the Plans.

(b)	The parties hereto acknowledge and agree that GDOT’s review, comments, and/or approval of a Utility Work Plan or any component thereof is solely for the purpose of ascertaining matters of particular concern to GDOT, and GDOT has, and by its review, comments and/or approval of such Utility Work Plan or any component thereof undertakes, no duty to review the Utility Work Plan or its components for their quality or for the adequacy of adjusted facilities (as designed) for the purposes for which they are intended to be used or for compliance with law or applicable standards (other than GDOT requirements).

3.	Design and Construction Standards.  All design and construction performed for the Adjustment work which is the subject of this Agreement shall comply with and conform to the following:

(a)	All applicable local and state laws, regulations, decrees, ordinances and policies, including the UAM, the Utility Manual issued by GDOT (to the extent its requirements are mandatory for Utility Adjustments necessitated by the Facility, communicated to the Owner by the  Developer or GDOT), the requirements of the DBFA, and the policies of GDOT;

(b)	All Federal laws, regulations, decrees, ordinances and policies applicable to projects receiving Federal funding, financing and/or credit assistance (including without limitation 23 CFR 645 Subparts A and B, incorporated herein by this reference);

(c)	The terms of all governmental permits or other approvals, as well as any private approvals of third parties necessary for such work; and

(d)	The standard specifications, standards of practice, and construction methods (collectively, “standards”) which the Owner customarily applies to facilities comparable to the Owner’s Utilities that are constructed by the Owner or for the Owner by its Pre-Approved Contractors at the Owner’s expense, which standards are current at the time this Agreement is signed by the Owner, and which the Owner has submitted to the Developer in writing.

Such design and construction shall also be consistent and compatible with (i) the Developer’s current design and construction of the Facility, (ii) any other utilities being installed in the same vicinity.  The Owner acknowledges receipt from the Developer of Facility plans and documents as necessary to comply with the foregoing.  In case of any inconsistency among any of the standards referenced in this Agreement, the most stringent standard shall apply.

4.	Construction by the Owner; Scheduling.

(a)	The Owner hereby agrees to perform the construction necessary to adjust the Owner’s Utilities. All construction work hereunder shall be performed in a good and workmanlike manner, and in accordance with the Plans (except as modified pursuant to Paragraph 17).  The Owner agrees that during the Adjustment of the Owner’s Utilities, the Owner and its Pre-Approved Contractors will coordinate their work with the Developer so as not to interfere with the performance of work on the Facility by the Developer or by any other party.  “Interfere” means any action or inaction that interrupts, interferes, delays or damages Facility work.

(b)	The Owner may utilize its own employees or may retain such Contractor or Sub-Contractors as are necessary to adjust the Owner’s Utilities, through the procedures set forth in the “Statement Covering Contract Work” attached hereto as Exhibit C.  If the Owner utilizes its own employees for the Adjustment of the Owner’s Utilities, Exhibit C is not required.  If the Adjustment of the Owner’s Utilities is undertaken by the Owner’s Pre-Approved Contractor under a competitive bidding process, all bidding and contracting shall be conducted in accordance with all federal and state laws and regulations applicable to the Owner and the Facility.

(c)	The Owner shall obtain all permits necessary for the construction to be performed by the Owner hereunder, and the Developer shall cooperate in that process as needed.  The Owner shall submit a traffic control plan to the Developer as required for Adjustment work to be performed on existing road rights of way.

(d)	The Owner shall commence its construction for Adjustment of each Owner Utility hereunder promptly after (i) receiving written notice to proceed therewith from the  Developer, and (ii) any right of way necessary for such Adjustment has been acquired either by GDOT (for adjusted facilities to be located within the Facility right of way) or by the Owner (for adjusted facilities to be located outside of the Facility right of way), or a right-of-entry permitting Owner’s construction has been obtained from the landowner by the  Developer or by the Owner with the  Developer’s prior approval.  The Owner shall notify the Developer at least 72 hours prior to commencing construction for the Adjustment of each Owner Utility hereunder.

(e)	The Owner shall expeditiously stake the survey of the proposed locations of the Owner’s Utilities being adjusted, on the basis of the final approved Plans.  The Developer shall verify that the Owner’s Utilities, whether moving to a new location or remaining in place, clear the planned construction of the Facility as staked in the field as well as the final Work Plan.

(f)	The Owner shall complete all of the Utility reconstruction and relocation work, including final testing and acceptance thereof [check one box that applies]:

on or before ______, 20___.

duration not to exceed _____ calendar days upon notice to proceed by the Developer.

(g)	The amount of reimbursement due to the Owner pursuant to this Agreement for the affected Adjustment(s) shall be reduced by ten percent (10%) for each 30-day period (and by a pro rata amount of said ten percent (10%) for any portion of a 30-day period) by which the final completion and acceptance date for the affected Adjustment(s) exceeds the applicable deadline.  The provisions of this Paragraph 4(g) shall not limit any other remedy available to the Developer at law or in equity as a result of the Owner’s failure to meet any deadline hereunder.

The above reduction applies except to the extent due to (i) Force Majeure as described in Paragraph 25(c), (ii) any act or omission of the   Developer, if the Owner fails to meet any deadline established pursuant to Paragraph 4(f), or (iii) if the  Developer and GDOT determine, in their sole discretion, that a delay in the relocation work is the result of circumstances beyond the control of the Owner or Owner’s Pre-Approved Contractor and the  Developer will not reduce the reimbursement.

5.	Costs of the Work.

(a)	The Owner’s costs for Adjustment of each Owner Utility shall be derived from (i) the accumulated total of costs incurred by the Owner for design and construction of such Adjustment, plus (ii) the Owner’s other related costs to the extent permitted pursuant to Paragraph 5(c) (including without limitation the eligible engineering costs incurred by the Owner for design prior to execution of this Agreement), plus (iii) the Owner’s right of way acquisition costs, if any, which are reimbursable pursuant to Paragraph 16.

(b)	The Owner’s costs associated with Adjustment of the Owner’s Utilities shall be developed pursuant to the method checked and described below [check only one box]:

(1)	Actual costs accumulated in accordance with a work order accounting procedure prescribed by the applicable Federal or State regulatory body (“Actual Cost”); or

(2)	Actual costs accumulated in accordance with an established accounting procedure developed by the Owner and which the Owner uses in its regular operations (“Actual Cost”); or

(3)	The agreed sum of $       (“Agreed Sum”), as supported by the analysis of estimated costs attached hereto as part of Exhibit A.

(c)	Eligible Owner costs shall include only those authorized under 23 C.F.R. Part 645, Subpart A.  The Owner agrees that costs referenced in 23 C.F.R. Section 645.117(d)(2) are not eligible for reimbursement.  These regulations can be found at:

http://www.access.gpo.gov/nara/cfr/waisidx_04/23cfr645_04.html

6.	Responsibility for Costs of Adjustment Work.

The Agreed Sum or Actual Cost, as applicable, of all work to be performed pursuant to this Agreement shall be allocated between the  Developer and the Owner as identified in Exhibit A and in accordance with O.C.G.A. § 32-6-170(b).   An allocation percentage may be determined by application of an Eligibility Ratio, if appropriate, as detailed in Exhibit A; provided, however, that any portion of an Agreed Sum or Actual Cost attributable to Betterment shall be allocated 100% to the Owner in accordance with Paragraph 10.  All costs charged to the Developer by the Owner shall be reasonable and shall be computed using rates and schedules not exceeding those applicable to similar work performed by or for the Owner at the Owner’s expense.  Payment of the costs allocated to the  Developer pursuant to this Agreement (if any) shall be full compensation to the Owner for all costs incurred by the Owner in Adjusting the Owner’s Utilities (including without limitation costs of relinquishing and/or acquiring right of way), and GDOT shall have no liability to the Owner for any such costs.  Owner expressly acknowledges that it shall be entitled to compensation only from the  Developer for any Adjustment costs for the Owner’s Utilities covered by this Agreement, including costs with respect to real property interests (either acquired or relinquished), and specifically acknowledges that it shall not be entitled to compensation or reimbursement from GDOT or the State of Georgia.

7.	Billing, Payment, Records and Audits:  Actual Cost Method.  The following provisions apply if the Owner’s costs are developed under procedure (1) or (2) described in Paragraph 5(b):

(a)	After (i) completion of all Adjustment work to be performed pursuant to this Agreement, (ii) the  Developer’s final inspection of the Adjustment work by Owner hereunder (and resolution of any deficiencies found), and (iii) receipt of an invoice complying with the applicable requirements of Paragraph 9, the  Developer shall pay to the Owner an amount equal to ninety percent (90%) of the  Developer’s share of the Owner’s costs as shown in such final invoice (less amounts previously paid, and applicable credits).  After completion of the  Developer’s audit referenced in Paragraph 7(c) and the parties’ mutual determination of any necessary adjustment to the final invoice resulting therefrom, the  Developer shall make any final payment due so that total payments will equal the total amount of the  Developer’s share reflected on such final invoice (as adjusted, if applicable).

(b)	When requested by the Owner and properly invoiced in accordance with Paragraph 9, the Developer shall make intermediate payments to the Owner based upon the progress of the work completed at not more than monthly intervals, and such payments shall not exceed eighty percent (80%) of the Developer’s share of the Owner’s eligible costs as shown in each such invoice (less applicable credits).  Intermediate payments shall not be construed as final payment for any items included in the intermediate payment.

- The Owner shall maintain complete and accurate cost records for all work performed pursuant to this Agreement, in accordance with the provisions of 23 C.F.R. Part 645, Subpart A.  The Owner shall maintain such records for four (4) years after receipt of final payment hereunder.  The Developer and their respective representatives shall be allowed to audit such records during the Owner’s regular business hours.  Unsupported charges will not be considered eligible for reimbursement.  The parties shall mutually agree upon (and shall promptly implement by payment or refund, as applicable) any financial adjustment found necessary by the Developer’s audit.  GDOT, the Federal Highway Administration, and their respective representatives also shall be allowed to audit such records upon reasonable notice to the Owner, during the Owner’s regular business hours.

8.	Billing and Payment:  Agreed Sum Method.  If the Owner’s costs are developed under procedure (3) described in Paragraph 5(b), then the Developer shall pay its share of the Agreed Sum to the Owner after (a) completion of all Adjustment work to be performed pursuant to this Agreement, (b) the Developer’s final inspection of the Adjustment work by Owner hereunder (and resolution of any deficiencies found), and (c) receipt of an invoice complying with the applicable requirements of Paragraph 9.

9.	Invoices.  Each invoice submitted by the Owner (i) shall be prepared in the form and manner prescribed by 23 C.F.R. Part 645, Subpart A, and (ii) if the Owner’s costs are developed under procedure (1) or (2) described in Paragraph 5(b), shall list each of the services performed, the amount of time spent and the date on which the service was performed.  The original and three (3) copies of each invoice shall be submitted to the Developer at the address for notices stated in Paragraph 23, unless otherwise directed by the Developer pursuant to Paragraph 23, together with (1) such supporting information to substantiate all invoices as reasonably requested by the Developer, and (2) such waivers or releases of liens as the Developer may reasonably require.  The Owner shall make commercially reasonable efforts to submit final invoices not later than one hundred twenty (120) days after completion of work.  Final invoices shall include any necessary quitclaim deeds pursuant to Paragraph 16, and all applicable record drawings accurately representing the Adjustment as installed.  The Owner hereby acknowledges and agrees that any right it may have for reimbursement of any of its costs not submitted to the Developer within eighteen months following completion of all Adjustment work to be performed by both parties pursuant to this Agreement shall be deemed to have been abandoned and waived.  Invoices shall clearly delineate total costs, and those costs that are reimbursable pursuant to the terms of this Agreement.

10.	Betterment.

(a)	For purposes of this Agreement, the term “Betterment” means any upgrading of an Owner’s Utilities” being adjusted that is not attributable to the construction of the Facility and is made solely for the benefit of and at the election of the Owner, including but not limited to an increase in the capacity, capability, efficiency or function of the adjusted Utility over that provided by the existing Utility facility or an expansion of the existing Utility facility; provided, however, that the following are not considered Betterments:

(i)	any upgrading which is required for accommodation of the Facility;

(ii)	replacement devices or materials that are of equivalent standards although not identical;

(iii)	replacement of devices or materials no longer regularly manufactured with the next highest grade or size;

(iv)	any upgrading required by applicable laws, regulations or ordinances;

(v)	replacement devices or materials which are used for reasons of economy (e.g., non-stocked items may be uneconomical to purchase); or

(vi)	any upgrading required by the Owner’s written “standards” meeting the requirements of Paragraph 3(d).

[Include the following for fiber optic Owner’s Utilities only:]  Extension of an Adjustment to the nearest splice boxes shall not be considered a Betterment if required by the Owner in order to maintain its written telephony standards.

Any upgrading required by the Owner’s written “standards” meeting the requirements of Paragraph 3(d) shall be deemed to be of direct benefit to the Facility.

(b)	It is understood and agreed that the Developer will not pay for any Betterments and that the Owner shall not be entitled to payment therefore.  No Betterment may be performed in connection with the Adjustment of the Owner’s Utilities which is incompatible with the Facility or the Ultimate Configuration or which cannot be performed within the other constraints of applicable law, any applicable governmental approvals, and the requirements imposed on the Developer by the DBFA, including without limitation the scheduling requirements there under.  Accordingly, the parties agree as follows [check the one box that applies, and complete if appropriate]:

- (i) The Adjustment of the Owner’s Utilities pursuant to the Plans does not include any Betterment.

- The Adjustment of the Owner’s Utilities pursuant to the Plans includes Betterment to the Owner’s Utilities by reason of [insert explanation, e.g. “replacing 12” pipe with 24” pipe]:      .  The Owner has provided to the Developer comparative estimates for (i) all costs for work to be performed by the Owner pursuant to this Agreement, including work attributable to the Betterment, and (ii) the cost to perform such work without the Betterment, which estimates are hereby approved by the Developer.  The estimated amount of the Owner’s costs for work hereunder which is attributable to Betterment is $     , calculated by subtracting (ii) from (i).  The percentage of the total cost of the Owner’s work hereunder which is attributable to Betterment is      %, calculated by subtracting (ii) from (i), which remainder shall be divided by (i).

(c)	If Paragraph 10(b) identifies Betterment, then the following shall apply:

(i)	If the Owner’s costs are developed under procedure (3) described in Paragraph 5(b), then the Agreed Sum stated in that Paragraph includes any credits due to the Developer on account of the identified Betterment, and no further adjustment shall be made on account of same.

(ii)	If the Owner’s costs are developed under procedure (1) or (2) described in Paragraph 5(b), the parties agree as follows [If Paragraph 10(b) identifies Betterment and the Owner’s costs are developed under procedure (1) or (2), check the one appropriate provision]:

- The estimated cost stated in Paragraph 10(b) is the agreed and final amount due for Betterment hereunder.  Accordingly, each intermediate invoice submitted pursuant to Paragraph 7(b) shall include a credit for an appropriate percentage of the agreed Betterment amount, proportionate to the percentage of completion reflected in such invoice.  The final invoice submitted pursuant to Paragraph 7(a) shall reflect the full amount of the agreed Betterment credit.  For each invoice described in this paragraph, the credit for Betterment shall be applied before calculating the Developer’s share (pursuant to Paragraph 6) of the cost of the Adjustment work. No other adjustment (either up or down) shall be made based on actual Betterment costs.

- The Owner is responsible for the actual cost of the identified Betterment, determined by multiplying (a) the Betterment percentage stated in Paragraph 10(b), by (b) the actual cost of all work performed by the Owner pursuant to this Agreement (including work attributable to the Betterment), as invoiced by the Owner to the  Developer.  Accordingly, each invoice submitted pursuant to either Paragraph 7(a) or Paragraph 7(b) shall credit the Developer with an amount calculated by multiplying (x) the Betterment percentage stated in Paragraph 10(b), by (y) the amount billed on such invoice.

(d)	The determinations and calculations of Betterment described in this Paragraph 10 shall exclude right of way acquisition costs.  Betterment in connection with right-of-way acquisition is addressed in Paragraph 16.

11.	Salvage.  For any Adjustment from which the Owner recovers any materials and/or parts and retains or sells the same, after application of any applicable Betterment credit, the  Developer is entitled to a credit for the salvage value of such materials and/or parts, determined in accordance with 23 C.F.R. Section 645.105(j).  If the Owner’s costs are developed under procedure (1) or (2) described in Paragraph 5(b), then the final invoice submitted pursuant to Paragraph 7(a) shall credit the Developer with the full salvage value.  If the Owner’s costs are developed under procedure (3) described in Paragraph 5(b), then the Agreed Sum includes any credit due to the Developer on account of salvage.

12.	Utility Investigations.  At the Developer’s request, the Owner will assist the Developer in locating any Utilities (including appurtenances) which are owned and/or operated by Owner and may be impacted by the Facility.  Without limiting the generality of the foregoing, in order to help assure that neither the adjusted Owner’s Utilities nor existing, unadjusted utilities owned or operated by the Owner are damaged during construction of the Facility, the Developer shall adhere to O.C.G.A 25-9 Georgia Utility Protection Act.

13.	Inspection and Ownership of Owner’s Utilities.

(a)	The Developer shall have the right, at its own expense, to inspect the Adjustment work performed by the Owner or its Developers, during and upon completion of construction.  All inspections of work shall be completed and any comment provided within five (5) business days after request for inspection is received.

(b)	The Owner shall accept full responsibility for all future repairs and maintenance of said Owner’s Utilities.  In no event shall the Developer or GDOT become responsible for making any repairs or maintenance, or for discharging the cost of same.  The provisions of this Paragraph 13(b) shall not limit any rights which the Owner may have against the Developer if either party respectively damages any Owner Utility as a result of its respective Facility activities.

- Design Changes.  The Developer will be responsible for additional Adjustment design and the Developer will be responsible for additional construction costs necessitated by design changes to the Facility made after approval of the Plans, upon the terms specified herein.

15.	Field Modifications.  The Owner shall provide the Developer with documentation of any field modifications, including Utility Adjustment Field Modifications as well as minor changes as described in Paragraph 17(b), occurring in the Adjustment of the Owner’s Utilities.

# 16.	Real Property Interests.

(a)	The Owner has provided, or upon execution of this Agreement shall promptly provide to the Developer, documentation acceptable to GDOT indicating any right, title or interest in real property claimed by the Owner with respect to the Owner’s Utilities in their existing location(s).  Such claims are subject to GDOT’s approval as part of its review of the Developer’s Utility Work Plan as described in Paragraph 2.  Claims approved by GDOT as to rights or interests are referred to herein as “Existing Interests”.

(b)	If acquisition of any new easement or other interest in real property (“New Interest”) is necessary for the Adjustment of any Owner’s Utilities, then the Owner shall be responsible for undertaking such acquisition.  The Owner shall implement each acquisition hereunder expeditiously so that related Adjustment construction can proceed in accordance with the Developer’s Facility schedules.  The  Developer shall be responsible for its share (if any, as specified in Paragraph 6) of the actual and reasonable acquisition costs of any such New Interest (including without limitation the Owner’s reasonable overhead charges and reasonable legal costs as well as compensation paid to the landowner), excluding any costs attributable to Betterment as described in Paragraph 16(c), and subject to the provisions of Paragraph 16(e); provided, however, that all acquisition costs shall be subject to the  Developer’s prior written approval.  Eligible acquisition costs shall be segregated from other costs on the Owner’s estimates and invoices.  Any such New Interest shall have a written valuation and shall be acquired in accordance with applicable law.

(c)	The  Developer shall pay its share only for a replacement in kind of an Existing Interest (e.g., in width and type), unless a New Interest exceeding such standard (i) is required in order to accommodate the Facility or by compliance with applicable law, or (ii) is called for by the  Developer in the interest of overall Facility project economy.  Any New Interest which is not the Developer’s cost responsibility pursuant to the preceding sentence shall be considered a Betterment to the extent that it upgrades the Existing Interest which it replaces, or in its entirety if the related Owner Utility was not installed pursuant to an Existing Interest.  Betterment costs shall be solely the Owner’s responsibility.

(d)	For each Existing Interest located within the final Facility right of way, upon completion of the related Adjustment work and its acceptance by the Owner, the Owner agrees to execute a quitclaim deed or other appropriate documentation relinquishing such Existing Interest to GDOT, unless the affected Owner Utility is remaining in its original location or is being reinstalled in a new location within the area subject to such Existing Interest.  All quitclaim deeds or other relinquishment documents shall be subject to GDOT’s approval as part of its review of the Utility Work Plan as described in Paragraph 2.  For each such Existing Interest relinquished by the Owner, the Developer shall do one of the following to compensate the Owner for such Existing Interest, as appropriate:

(i)	If the Owner acquires a New Interest for the affected Owner Utility, the  Developer shall reimburse the Owner for the  Developer’s share of the Owner’s actual and reasonable acquisition costs in accordance with Paragraph 16(b) and subject to Paragraph 16(c); or

(ii)	If the Owner does not acquire a New Interest for the affected Owner Utility, the Developer shall compensate the Owner for the Developer’s share of the fair market value of such relinquished Existing Interest, as mutually agreed between the Owner and the Developer and supported by a written valuation.

The compensation, if any, provided to the Owner pursuant to either subparagraph (i) or subparagraph (ii) above shall constitute complete compensation to the Owner for the relinquished Existing Interest and any New Interest, and no further compensation shall be due to the Owner from the  Developer or GDOT on account of such Existing Interest or New Interest(s).

(e)	The Owner shall complete a Utility Permit in the Georgia Utility Permit System (GUPS) for each Adjustment where required pursuant to GDOT policies.  All Utility Permits shall be subject to GDOT approval as part of its review of the Utility Work Plan as described in Paragraph 2.

# 17.	Amendments and Modifications.  This Agreement may be amended or modified only by a written instrument executed by the parties hereto, in accordance with Paragraph 17(a) or Paragraph 17(b) below.

- Except as otherwise provided in Paragraph 17(b), any amendment or modification to this Agreement or the Plans attached hereto shall be implemented by a Master Utility Adjustment Agreement Amendment (“MUAAA”) in the form of Exhibit B. The MUAAA form can be used for a new scope of work with concurrence of the Developer and GDOT as long as the Design and Construction responsibilities have not changed.  Each MUAAA is subject to the review and approval of GDOT prior to its becoming effective for any purpose and prior to any work being initiated there under.  The Owner agrees to keep and track costs for each MUAAA separately from other work being performed.

- For purposes of this Paragraph 17(b), “Utility Adjustment Field Modification” shall mean any horizontal or vertical design change from the Plans included in a Utility Work Plan previously approved by GDOT, due either to design of the Facility or to conditions not accurately reflected in the approved Utility Work Plan (e.g., shifting the alignment of an 8 in. water line to miss a modified or new roadway drainage structure).  A Utility Adjustment Field Modification agreed upon by the Developer and the Owner does not require a MUAAA, provided that the modified Plans have been submitted to GDOT for its review and comment.  A minor change (e.g., an additional water valve, an added Utility marker at a ROW line, a change in vertical bend, etc.) will not be considered a Utility Adjustment Field Modification and will not require a MUAAA, but shall be shown in the documentation required pursuant to Paragraph 15.

18.	Entire Agreement.  This Agreement embodies the entire agreement between the parties and there are no oral or written agreements between the parties or any representations made which are not expressly set forth herein.

19.	Assignment; Binding Effect; GDOT as Third Party Beneficiary.  Neither the Owner or the  Developer may assign any of its rights or delegate any of its duties under this Agreement without the prior written consent of the other parties and of GDOT, which consent may not be unreasonably withheld or delayed; provided, however, that the  Developer may assign any of its rights and/or delegate any of its duties to GDOT or to any other entity with which GDOT contracts to fulfill the Developer’s obligations under the DBFA, at any time without the prior consent of the Owner.

This Agreement shall bind the Owner, the  Developer and their successors and permitted assigns, and nothing in this Agreement nor in any approval subsequently provided by any party hereto shall be construed as giving any benefits, rights, remedies, or claims to any other person, firm, corporation or other entity, including, without limitation, any Developer or other party retained for the Adjustment work or the public in general; provided, however, that the Owner, the  Developer agree that although GDOT is not a party to this Agreement, GDOT is intended to be a third-party beneficiary to this Agreement.

20.	Breach by the Parties.

(a)	If the Owner claims that the  Developer (the “Defaulting Party”) has breached any of its obligations under this Agreement, the Owner will notify the  Developer and GDOT in writing of such breach, and the Developer shall have 30 days following receipt of such notice in which to cure such breach, before the Owner may invoke any remedies which may be available to it as a result of such breach; provided, however, that both during and after such period GDOT shall have the right, but not the obligation, to cure any breach by the Defaulting Party.  Without limiting the generality of the foregoing, (a) GDOT shall have no liability to the Owner for any act or omission committed by the Defaulting Party in connection with this Agreement, including without limitation any reimbursement owed to the Owner hereunder, and (b) in no event shall GDOT be responsible for any repairs or maintenance to the Owner’s Utilities adjusted pursuant to this Agreement.

(b)	If the Developer claims that the Owner has breached any of its obligations under this Agreement, the Developer will notify the Owner and GDOT in writing of such breach, and the Owner shall have 30 days following receipt of such notice in which to cure such breach, before the Developer may invoke any remedies which may be available to it as a result of such breach.

21.	Traffic Control.  The Developer shall provide traffic control or shall reimburse the Owner for the Developer’s share (if any, as specified in Paragraph 6) of the costs for traffic control made necessary by the Adjustment work performed by either the Developer or the Owner pursuant to this Agreement, in compliance with the requirements of the Manual on Uniform Traffic Control Devices.  Betterment percentages calculated in Paragraph 10 shall also apply to the traffic control costs.

22.	Notices.  Except as otherwise expressly provided in this Agreement, all notices or communications pursuant to this Agreement shall be sent or delivered to the following:

The Owner:

Phone:

Fax:

The Developer:

Phone:

Fax:

A party sending a notice of default of this Agreement to another party shall also send a copy of such notice to GDOT and to the DBFA Utility Manager at the following addresses:

GDOT: 		GDOT Department of Transportation

Attention: _________________

Address: __________________

__________________________

City & State: ________________

Phone:  ____________________

Utility Manager		Name: _____________________

Attention: __________________

Address: ___________________

___________________________

City & State: ________________

Phone:_____________________

Any notice or demand required herein shall be given (a) personally, (b) by certified or registered mail, postage prepaid, return receipt requested, or (c) by reliable messenger or overnight courier to the appropriate address set forth above.  Any notice served personally shall be deemed delivered upon receipt and served by certified or registered mail or by reliable messenger or overnight courier shall be deemed delivered on the date of receipt as shown on the addressee’s registry or certification of receipt or on the date receipt is refused as shown on the records or manifest of the U.S. Postal Service or such courier.  Any party may from time to time designate any other address for this purpose by written notice to all other parties; GDOT may designate another address by written notice to all parties.

23.	Approvals.  Any acceptance, approval, or any other like action (collectively “Approval”) required or permitted to be given by the Developer, or the Owner pursuant to this Agreement:

- (a)	Must be in writing to be effective (except if deemed granted pursuant hereto),

- (b)	Shall not be unreasonably withheld or delayed; and if Approval is withheld, such withholding shall be in writing and shall state with specificity the reason for withholding such Approval, and every effort shall be made to identify with as much detail as possible what changes are required for Approval, and

- (c)	Except for approvals by GDOT, and except as may be specifically provided otherwise in this Agreement, shall be deemed granted if no response is provided to the party requesting an Approval within the time period prescribed by this Agreement (or if no time period is prescribed, then fourteen (14) calendar days), commencing upon actual receipt by the party from which an Approval is requested or required, of a request for Approval from the requesting party.  All requests for Approval shall be sent out by the requesting party to the other party in accordance with Paragraph 23.

24.	Time; Force Majeure.

(a)	Time is of the essence in the performance of this Agreement.

(b)	All references to “days” herein shall be construed to refer to calendar days, unless otherwise stated.

(c)	No party shall be liable to another party for any delay in performance under this Agreement from any cause beyond its control and without its fault or negligence (“Force Majeure”), such as acts of God, acts of civil or military authority, fire, earthquake, strike, unusually severe weather, floods or power blackouts. If any such event of Force Majeure occurs, the Owner agrees, if requested by the Developer, to accelerate its efforts hereunder if reasonably feasible in order to regain lost time, so long as the Developer agrees to reimburse the Owner for the reasonable and actual costs of such efforts.

25.	GDOT Review and Approval.  Notwithstanding any contrary provision of this Agreement, if this Agreement and the DBFA call for different levels of review for any items submitted to GDOT (e.g., “approval” as opposed to “review and comment”), then the level of review called for by the DBFA will prevail for purposes of this Agreement.

26.	Continuing Performance.  In the event of a dispute, the Owner, the  Developer agree to continue their respective performance hereunder to the extent feasible in light of the dispute, including paying billings, and such continuation of efforts and payment of billings shall not be construed as a waiver of any legal right.

27.	Equitable Relief.  The Developer and the Owner acknowledge and agree that delays in Adjustment of the Owner’s Utilities will impact the public convenience, safety and welfare, and that (without limiting the parties’ remedies hereunder) monetary damages would be inadequate to compensate for delays in the construction of the Facility.  Consequently, the parties hereto (and GDOT as well, as a third party beneficiary) shall be entitled to specific performance or other equitable relief in the event of any breach of this Agreement which threatens to delay construction of the Facility; provided, however, that the fact that specific performance or other equitable relief may be granted shall not prejudice any claims for payment or otherwise related to performance of the Adjustment work hereunder.

28.	Authority.  The Owner and the  Developer each represents and warrants to the other party that the warranting party possesses the legal authority to enter into this Agreement and that it has taken all actions necessary to exercise that authority and to lawfully authorize its undersigned signatory to execute this Agreement and to bind such party to its terms.  Each person executing this Agreement on behalf of a party warrants that he or she is duly authorized to enter into this Agreement on behalf of such party and to bind it to the terms hereof.

29.	Cooperation.  The parties acknowledge that the timely completion of the Facility will be influenced by the ability of the Owner (and its Pre-Approved Contractors), and the Developer to coordinate their activities, communicate with each other, and respond promptly to reasonable requests.  Subject to the terms and conditions of this Agreement, the Owner and, the Developer agree to take all steps reasonably required to coordinate their respective duties hereunder in a manner consistent with the Developer’s current and future construction schedules for the Facility.  The Owner further agrees to require its contractors to coordinate their respective work hereunder with the Developer.

30	Termination.  If the Facility project is canceled or modified so as to eliminate the necessity of the Adjustment work described herein, then the Developer shall notify the Owner in writing and the Developer reserves the right to thereupon terminate this Agreement.  Upon such termination, the parties shall negotiate in good faith an amendment that shall provide mutually acceptable terms and conditions for handling the respective rights and liabilities of the parties relating to such termination.

31.	Nondiscrimination.  Each party hereto agrees, with respect to the work performed by such party pursuant to this Agreement that such party shall not discriminate on the grounds of race, color, sex, national origin or disability in the selection and/or retention of Developers and consultants, including procurement of materials and leases of equipment.

# 32.	Applicable Law, Jurisdiction and Venue.  This Agreement shall be governed by the laws of the State of Georgia, without regard to the conflict of laws principles thereof.  Venue for any action brought to enforce this Agreement or relating to the relationship between any of the parties shall be the District Court of _________ County, Georgia or the United States District Court for the ______________ District of Georgia.  To the extent that the Department is a desired or necessary party to a legal action under this Agreement, venue and jurisdiction for said action shall only be in the Superior Court of Fulton County, Georgia.  Nothing in this agreement waives the State of Georgia’s and the Department’s Eleventh Amendment immunity from suit in federal court.

33.	Waiver of Consequential Damages.  No party hereto shall be liable to any other party to this Agreement, whether in contract, tort, equity, or otherwise (including negligence, warranty, indemnity, strict liability, or otherwise), for any punitive, exemplary, special, indirect, incidental, or consequential damages, including, without limitation, loss of profits or revenues, loss of use, claims of customers, or loss of business opportunity.

34.	Captions.  The captions and headings of the various paragraphs of this Agreement are for convenience and identification only, and shall not be deemed to limit or define the content of their respective paragraphs.

35.	Counterparts.  This Agreement may be executed in any number of counterparts.  Each such counterpart hereof shall be deemed to be an original instrument but all such counterparts together shall constitute one and the same instrument.

36.	Effective Date.  Except for the provisions of Paragraph 2(a) (which shall become effective immediately upon execution of this Agreement by the Owner, the Developer without regard to GDOT’s signature), this Agreement shall become effective upon the later of (a) the date of signing by the last party (either the Owner, the Developer) signing this Agreement, and (b) the date of GDOT’s approval as indicated by the signature of GDOT’s representative, below.

| APPROVED BY: GEORGIA DEPARTMENT OF TRANSPORTATION By: Authorized Signature | UTILITY OWNER [Print Owner Name] By: Duly Authorized Representative |
| --- | --- |
| Printed Name: Title: Date: | Printed Name: Title: Date: |
| DEVELOPER Name:___________________________________ By: Duly Authorized Representative |  |
| Printed Name: Title: Date: ____________________________________ |  |

# Exhibit A

PLANS, SPECIFICATIONS, COST ESTIMATES AND ALLOCATION

# Exhibit B

MASTER UTILITY ADJUSTMENT AGREEMENT AMENDMENT

# Exhibit c

STATEMENT COVERING CONTRACT WORK