## Instructions
Purpose statement: The use of this conflict matrix provides the advantage of tracking conflicts with existing utilities and proposed roadway design and is intended to follow the life of the project. This document is used to assist with utility coordination by identifying utility conflicts, the need for SUE QL-A, mitigation measures, and cost/time estimates.
INSTRUCTIONS:
1. Please do not change the format of this sheet. Initial submittal should start after 1st submission and be completed prior to PURP Meeting of PFPR.
2. The initial submittal will only include columns A-F and N.
3. The remaining columns will be used to assist with on-going coordination as needed.
4. "Station & Offset" column: Provide the Main Line or Side Street Base Line Station and Offset, as appropriate. For Side Streets Only: Include street name.
5. "Utility Type": Provide the type of utility and color code according to utility. The color code can be found on the Georgia Utilities Protection Center website at www.georgia811.com
6. "Utility Company": Provide the name of type of utility. The Utility Owners list are examples only. Provide abbreviations as shown in the plans and appropriate for the project.
7. "Existing Utility" column: Show the Size, & Material Type; i.e. 4" Steel.
8. " Identified Conflict" column: Please include the size of proposed pipe, cut/fill depths and length, structure ID#, erosion control measure type (i.e. Sd1-C), etc.
9. "TH (Y/N)#" column: Reserved for the decisions made during PURP Meeting or coordinating with GDOT, designer, and/or utility owner.
10. "TH#" column: Reserved for the decisions made once test holes are performed and should correspond to the test hole number in the plans.
11. "Utility Impact (As designed)" - Provide approximate impact to cost and/or time. To be completed during PURP or coordinated between Utility Coordinator and utility owner.
12. "Recommended resolution": Provide recommendations that were made at PURP, FPR, or through other coordination efforts (i.e. utility avoidance, utility relocation, etc.). Recommended to be completed by the Designer.
13. "Benefit of resolution": Provide cost savings and/or time savings benefits. Recommended to be completed by the Utility Coordinator
14. For conflicts that have a range provide same conflict number at begin point and end point. (ex. Telecom is in conflict with cut limits from station 20+00 to 40+00 so there should be a conflict circle at both stations with the same conflict number.
15. For places where there are multiple utilities at one point of conflict, provide a separate entry for each utility with the same conflict number. Provide one conflict circle on the plans and multiple rows for each conflict in the matrix.

## Sample Sheet 1
C# | Station & Offset | Utility Type | Utility Company | Existing Utility | Identified Conflict | TH (Y/N) | TH# | Utility Impact ("As-designed") |  | Recommended Resolution | Benefit of Resolution (cost and/or time) |  | Comment | UTILITY KEY
[8 empty] | Cost | Time |  | Cost | Time |  | Underground
E - Electric
G - Gas
NW - Non-Potable Water
P - Petroleum
SFM - Sanitary Sewer
SS - Sanitary Sewer
STM -Steam
T - Telecommunications
TC - Traffic Control
TV - Cable TV
UNK - Unknown Type
W - Water
Overhead
OE - Overhead Electric
OGW - Overhead Guy Wire
OT - Overhead Telecommunications
OTC - Overhead Traffic Control
OTV - Overhead Cable TV
UTILITY OWNERS
AGL - Atlanta Gas Light
GP - Georgia Power
ATT - AT&T (formerly BellSouth)
L3 - Level 3 Communications
MFN - Metromedia Fiber Network
FCPW - Fulton County Public Works
CoA - City of Atlanta
UNK - Unknown Owner
ABBREVIATIONS
Material
AC - Asbestos Concrete
FO - Fiber Optic
MES - Mitered End Section
RCP - Reinforced Concrete Pipe
Other
BL - Baseline
TH - Test Hole
L - Left; R - Right
Y - Yes; N - No
Note on C3: Provide type and color code according to utility
Note on D3: Provide owner abreviations as shown in plans and UIA legend.
Note on E3: Provide size and type (i.e. 4" Steel)
Note on F3: Provide size of proposed pipe, cut/fill depths and length, structure ID#, (i.e. drainage structure C-2)
Note on H3: Made once test holes are performed and should correspond to the test hole number in the plans.
Note on I3: Provide impact to cost and/or time. (i.e. 2mil relocation cost and/or 24 months relocation time
Note on K3: Provide recommendations (i.e. utility avoidance, minimize, utility relocation, etc.)
Note on L3: Provide cost and/or time savings benefit of resolution. (i.e.1mil relocation cost savings and/or 18 months utility relocation time savings

## Sample Sheet 2
C# | Station & Offset | Utility Type | Utility Company | Existing Utility | Identified Conflict | TH (Y/N) | TH# | Utility Impact ("As-designed") |  | Recommended Resolution | Benefit of Resolution (cost and/or time) |  | Comment | UTILITY KEY
[8 empty] | Cost | Time |  | Cost | Time |  | Underground | Underground
[14 empty] | E - Electric | E
[14 empty] | G - Gas | G
[14 empty] | NW - Non-Potable Water | NW
[14 empty] | P - Petroleum | P
[14 empty] | SFM - Sanitary Sewer | SFM
[14 empty] | SS - Sanitary Sewer | SS
[14 empty] | STM -Steam | STM
[14 empty] | T - Telecommunications | T
[14 empty] | TC - Traffic Control | TC
[14 empty] | TV - Cable TV | TV
[14 empty] | UNK - Unknown Type | UNK
[14 empty] | W - Water | W
Overhead
OE - Overhead Electric
OGW - Overhead Guy Wire
OT - Overhead Telecommunications
OTC - Overhead Traffic Control
OTV - Overhead Cable TV
UTILITY OWNERS
AGL - Atlanta Gas Light
GP - Georgia Power
ATT - AT&T (formerly BellSouth)
L3 - Level 3 Communications
MFN - Metromedia Fiber Network
FCPW - Fulton County Public Works
CoA - City of Atlanta
UNK - Unknown Owner
ABBREVIATIONS
Material
AC - Asbestos Concrete
FO - Fiber Optic
MES - Mitered End Section
RCP - Reinforced Concrete Pipe
Other
BL - Baseline
TH - Test Hole
L - Left; R - Right
Y - Yes; N - No
Note on C3: Provide type and color code according to utility
Note on D3: Provide owner abreviations as shown in plans and UIA legend.
Note on E3: Provide size and type (i.e. 4" Steel)
Note on F3: Provide size of proposed pipe, cut/fill depths and length, structure ID#, (i.e. drainage structure C-2)
Note on H3: Made once test holes are performed and should correspond to the test hole number in the plans.
Note on I3: Provide impact to cost and/or time. (i.e. 2mil relocation cost and/or 24 months relocation time
Note on K3: Provide recommendations (i.e. utility avoidance, minimize, utility relocation, etc.)
Note on L3: Provide cost and/or time savings benefit of resolution. (i.e.1mil relocation cost savings and/or 18 months utility relocation time savings